## Population
Population estimates
SN | Location | Population |  | Health | Public sec | Energy | W & S | Municipal | garbage | 2020-05-14 | EU | Misc
1 | Ajdabiya | 297934
2 | Bani Walid | 76829 |  | 76829 | 76829 | 76829 | 76829 |  | 76829 |  | 76829
3 | Benghazi | 1093663 |  | 1093663 | 1093663 | 1093663 | 1093663 |  | 1093663 |  | 1093663 | 1093663
4 | Derna | 260199
5 | Ghat | 39448 |  |  |  | 39448 | 39448 |  |  |  | 39448
6 | Kikla | 17892 |  | 17892 | 17892 | 17892 |  |  |  |  | 17892 | 17892
7 | Kufra | 74134 | [5 empty] | 74134 |  |  | 74134
8 | Misrata | 785984
9 | Sebha | 212159 |  | 212159 |  | 212159 | 212159 | 212159 |  |  | 212159
10 | Sirt | 241984 |  | 241984 |  |  |  |  | 241984 |  | 241984 | 241984
11 | Tawergha | 24223 |  | 24223 |  | 24223 |  | 24223 |  |  | 24223
12 | Tripoli | 1749347 |  | 1749347 |  |  | 672825.7692 |  | 1749347 |  | 1749347
13 | Ubari | 133652 |  | 133652 | 133652 |  |  | 133652 | 133652 |  | 133652 | 133652
| Total | 5007448 |  | 3549749 | 1322036 | 1464214 | 2094924.7692 | 444168 | 3295475 |  | 3663331 | 1487191
Tripoli Municipalities
SN | Location | Population
1 | Abu Salim | 256855 | 0 | 256855
2 | Al-Swani | 53528
3 | Al-Ssabiaa | 55000 |  | 55000
4 | Ein Zara | 114018 |  | 114018
5 | Central Tripoli | 157733 |  | 157733
6 | Al-Garabouli | 51481
7 | Hay Al-Andoules | 280043
8 | Janzour | 144097
9 | Ben Gashir | 97402
10 | Sidi Al-Sayah | 25644
11 | Souq Al-Gomma | 276674 |  | 276674
12 | Souq Al-Khamees | 27758
13 | Tajoura | 209114 |  | 209114
| Total | 1749347 |  | 1069394
Note on D14: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2006 est wiki
Note on D24: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: as received from Saeed Zekry

## Location
Location | Latitude | Longitude
Ajdabiya | 30.9287 | 20.2538
Bani Walid | 31.8057 | 14.0536
Benghazi | 32.1298 | 20.0876
Bent Baya | 26.6847 | 13.6626
Derna | 32.7579 | 22.6379
Ghat | 25.0411 | 10.1602
Kikla | 32.0617 | 12.6963
Kufra | 23.662 | 21.9202
Misurata | 32.335 | 15.1013
Sebha | 27.0459 | 14.429
Sirt | 31.1922 | 16.5695
Tawergha | 32.0226 | 15.055
Tripoli | 32.8901 | 13.1912
Ubari | 26.5836 | 12.7939

## Tracker
Works / Goods | Region | Location | Sector | Project | Funding Stage | Amount | Expenditure | Initial Phase Status | Procurement Phase Status | Contract Signing | Implementation Phase Status | Site handover date | Start Date | Actual completion date | Overall Status | Type | Project ID | Latitude | Longitude | Donor | Implementation_duration
Goods | West | Sirt | Solid Waste Management | Supply of Garbage Trucks | Phase 1 | 592330.7558 | 592588.3309 | Completed | PO + Contract issuance done | 2017-10-01 | Substantial completion / handover done |  |  | 2018-07-24 | Completed | Garbage truck | 98720 | 31.2103 | 16.4923 | EU | 296
Goods | West | Sirt | Solid Waste Management | Supply of Garbage Trucks | Phase 1 | 885386.3895 | 0 | To be initiated | [6 empty] | In Development | Truck
Goods | West | Sirt | Solid Waste Management | Supply of Garbage Trucks | Phase 1 | 505202.5674 | 0 | To be initiated | [6 empty] | In Development | Garbage truck
Goods | West | Sirt | Solid Waste Management | Supply of Garbage Trucks | Phase 1 | 794730.1535 | 0 | To be initiated | [6 empty] | In Development | Truck
Goods | West | Sirt | Solid Waste Management | Supply of Garbage Bins | Phase 1 | 48357.8675 | 48357.8675 | Completed | PO + Contract issuance done | 2017-10-01 | Substantial completion / handover done |  |  | 2018-07-26 | Completed | Garbage Bin | 98720 | 31.2096 | 16.4925 | EU | 298
Goods | West | Sirt | Solid Waste Management | Supply of Garbage Bins | Phase 1 | 26331.5703 | 0 | To be initiated | [6 empty] | In Development | Garbage Bin
Goods | West | Sirt | WASH | Supply of Sewage Suction Trucks | Phase 1 | 222241.0919 | 0 | To be initiated | [6 empty] | In Development | Sewage suction truck
Works | West | Sirt | Health | Rehabilitation of Clinic | Phase 1 | 83941.1089 | 83941.1089 | Completed | PO + Contract issuance done | 2018-03-29 | Substantial completion / handover done | 2018-04-09 | 2018-04-16 | 2018-08-28 | Completed | Clinic | 98720 | 31.198 | 16.576 | EU | 152
Goods | West | Sirt | Health | Supply of Freezers | Phase 1 | 48281.9072 | 48281.9072 | Completed | PO + Contract issuance done | 2020-10-10 | Substantial completion / handover done | 2020-10-22 | 2020-10-28 | 2021-03-28 | Completed | Other health building | 98720 | 31.184 | 16.582 | France | 169
Goods | West | Sirt | Health | Supply of Ambulances | Phase 1 | 85445.3144 | 93101.9842 | Completed | PO + Contract issuance done | 2017-02-01 | Substantial completion / handover done |  |  | 2017-12-31 | Completed | Ambulance | 98720 | 31.1876 | 16.5897 | South Korea | 333
Works | West | Sirt | Health | Rehabilitation of Clinic | Phase 1 | 49276.8937 | 0 | BOQ development stage | [6 empty] | In Development | Clinic
Works | West | Sirt | Health | Rehabilitation of Clinic | Phase 1 | 39032.8204 | 39032.8204 | Completed | PO + Contract issuance done | 2019-08-05 | Substantial completion / handover done | 2019-09-03 |  | 2020-03-22 | Completed | Clinic | 112158 | 31.2083 | 16.5711 | South Korea | 230
Works | West | Sirt | Health | Rehabilitation of Clinic | Phase 1 | 18984.6069 | 18984.6069 | Completed | PO + Contract issuance done | 2018-12-07 | Substantial completion / handover done | 2019-01-03 | 2019-01-10 | 2019-03-31 | Completed | Clinic | 98720 | 31.1754 | 16.5944 | Japan | 114
Works | West | Sirt | Health | Rehabilitation of Clinic | Phase 1 | 23862.1006 | 23862.1006 | Completed | PO + Contract issuance done | 2019-07-05 | Substantial completion / handover done |  |  | 2019-10-28 | Completed | Clinic | 112158 | 31.2089 | 16.5596 | Germany | 115
Works | West | Sirt | Health | Rehabilitation of Clinic | Phase 1 | 18463.3032 | 18562.7885 | Completed | PO + Contract issuance done | 2018-11-13 | Substantial completion / handover done | 2018-11-30 | 2018-12-07 | 2019-03-15 | Completed | Clinic | 112158 | 31.1886 | 16.4173 | EU | 122
Works | West | Sirt | Education | Rehabilitation of School | Phase 1 | 89867.9497 | 88825.0129 | Completed | PO + Contract issuance done | 2017-11-11 | Substantial completion / handover done | 2017-11-20 | 2017-11-27 | 2018-02-05 | Completed | School | 98720 | 31.2079 | 16.5728 | Germany | 86
Works | West | Sirt | Education | Rehabilitation of School | Phase 1 | 39672.1347 | 39672.1347 | Completed | PO + Contract issuance done | 2018-07-25 | Substantial completion / handover done | 2017-09-06 | 2017-09-13 | 2018-12-25 | Completed | School | 98720 | 31.2052 | 16.5972 | Germany | 153
Works | West | Sirt | Education | Rehabilitation of School | Phase 1 | 43275.2108 | 43087.7994 | Completed | PO + Contract issuance done | 2017-11-16 | Substantial completion / handover done | 2017-12-02 | 2017-12-09 | 2018-07-28 | Completed | School | 98720 | 31.2067 | 16.5877 | Germany | 254
Works | West | Sirt | Education | Rehabilitation of School | Phase 1 | 81050.6416 | 81050.6416 | Completed | PO + Contract issuance done | 2017-11-09 | Substantial completion / handover done | 2017-11-19 | 2017-11-26 | 2018-03-25 | Completed | School | 98720 | 31.2101 | 16.5703 | Germany | 136
Works | West | Sirt | Education | Rehabilitation of School | Phase 1 | 58317.7648 | 58317.7648 | Completed | PO + Contract issuance done | 2017-12-17 | Substantial completion / handover done | 2017-12-25 | 2018-01-01 | 2018-04-24 | Completed | School | 98720 | 31.2099 | 16.5862 | EU | 128
Works | West | Sirt | Education | Rehabilitation of School | Phase 1 | 198566.2847 | 198496.8897 | Completed | PO + Contract issuance done | 2018-11-08 | Substantial completion / handover done | 2018-11-30 | 2018-12-04 | 2019-04-04 | Completed | School | 98720 | 31.1778 | 16.5967 | Canada | 147
Works | West | Sirt | Education | Rehabilitation of School | Phase 1 | 30779.8454 | 30692.6358 | Completed | PO + Contract issuance done | 2018-11-13 | Substantial completion / handover done | 2018-11-30 | 2018-12-07 | 2019-03-15 | Completed | School | 112158 | 31.1874 | 16.4175 | EU | 122
Works | West | Sirt | Education | Rehabilitation of School | Phase 1 | 177684.7519 | 177684.7519 | Completed | PO + Contract issuance done | 2019-05-27 | Substantial completion / handover done | 2019-06-11 |  | 2019-10-20 | Completed | School | 112158 | 31.2073 | 16.5791 | EU | 146
Works | West | Sirt | Education | Rehabilitation of School | Phase 1 | 190090.894 | 190090.894 | Completed | PO + Contract issuance done | 2018-11-13 | Substantial completion / handover done | 2018-11-28 | 2018-12-06 | 2019-04-14 | Completed | School | 98720 | 31.2067 | 16.5604 | Norway | 152
Works | West | Sirt | Education | Rehabilitation of School | Phase 1 | 36440.281 | 36440.281 | Completed | PO + Contract issuance done | 2018-12-11 | Substantial completion / handover done | 2018-12-31 | 2019-01-07 | 2019-03-27 | Completed | Other Educational building | 98720 | 31.1992 | 16.594 | UK | 106
Works | West | Sirt | Education | Rehabilitation of School | Phase 1 | 190689.5227 | 190689.5227 | Completed | PO + Contract issuance done | 2019-05-27 | Substantial completion / handover done | 2019-09-02 | 2019-09-09 | 2019-12-25 | Completed | Other Educational building | 112158 | 31.2093 | 16.5869 | EU | 212
Works | West | Sirt | Education | Rehabilitation of School | Phase 1 | 224318.402 | 224318.402 | Completed | PO + Contract issuance done | 2019-05-21 | Substantial completion / handover done |  | 2019-06-03 | 2019-12-08 | Completed | Other Educational building | 112158 | 31.2088 | 16.5709 | Netherlands | 201
Goods | West | Sirt | Health | Supply of Ambulances | Phase 1 | 65089.0348 | 82620.9385 | Completed | PO + Contract issuance done | 2017-02-01 | Substantial completion / handover done |  |  | 2017-12-31 | Completed | Ambulance | 98720 | 31.1838 | 16.5843 |  | 333
Goods | West | Sirt | Health | Supply of Medical Waste incinerator | Phase 1 | 44166.1126 | 46403.5662 | Completed | PO + Contract issuance done | 2017-11-03 | Substantial completion / handover done |  |  | 2017-12-31 | Completed | Incinerator | 98720 | 31.1838 | 16.5843 | UK | 58
Works | West | Bani Walid | Education | Rehabilitation of School | Phase 1 | 22486.0766 | 100282.431 | Completed | PO + Contract issuance done | 2019-05-20 | Substantial completion / handover done |  |  | 2019-10-17 | Completed | School | 112158 | 31.3886 | 13.7567 | EU | 150
Works | West | Bani Walid | Education | Rehabilitation of School | Phase 1 | 24729.7433 | 0 | Completed | PO + Contract issuance done | 2019-05-20 | Substantial completion / handover done |  |  | 2019-10-17 | Completed | School | 112158 | 31.7519 | 14.0185 | EU | 150
Works | West | Bani Walid | Education | Rehabilitation of School | Phase 1 | 32171.5696 | 0 | Completed | PO + Contract issuance done | 2019-05-20 | Substantial completion / handover done |  |  | 2019-10-17 | Completed | School | 112158 | 31.7501 | 14.0152 | EU | 150
Works | West | Bani Walid | Education | Rehabilitation of School | Phase 1 | 33698.0155 | 30328.2139 | Completed | PO + Contract issuance done | 2019-05-04 | Substantial completion / handover done | 2019-07-21 |  | 2019-11-26 | Completed | School | 112158 | 31.7456 | 14.0097 | EU | 206
Works | West | Bani Walid | Education | Rehabilitation of School | Phase 1 | 26253.0344 | 23627.731 | Completed | PO + Contract issuance done | 2019-05-04 | Substantial completion / handover done | 2019-07-21 |  | 2019-11-26 | Completed | School | 112158 | 31.8306 | 14.0875 | EU | 206
Works | West | Bani Walid | Education | Rehabilitation of School | Phase 1 | 36574.4226 | 32916.9803 | Completed | PO + Contract issuance done | 2019-05-04 | Substantial completion / handover done | 2019-07-21 |  | 2019-11-26 | Completed | School | 112158 | 31.7327 | 14.4851 | EU | 206
Works | West | Bani Walid | Health | Rehabilitation of Clinic | Phase 1 | 54801.1425 | 54801.1425 | Completed | PO + Contract issuance done | 2018-10-12 | Substantial completion / handover done | 2018-10-16 | 2018-10-23 | 2019-01-02 | Completed | Other health building | 98720 | 31.7586 | 14.0285 | USA | 82
Works | West | Bani Walid | Education | Rehabilitation of School | Phase 1 | 46925.9017 | 46925.9017 | Completed | PO + Contract issuance done | 2018-11-16 | Substantial completion / handover done | 2018-12-05 | 2018-12-12 | 2019-02-05 | Completed | School | 112158 | 31.775 | 13.9959 | USA | 81
Goods | West | Bani Walid | Health | Supply of Ambulances | Phase 1 | 72330.5088 | 80254.1786 | Completed | PO + Contract issuance done | 2018-02-01 | Substantial completion / handover done |  |  | 2018-12-31 | Completed | Ambulance | 98720 | 31.7564 | 14.0268 | South Korea | 333
Goods | West | Bani Walid | Health | Supply of Generators | Phase 1 | 127786.2971 | 138652.4547 | Completed | PO + Contract issuance done | 2017-04-01 | Substantial completion / handover done |  |  | 2018-02-15 | Completed | Generator | 98720 | 31.757 | 14.0269 | Germany | 320
Goods | West | Bani Walid | Health | Supply of Generators | Phase 1 | 36197.9821 | 36197.9821 | Completed | PO + Contract issuance done | 2017-07-01 | Substantial completion / handover done |  |  | 2018-05-24 | Completed | Generator | 98720 | 31.7565 | 14.0277 | Germany | 327
Works | West | Bani Walid | Health | Rehabilitation of Hospital | Phase 1 | 372308.841 | 332563.0477 | Completed | PO + Contract issuance done | 2019-11-08 | Substantial completion / handover done | 2020-08-09 | 2020-08-19 | 2021-03-15 | Completed | Hospital | 112158 | 31.7568 | 14.0276 | Germany | 493
Goods | West | Bani Walid | Health | Supply of Ambulances | Phase 1 | 25069.3892 | 32222.6549 | Completed | PO + Contract issuance done | 2018-02-01 | Substantial completion / handover done |  |  | 2018-12-31 | Completed | Ambulance | 98720 | 31.7564 | 14.0268 | South Korea | 333
Goods | West | Bani Walid | Health | Supply of Generators | Phase 1 | 103892.803 | 52865.605 | Completed | PO + Contract issuance done | 2019-02-17 | Substantial completion / handover done |  |  | 2019-10-03 | Completed | Water Pump | 98720 | 31.7565 | 14.0277 | USA | 228
Goods | West | Bani Walid | Solid Waste Management | Supply of Garbage Trucks | Phase 1 | 163907.0147 | 209406.7385 | Completed | PO + Contract issuance done | 2017-04-01 | Substantial completion / handover done |  |  | 2018-02-08 | Completed | Garbage truck | 98720 | 31.7307 | 14.0492 | Germany | 313
Goods | West | Bani Walid | Public Infrastructure and Services | Supply of Generators | Phase 1 | 34328.485 | 34328.485 | Completed | PO + Contract issuance done | 2017-07-01 | Substantial completion / handover done |  |  | 2018-05-24 | Completed | Generator | 98720 | 31.7562 | 14.0222 | Germany | 327
Goods | West | Bani Walid | WASH | Supply of Pesticide Sprayer Trucks | Phase 1 | 40108.2276 | 36679.8518 | Completed | PO + Contract issuance done | 2018-03-28 | Substantial completion / handover done |  |  | 2018-12-31 | Completed | Pesticide Sprayer | 98720 | 31.7513 | 13.9893 | EU | 278
Goods | West | Bani Walid | WASH | Supply of Water Pumps | Phase 1 | 188132.6661 | 171833.696 | Completed | PO + Contract issuance done | 2018-06-24 | Substantial completion / handover done |  |  | 2019-04-01 | Completed | Water Pump | 98720 | 31.7522 | 14.02 | Italy | 281
Goods | West | Bani Walid | WASH | Supply of Water Pumps | Phase 1 | 4014.6021 | 3864.6102 | Completed | PO + Contract issuance done | 2018-06-24 | Substantial completion / handover done |  |  | 2019-05-12 | Completed | Water Pump | 98720 | 31.7522 | 14.02 | Italy | 322
Goods | West | Bani Walid | WASH | Supply of Generators | Phase 1 | 116435.076 | 0 | Completed | PO + Contract issuance done | 2018-10-01 | Substantial completion / handover done |  |  | 2019-06-27 | Completed | Generator |  | 31.7522 | 14.02 |  | 269
Goods | West | Bani Walid | WASH | Supply of Generators | Phase 1 | 20771.5693 | 20771.5693 | Completed | PO + Contract issuance done | 2018-06-24 | Substantial completion / handover done |  |  | 2019-02-10 | Completed | Generator | 98720 | 31.7522 | 14.02 | EU | 231
Goods | West | Bani Walid | WASH | Supply of Sewage Suction Trucks | Phase 1 | 128746.7868 | 118954.028 | Completed | PO + Contract issuance done | 2018-06-05 | Substantial completion / handover done |  |  | 2019-04-03 | Completed | Sewage suction truck | 98720 | 31.7522 | 14.02 | EU | 302
Goods | West | Bani Walid | Education | Provision of Educational Equipment | Phase 1 | 36395.8889 | 39490.7706 | Completed | PO + Contract issuance done | 2018-02-01 | Substantial completion / handover done |  |  | 2018-12-31 | Completed | Generator | 98720 | 31.7545 | 14.0255 | Germany | 333
Works | East | Benghazi | Health | Rehabilitation of Hospital | Phase 1 | 63702.1437 | 63702.1437 | Completed | PO + Contract issuance done | 2017-05-12 | Substantial completion / handover done | 2017-05-23 |  | 2017-09-27 | Completed | Hospital | 98720 | 32.203 | 20.1809 | EU | 138
Works | East | Benghazi | Health | Rehabilitation of Clinic | Phase 1 | 21610.9857 | 21610.9857 | Completed | PO + Contract issuance done | 2017-01-29 | Substantial completion / handover done | 2017-02-13 |  | 2017-06-20 | Completed | Clinic | 98720 | 32.0506 | 20.1103 | Italy | 142
Works | East | Benghazi | Health | Rehabilitation of Clinic | Phase 1 | 24889.0186 | 24889.0186 | Completed | PO + Contract issuance done | 2017-05-31 | Substantial completion / handover done |  |  | 2017-09-13 | Completed | Clinic | 98720 | 32.0291 | 20.0696 | France | 105
Works | East | Benghazi | Health | Rehabilitation of Clinic | Phase 1 | 64109.371 | 64109.371 | Completed | PO + Contract issuance done | 2016-11-22 | Substantial completion / handover done | 2016-12-01 |  | 2017-02-20 | Completed | Clinic | 98720 | 32.0535 | 20.1093 | Italy | 90
Works | East | Benghazi | Public Infrastructure and Services | Rehabilitation of Public Building | Phase 1 | 59611.6499 | 59346.8855 | Completed | PO + Contract issuance done | 2016-11-22 | Substantial completion / handover done | 2016-11-30 |  | 2017-02-26 | Completed | Public Infrastructure | 98720 | 32.098 | 20.1839 | Italy | 96
Works | East | Benghazi | Public Infrastructure and Services | Rehabilitation of Public Building | Phase 1 | 21498.213 | 21498.213 | Completed | PO + Contract issuance done | 2016-12-31 | Substantial completion / handover done | 2017-01-08 |  | 2017-05-01 | Completed | Public Infrastructure | 98720 | 32.114 | 20.0756 | Italy | 121
Works | East | Benghazi | Public Infrastructure and Services | Rehabilitation of Public Infrastructure | Phase 1 | 81854.0188 | 81854.0188 | Completed | PO + Contract issuance done | 2017-08-01 | Substantial completion / handover done |  |  | 2017-11-03 | Completed | Public Infrastructure | 98720 | 32.1065 | 20.0792 | Germany | 94
Works | East | Benghazi | Education | Rehabilitation of School | Phase 1 | 82857.1478 | 82857.1478 | Completed | PO + Contract issuance done | 2017-06-14 | Substantial completion / handover done |  |  | 2017-10-10 | Completed | School | 98720 | 32.0543 | 20.0367 | Norway | 118
Works | East | Benghazi | Energy | Rehabilitation of Substation | Phase 1 | 57047.1025 | 57047.1025 | Completed | PO + Contract issuance done | 2017-04-20 | Substantial completion / handover done |  |  | 2017-08-29 | Completed | Substation | 98720 | 32.099 | 20.1318 | EU | 131
Works | East | Benghazi | Energy | Rehabilitation of Substation | Phase 1 | 135536.4762 | 135536.4762 | Completed | PO + Contract issuance done | 2017-05-20 | Substantial completion / handover done |  |  | 2017-08-30 | Completed | Substation | 98720 | 32.1039 | 20.1548 | Japan | 102
Goods | East | Benghazi | Solid Waste Management | Supply of Garbage Trucks | Phase 1 | 412574.3701 | 426068.0739 | Completed | PO + Contract issuance done | 2016-02-01 | Substantial completion / handover done |  |  | 2016-12-10 | Completed | Garbage truck | 98720 |  |  | Germany | 313
Goods | East | Benghazi | Solid Waste Management | Supply of Garbage Bins | Phase 1 | 24457.4494 | 24457.4494 | Completed | PO + Contract issuance done | 2017-10-01 | Substantial completion / handover done |  |  | 2018-07-26 | Completed | Garbage Bin | 98720 |  |  | Germany | 298
Goods | East | Benghazi | Health | Supply of Ambulances | Phase 1 | 70167.3835 | 252871.5261 | Completed | PO + Contract issuance done | 2016-02-01 | Substantial completion / handover done |  |  | 2016-12-05 | Completed | Ambulance | 98720 | 32.0773 | 20.0979 | Germany | 308
Goods | East | Benghazi | Health | Supply of Ambulances | Phase 1 | 42893.4279 |  | Completed | PO + Contract issuance done | 2016-02-01 | Substantial completion / handover done |  |  | 2016-12-05 | Completed | Ambulance | 98720 | 32.051 | 20.1107 | Germany | 308
Goods | East | Benghazi | Health | Supply of Ambulances | Phase 1 | 67281.7589 |  | Completed | PO + Contract issuance done | 2016-02-01 | Substantial completion / handover done |  |  | 2016-12-05 | Completed | Ambulance | 98720 | 32.1101 | 20.0897 | Germany | 308
Goods | East | Benghazi | Health | Supply of Ambulances | Phase 1 | 81043.4658 |  | Completed | PO + Contract issuance done | 2016-02-01 | Substantial completion / handover done |  |  | 2016-12-05 | Completed | Ambulance | 98720 | 32.114 | 20.0755 | Germany | 308
Goods | East | Benghazi | Health | Supply of Ambulances | Phase 1 | 36325.8095 |  | Completed | PO + Contract issuance done | 2016-02-01 | Substantial completion / handover done |  |  | 2016-12-05 | Completed | Ambulance | 98720 | 32.0199 | 20.1239 | Germany | 308
Goods | East | Benghazi | Health | Supply of Generators | Phase 1 | 35565.9272 | 35565.9272 | Completed | PO + Contract issuance done | 2016-04-01 | Substantial completion / handover done |  |  | 2017-02-04 | Completed | Generator | 98720 | 32.2031 | 20.1806 | Germany | 309
Goods | East | Benghazi | Public Infrastructure and Services | Supply of Generators | Phase 1 | 31202.0612 | 31202.0612 | Completed | PO + Contract issuance done | 2016-04-01 | Substantial completion / handover done |  |  | 2017-02-01 | Completed | Generator | 98720 | 32.114 | 20.0756 | Germany | 306
Goods | East | Benghazi | Health | Suppy of Medical Equipment | Phase 1 | 137656.0454 | 153218.8406 | Completed | PO + Contract issuance done | 2017-06-30 | Substantial completion / handover done |  |  | 2018-12-31 | Completed | Medical Equipment | 98720 | 32.0535 | 20.1093 | Japan | 549
Goods | East | Benghazi | Health | Supply of Solar Panels | Phase 1 | 132320.1948 | 132320.1948 | Completed | PO + Contract issuance done | 2016-08-24 | Substantial completion / handover done |  |  | 2016-12-31 | Completed | Solar Panels | 98720 | 32.0773 | 20.0979 | Germany | 129
Goods | East | Benghazi | Health | Supply of Solar Panels | Phase 1 | 104547.6456 | 104547.6456 | Completed | PO + Contract issuance done | 2016-08-24 | Substantial completion / handover done |  |  | 2016-12-31 | Completed | Solar Panels | 98720 | 32.077 | 20.0927 | Germany | 129
Goods | East | Benghazi | Health | Supply of Solar Panels | Phase 1 | 103709.529 | 103709.529 | Completed | PO + Contract issuance done | 2016-08-24 | Substantial completion / handover done |  |  | 2016-12-31 | Completed | Solar Panels | 98720 | 32.1101 | 20.0897 | Germany | 129
Goods | East | Benghazi | Health | Supply of Solar Panels | Phase 1 | 101892.1184 | 101892.1184 | Completed | PO + Contract issuance done | 2016-08-24 | Substantial completion / handover done |  |  | 2016-12-31 | Completed | Solar Panels | 98720 | 32.2031 | 20.1806 | Germany | 129
Goods | East | Benghazi | Public Infrastructure and Services | Supply of Vehicles | Phase 1 | 72661.6633 | 72661.6633 | Completed | PO + Contract issuance done | 2017-06-06 | Substantial completion / handover done |  |  | 2017-12-31 | Completed | Vehicle | 98720 | 32.114 | 20.0755 | Japan | 208
Goods | East | Benghazi | Public Infrastructure and Services | Supply of Vehicles | Phase 1 | 27753.2166 | 27753.2166 | Completed | PO + Contract issuance done | 2017-09-08 | Substantial completion / handover done |  |  | 2017-12-31 | Completed | Boat | 98720 | 32.114 | 20.0755 | Germany | 114
Works | East | Benghazi | Energy | Supply and Installation of Solar Street Lights | Phase 1 | 644011.005 | 596021.0193 | Completed | PO + Contract issuance done | 2017-04-20 | Substantial completion / handover done |  |  | 2019-09-01 | Completed | Solar Street Light | 98720 | 32.0068 | 20.1297 | EU | 864
Goods | East | Benghazi | WASH | Supply of Sewage Pumps | Phase 1 | 209917.9152 | 206666.4776 | Completed | PO + Contract issuance done | 2017-08-10 | Substantial completion / handover done |  |  | 2018-12-31 | Completed | Sewage Pump | 98720 |  |  | USA | 508
Goods | East | Benghazi | WASH | Supply of Water Pumps | Phase 1 | 175389.6954 | 175389.6954 | Completed | PO + Contract issuance done | 2017-08-14 | Substantial completion / handover done |  |  | 2018-12-31 | Completed | Water Pump | 112158 | 32.0749 | 20.2307 | USA | 504
Goods | East | Benghazi | Health | Supply of Generators | Phase 1 | 46846.7377 | 46846.7377 | Completed | PO + Contract issuance done | 2016-04-01 | Substantial completion / handover done |  |  | 2017-02-01 | Completed | Generator | 98720 | 32.0502 | 20.1101 | Germany | 306
Goods | East | Benghazi | Health | Supply of Generators | Phase 1 | 38443.6482 | 38443.6482 | Completed | PO + Contract issuance done | 2016-04-01 | Substantial completion / handover done |  |  | 2017-02-01 | Completed | Generator | 98720 | 32.0199 | 20.1239 | Germany | 306
Goods | West | Kikla | Health | Supply of Ambulances | Phase 1 | 91831.4441 | 73772.8762 | Completed | PO + Contract issuance done | 2016-04-01 | Substantial completion / handover done |  |  | 2017-02-01 | Completed | Ambulance | 98720 | 32.0654 | 12.6953 | Germany | 306
Goods | West | Kikla | Health | Suppy of Medical Equipment | Phase 1 | 229796.3655 | 229137.3214 | Completed | PO + Contract issuance done | 2018-11-21 | Substantial completion / handover done |  |  | 2019-12-16 | Completed | Medical Equipment | 98720 | 32.0645 | 12.6905 | Norway | 390
Works | West | Kikla | Health | Rehabilitation of Hospital | Phase 1 | 242458.9372 | 242458.9372 | Completed | PO + Contract issuance done | 2017-07-03 | Substantial completion / handover done | 2017-06-14 | 2017-06-21 | 2018-02-17 | Completed | Hospital | 98720 | 32.0645 | 12.6905 | Germany | 229
Works | West | Kikla | Health | Rehabilitation of Hospital | Phase 1 | 11350.9158 | 11350.9158 | Completed | PO + Contract issuance done | 2018-03-07 | Substantial completion / handover done | 2018-03-30 | 2018-04-06 | 2018-05-08 | Completed | Other health building | 98720 | 32.0651 | 12.6908 | UK | 62
Works | West | Kikla | Health | Rehabilitation of Hospital | Phase 1 | 67748.8884 | 67748.8884 | Completed | PO + Contract issuance done | 2017-05-22 | Substantial completion / handover done | 2017-06-04 | 2017-06-11 | 2017-10-11 | Completed | Hospital | 98720 | 32.065 | 12.6897 | Japan | 142
Goods | West | Kikla | Public Infrastructure and Services | Supply of Fire Fighting Trucks | Phase 1 | 122240.9885 | 127201.3473 | Completed | PO + Contract issuance done | 2016-02-01 | Substantial completion / handover done |  |  | 2016-11-17 | Completed | Firetruck | 98720 | 32.0654 | 12.6953 | Germany | 290
Goods | West | Kikla | Public Infrastructure and Services | Supply of IT Equipment | Phase 1 | 10397.6038 | 10288.1553 | Completed | PO + Contract issuance done | 2017-02-03 | Substantial completion / handover done |  |  | 2017-02-23 | Completed | IT equipment | 98720 | 32.0654 | 12.6953 | Italy | 20
Goods | West | Kikla | Public Infrastructure and Services | Supply of Solar Power System | Phase 1 | 9555.4975 | 9555.4975 | Completed | PO + Contract issuance done | 2016-12-29 | Substantial completion / handover done |  |  | 2017-12-31 | Completed | Solar backup | 98720 | 32.0654 | 12.6953 | Italy | 367
Goods | West | Kikla | Public Infrastructure and Services | Supply of Sport Equipment | Phase 1 | 46842.0703 | 46842.0703 | Completed | PO + Contract issuance done | 2017-05-01 | Substantial completion / handover done |  |  | 2018-02-09 | Completed | Sports equipment | 98720 | 32.0654 | 12.6953 | Germany | 284
Works | West | Kikla | Public Infrastructure and Services | Rehabilitation of Public Building | Phase 1 | 44231.4687 | 44231.4687 | Completed | PO + Contract issuance done | 2017-03-02 | Substantial completion / handover done | 2017-03-13 | 2017-03-20 | 2017-05-14 | Completed | Public Infrastructure | 98720 | 32.0277 | 12.7078 | EU | 73
Goods | West | Kikla | Energy | Provision of Power Cables | Phase 1 | 56751.4917 | 56751.4917 | Completed | PO + Contract issuance done | 2016-05-01 | Substantial completion / handover done |  |  | 2017-02-01 | Completed | Generator | 98720 | 32.0654 | 12.6953 | Germany | 276
Goods | West | Kikla | Education | Provision of Educational Equipment | Phase 1 | 50964.9357 | 50964.9357 | Completed | PO + Contract issuance done | 2017-10-18 | Substantial completion / handover done |  |  | 2017-12-31 | Completed | Educational equipment | 98720 | 32.0654 | 12.6953 | Germany | 74
Goods | West | Kikla | Education | Provision of Educational Equipment | Phase 1 |  |  | Completed | PO + Contract issuance done | 2017-10-18 | Substantial completion / handover done |  |  | 2017-12-31 | Completed | Educational equipment | 98720 | 32.0654 | 12.6953 | Germany | 74
Goods | West | Kikla | Education | Provision of Educational Equipment | Phase 1 | 19649.2888 | 19649.2888 | Completed | PO + Contract issuance done | 2017-02-02 | Substantial completion / handover done |  |  | 2017-12-31 | Completed | Educational equipment | 98720 | 32.0654 | 12.6953 | Italy | 332
Goods | West | Kikla | Education | Provision of Educational Equipment | Phase 1 | 59775.6587 | 59775.6587 | Completed | PO + Contract issuance done | 2016-05-01 | Substantial completion / handover done |  |  | 2017-02-01 | Completed | Educational equipment | 98720 | 32.0654 | 12.6953 | Germany | 276
Goods | West | Kikla | Education | Provision of Educational Equipment | Phase 1 | 12380.9721 | 12380.9721 | Completed | PO + Contract issuance done | 2017-10-02 | Substantial completion / handover done |  |  | 2018-07-31 | Completed | Educational equipment | 98720 | 32.0654 | 12.6953 | EU | 302
Works | West | Kikla | Education | Rehabilitation of University | Phase 1 | 75085.0675 | 75085.0675 | Completed | PO + Contract issuance done | 2017-03-02 | Substantial completion / handover done | 2017-03-13 | 2017-03-20 | 2017-05-24 | Completed | University | 98720 | 32.058 | 12.6977 | EU | 83
Works | West | Kikla | Education | Rehabilitation of University | Phase 1 | 10835.798 | 10835.798 | Completed | PO + Contract issuance done | 2018-03-07 | Substantial completion / handover done | 2018-03-30 | 2018-04-06 | 2018-05-08 | Completed | Other Educational building | 98720 | 32.059 | 12.6961 | UK | 62
Goods | West | Kikla | Education | Provision of Educational Equipment | Phase 1 | 2571.5796 | 2571.5796 | Completed | PO + Contract issuance done | 2017-02-13 | Substantial completion / handover done |  |  | 2017-02-23 | Completed | Educational equipment | 98720 | 32.0654 | 12.6953 | Germany | 10
Works | South | Sebha | Education | Rehabilitation of University | Phase 1 | 77277.6724 | 77237.6271 | Completed | PO + Contract issuance done | 2017-11-30 | Substantial completion / handover done | 2017-12-15 | 2017-12-24 | 2018-10-02 | Completed | Other Educational building | 98720 | 27.0446 | 14.4386 | Denmark | 306
Works | South | Sebha | Education | Rehabilitation of University | Phase 1 | 43322.5222 | 47654.7744 | Completed | PO + Contract issuance done | 2017-07-11 | Substantial completion / handover done | 2017-07-22 | 2017-07-29 | 2018-07-01 | Completed | University | 98720 | 27.0395 | 14.4434 | Germany | 355
Goods | South | Sebha | WASH | Supply of Sewage Pumps | Phase 1 | 315980.9816 | 266328.2642 | Completed | PO + Contract issuance done | 2018-06-21 | Substantial completion / handover done |  |  | 2019-09-14 | Completed | Water Pump | 98720 | refer to list | refer to list | France | 450
Goods | South | Sebha | WASH | Supply of Generators | Phase 1 | 274942.4398 | 274942.4398 | Completed | PO + Contract issuance done | 2018-06-19 | Substantial completion / handover done |  |  | 2019-09-02 | Completed | Generator | 98720 | refer to list | refer to list | EU | 440
Works | South | Sebha | WASH | Supply of Generators | Phase 1 | 169184.8762 | 169184.9411 | Completed | PO + Contract issuance done | 2019-03-10 | Substantial completion / handover done | 2019-03-20 | 2019-03-30 | 2019-08-10 | Completed | Public Infrastructure | 112158 | refer to list | refer to list | EU | 153
Goods | South | Sebha | WASH | Supply of Sewage Pumps | Phase 1 | 109439.5069 | 109519.0356 | Completed | PO + Contract issuance done | 2018-05-23 | Substantial completion / handover done |  |  | 2019-08-27 | Completed | Sewage Pump | 98720 | 27.0404 | 14.4295 | EU | 461
Goods | South | Sebha | WASH | Supply of Sewage Pumps | Phase 1 | 151431.2888 | 129235.7304 | Completed | PO + Contract issuance done | 2018-09-24 | Substantial completion / handover done |  |  | 2019-08-28 | Completed | Sewage Pump | 98720 | 27.0423 | 14.4394 | USA | 338
Works | South | Sebha | Education | Rehabilitation of School | Phase 1 | 224243.4156 | 0 | Completed | Advertisement period ongoing | [5 empty] | With Procurement | School | 112158 | 27.0266333333333 27.0360833333333 27.0334138888889 27.0401583333333 27.0456 27.0222 | 14.4330194444444 14.411175 14.4601861111111 14.4233194444444 14.4361944444444 14.4569416666667 | Norway
Goods | South | Sebha | Health | Supply of Freezers | Phase 1 | 37105.7613 | 36847.3646 | Completed | PO + Contract issuance done | 2018-02-22 | Substantial completion / handover done |  |  | 2018-12-31 | Completed | Freezers | 98720 | 27.0262 | 14.4383 | EU | 312
Works | South | Sebha | Health | Rehabilitation of Clinic | Phase 1 | 23418.2493 | 23362.27 | Completed | PO + Contract issuance done | 2017-12-03 | Substantial completion / handover done | 2017-12-15 | 2017-12-23 | 2018-02-01 | Completed | Hospital | 98720 | 27.0249 | 14.4398 | Germany | 60
Works | South | Ubari | Education | Rehabilitation of School | Phase 1 | 383091.5783 | 382243.8043 | Completed | PO + Contract issuance done | 2017-04-20 | Substantial completion / handover done | 2017-05-03 | 2017-05-10 | 2017-11-07 | Completed | School | 98720 | 26.5947 | 12.78 | EU | 201
Works | South | Ubari | Education | Rehabilitation of School | Phase 1 | 305252.9461 | 304339.0522 | Completed | PO + Contract issuance done | 2017-04-21 | Substantial completion / handover done | 2017-07-16 | 2017-07-23 | 2017-12-31 | Completed | School | 98720 | 26.5939 | 12.7797 | Germany | 254
Works | South | Ubari | Education | Rehabilitation of School | Phase 1 | 111125.5113 | 111059.3598 | Completed | PO + Contract issuance done | 2017-03-13 | Substantial completion / handover done | 2017-05-02 | 2017-05-09 | 2017-09-06 | Completed | School | 98720 | 26.5896 | 12.7711 | Germany | 177
Works | South | Ubari | Education | Rehabilitation of School | Phase 1 | 311395.5068 | 311365.8885 | Completed | PO + Contract issuance done | 2017-07-07 | Substantial completion / handover done | 2017-07-27 | 2017-08-03 | 2017-12-01 | Completed | School | 98720 | 26.5897 | 12.7695 | Germany | 147
Works | South | Ubari | Health | Rehabilitation of Hospital | Phase 1 | 266921.715 | 266921.715 | Completed | PO + Contract issuance done | 2017-03-01 | Substantial completion / handover done | 2017-03-12 | 2017-03-19 | 2017-07-17 | Completed | Hospital | 98720 | 26.5928 | 12.7629 | Japan | 138
Goods | South | Ubari | Health | Suppy of Medical Equipment | Phase 1 | 55914.056 | 54898.3966 | Completed | PO + Contract issuance done | 2018-11-07 | Substantial completion / handover done |  |  | 2019-08-22 | Completed | Medical Equipment | 98720 | 26.5928 | 12.7629 | Japan | 288
Goods | South | Ubari | Health | Supply of Ambulances | Phase 1 | 62002.5741 | 69106.7357 | Completed | PO + Contract issuance done | 2016-02-01 | Substantial completion / handover done |  |  | 2017-12-31 | Completed | Ambulance | 98720 | 26.5928 | 12.7629 | South Korea | 699
Goods | South | Ubari | Health | Supply of Generators | Phase 1 | 78445.163 | 78644.6454 | Completed | PO + Contract issuance done | 2016-02-01 | Substantial completion / handover done |  |  | 2017-12-31 | Completed | Generator | 98720 | 26.5904472222222 26.5858 | 12.8199638888889 12.7998694444444 | Germany | 699
Goods | South | Ubari | Solid Waste Management | Supply of Garbage Trucks | Phase 1 | 89838.3883 | 89734.2066 | Completed | PO + Contract issuance done | 2017-05-01 | Substantial completion / handover done |  |  | 2019-02-28 | Completed | Garbage truck | 98720 | 26.5878 | 12.7739 | Germany | 668
Works | South | Ubari | Public Infrastructure and Services | Rehabilitation of Public Building | Phase 1 | 49698.3253 | 49698.3253 | Completed | PO + Contract issuance done | 2017-03-08 | Substantial completion / handover done | 2017-03-13 | 2017-03-20 | 2017-07-18 | Completed | Public Infrastructure | 98720 | 26.591 | 12.7665 | EU | 132
Goods | South | Ubari | Public Infrastructure and Services | Supply of IT Equipment | Phase 1 | 4604.3633 | 4604.3633 | Completed | PO + Contract issuance done | 2018-07-19 | Substantial completion / handover done |  |  | 2018-12-31 | Completed | IT equipment | 98720 | 26.591 | 12.7665 | Japan | 165
Goods | South | Ubari | Public Infrastructure and Services | Supply of Furniture | Phase 1 | 3547.5029 | 3547.5029 | Completed | PO + Contract issuance done | 2018-07-19 | Substantial completion / handover done |  |  | 2018-12-31 | Completed | Other public equipment | 98720 | 26.591 | 12.7665 | Japan | 165
Works | South | Ubari | Health | Rehabilitation of Hospital | Phase 1 | 12065.774 | 12060.9112 | Completed | PO + Contract issuance done | 2018-05-04 | Substantial completion / handover done |  |  | 2018-07-01 | Completed | Other health building | 98720 | 26.5904 | 12.82 | UK | 58
Works | South | Ubari | Health | Rehabilitation of Clinic | Phase 1 | 24459.7206 | 24354.6804 | Completed | PO + Contract issuance done | 2018-05-04 | Substantial completion / handover done |  |  | 2018-08-14 | Completed | Other health building | 98720 | 26.5858 | 12.7999 | USA | 102
Works | South | Ubari | Public Infrastructure and Services | Rehabilitation of Public Market | Phase 1 | 314647.9422 | 314647.9422 | Completed | PO + Contract issuance done | 2017-07-17 | Substantial completion / handover done | 2017-08-03 | 2017-08-10 | 2018-05-01 | Completed | Public Infrastructure | 98720 | 26.5881 | 12.7777 | Germany | 288
Goods | South | Ubari | WASH | Supply of Pesticide Sprayer Trucks | Phase 1 | 30860.8006 | 28668.1772 | Completed | PO + Contract issuance done | 2017-05-04 | Substantial completion / handover done |  |  | 2017-12-31 | Completed | Pesticide Sprayer | 98720 | 26.5878 | 12.7739 | EU | 241
Works | West | Tripoli | Health | Rehabilitation of Hospital | Phase 1 | 324059.8005 | 323832.4196 | Completed | PO + Contract issuance done | 2018-03-06 | Substantial completion / handover done | 2018-03-18 | 2019-07-01 | 2020-02-20 | Completed | Hospital | 98720 | 32.8804 | 13.1901 | UK | 716
Works | West | Tripoli | Health | Rehabilitation of Hospital | Phase 1 | 100109.5081 | 100109.4542 | Completed | PO + Contract issuance done | 2019-08-19 | Substantial completion / handover done | 2020-06-17 |  | 2021-01-27 | Completed | Hospital | 112158 | 32.5583 | 13.1782 | Germany | 527
Works | West | Tripoli | Health | Rehabilitation of Hospital | Phase 1 | 78479.379 | 78475.6207 | Completed | PO + Contract issuance done | 2019-06-18 | Substantial completion / handover done | 2019-07-24 |  | 2020-02-20 | Completed | Hospital | 112158 | 32.8843 | 13.1629 | EU | 247
Works | West | Tripoli | Health | Rehabilitation of Hospital | Phase 1 | 163688.9806 | 147226.7936 | Completed | PO + Contract issuance done | 2020-09-09 | Substantial completion / handover done | 2020-10-01 | 2020-10-29 | 2021-06-09 | Completed | Hospital | 112158 | 32.8771 | 13.3963 | Germany | 273
Works | West | Tripoli | Health | Rehabilitation of Hospital | Phase 1 | 65609.0305 | 65597.308 | Completed | PO + Contract issuance done | 2020-07-28 | Substantial completion / handover done | 2020-08-16 |  | 2021-09-16 | Completed | Hospital | 112158 | 32.8545 | 13.1748 | Libya | 415
Goods | West | Tripoli | WASH | Supply of Sewage Suction Trucks | Phase 1 | 828929.3374 | 784363.7313 | Completed | PO + Contract issuance done | 2018-10-14 | Substantial completion / handover done |  |  | 2019-07-12 | Completed | Sewage suction truck | 98720 |  |  | Japan | 271
Goods | West | Tripoli | Solid Waste Management | Supply of Garbage Trucks | Phase 1 | 65984.2119 | 66041.6859 | Completed | PO + Contract issuance done | 2018-12-29 | Substantial completion / handover done |  |  | 2019-09-25 | Completed | Garbage truck | 98720 |  |  | EU | 270
Works | West | Tripoli | Education | Rehabilitation of School | Phase 1 | 19194.8523 | 19194.8523 | Completed | PO + Contract issuance done | 2018-07-30 | Substantial completion / handover done | 2018-08-29 | 2018-09-05 | 2018-12-02 | Completed | School | 98720 | 32.8453 | 13.0377 | Norway | 125
Works | West | Tripoli | Education | Rehabilitation of School | Phase 1 | 18259.2486 | 18259.2486 | Completed | PO + Contract issuance done | 2018-07-30 | Substantial completion / handover done | 2018-08-29 | 2018-09-05 | 2018-12-02 | Completed | School | 98720 | 32.7748 | 13.0042 | Norway | 125
Works | West | Tripoli | Education | Rehabilitation of School | Phase 1 | 19605.3846 | 19605.3846 | Completed | PO + Contract issuance done | 2018-07-30 | Substantial completion / handover done | 2018-08-29 | 2018-09-05 | 2018-12-02 | Completed | School | 98720 | 32.8388 | 13.0627 | Norway | 125
Works | West | Tripoli | Education | Rehabilitation of School | Phase 1 | 19929.6341 | 19929.6184 | Completed | PO + Contract issuance done | 2018-05-10 | Substantial completion / handover done | 2018-05-25 | 2018-06-01 | 2018-10-25 | Completed | School | 98720 | 32.8264 | 13.0168 | Japan | 168
Works | West | Tripoli | Education | Rehabilitation of School | Phase 1 | 18698.7159 | 18698.7012 | Completed | PO + Contract issuance done | 2018-05-10 | Substantial completion / handover done | 2018-05-25 | 2018-06-01 | 2018-10-25 | Completed | School | 98720 | 32.7918 | 12.9982 | Japan | 168
Works | West | Tripoli | Education | Rehabilitation of School | Phase 1 | 20789.0693 | 20789.053 | Completed | PO + Contract issuance done | 2018-05-10 | Substantial completion / handover done | 2018-05-25 | 2018-06-01 | 2018-10-25 | Completed | School | 98720 | 32.8268 | 12.9846 | Japan | 168
Goods | West | Tripoli | Health | Suppy of Medical Equipment | Phase 1 | 17209.1561 | 14293.7335 | Completed | PO + Contract issuance done | 2019-01-29 | Substantial completion / handover done |  |  | 2020-11-05 | Completed | Medical Equipment | 98720 | 32.8107 | 13.0016 | Norway | 646
Goods | West | Tripoli | Health | Suppy of Medical Equipment | Phase 1 | 19313.3136 | 16041.4233 | Completed | PO + Contract issuance done | 2019-01-29 | Substantial completion / handover done |  |  | 2020-11-05 | Completed | Medical Equipment | 98720 |  |  | Norway | 646
Goods | West | Tripoli | Health | Suppy of Medical Equipment | Phase 1 | 16276.3482 | 13518.9536 | Completed | PO + Contract issuance done | 2019-01-29 | Substantial completion / handover done |  |  | 2020-11-05 | Completed | Medical Equipment | 98720 | 32.8424 | 13.0414 | Norway | 646
Goods | West | Tripoli | Health | Suppy of Medical Equipment | Phase 1 | 18454.5123 | 15328.1126 | Completed | PO + Contract issuance done | 2019-01-29 | Substantial completion / handover done |  |  | 2020-11-05 | Completed | Medical Equipment | 98720 | 32.8106 | 12.9632 | Norway | 646
Goods | West | Tripoli | Health | Suppy of Medical Equipment | Phase 1 | 15021.9161 | 12477.0363 | Completed | PO + Contract issuance done | 2019-01-29 | Substantial completion / handover done |  |  | 2020-11-05 | Completed | Medical Equipment | 98720 | 32.8335 | 13.0726 | Norway | 646
Works | West | Tripoli | Education | Rehabilitation of School | Phase 1 | 13321.5449 | 12029.2409 | Completed | PO + Contract issuance done | 2018-11-25 | Substantial completion / handover done | 2018-12-22 | 2018-12-29 | 2020-08-31 | Completed | School | 98720 | 32.8548 | 13.1603 | Norway | 645
Works | West | Tripoli | Education | Rehabilitation of School | Phase 1 | 21726.7418 | 21930.0907 | Completed | PO + Contract issuance done | 2018-11-25 | Substantial completion / handover done | 2018-12-22 | 2018-12-29 | 2020-08-31 | Completed | School | 98720 | 32.8466 | 13.1789 | Norway | 645
Works | West | Tripoli | Education | Rehabilitation of School | Phase 1 | 18120.514 | 19150.1694 | Completed | PO + Contract issuance done | 2018-11-25 | Substantial completion / handover done | 2018-12-22 | 2018-12-29 | 2020-08-31 | Completed | School | 98720 | 32.8512 | 13.1838 | Norway | 645
Works | West | Tripoli | Education | Rehabilitation of School | Phase 1 | 20556.3996 | 22281.3881 | Completed | PO + Contract issuance done | 2018-11-08 | Substantial completion / handover done | 2018-11-15 | 2018-11-22 | 2019-03-15 | Completed | School | 98720 | 32.7943 | 13.1642 | Japan | 127
Works | West | Tripoli | Education | Rehabilitation of School | Phase 1 | 12997.8016 | 10439.2711 | Completed | PO + Contract issuance done | 2018-11-08 | Substantial completion / handover done | 2018-11-15 | 2018-11-22 | 2019-03-15 | Completed | School | 98720 | 32.8537 | 13.178 | Japan | 127
Works | West | Tripoli | Education | Rehabilitation of School | Phase 1 | 12020.8707 | 13038.0973 | Completed | PO + Contract issuance done | 2018-11-08 | Substantial completion / handover done | 2018-11-15 | 2018-11-22 | 2019-03-15 | Completed | School | 98720 | 32.7937 | 13.1425 | Japan | 127
Goods | West | Tripoli | Health | Suppy of Medical Equipment | Phase 1 | 13913.8822 | 11556.7157 | Completed | PO + Contract issuance done | 2019-01-29 | Substantial completion / handover done |  |  | 2020-11-05 | Completed | Medical Equipment | 98720 |  |  | Norway | 646
Goods | West | Tripoli | Health | Suppy of Medical Equipment | Phase 1 | 17742.8509 | 14737.0145 | Completed | PO + Contract issuance done | 2019-01-29 | Substantial completion / handover done |  |  | 2020-11-05 | Completed | Medical Equipment | 98720 |  |  | Norway | 646
Goods | West | Tripoli | Health | Suppy of Medical Equipment | Phase 1 | 18438.4903 | 15314.8048 | Completed | PO + Contract issuance done | 2019-01-29 | Substantial completion / handover done |  |  | 2020-11-05 | Completed | Medical Equipment | 98720 |  |  | Norway | 646
Goods | West | Tripoli | Health | Suppy of Medical Equipment | Phase 1 | 15044.1656 | 12495.5165 | Completed | PO + Contract issuance done | 2019-01-29 | Substantial completion / handover done |  |  | 2020-11-05 | Completed | Medical Equipment | 98720 |  |  | Norway | 646
Goods | West | Tripoli | Health | Suppy of Medical Equipment | Phase 1 | 16385.5998 | 13609.6969 | Completed | PO + Contract issuance done | 2019-01-29 | Substantial completion / handover done |  |  | 2020-11-05 | Completed | Medical Equipment | 98720 |  |  | Norway | 646
Works | West | Tripoli | Education | Rehabilitation of School | Phase 1 | 10393.9362 | 9670.1245 | Completed | PO + Contract issuance done | 2018-11-13 | Substantial completion / handover done | 2018-12-08 | 2018-12-15 | 2019-06-19 | Completed | School | 98720 | 32.7063 | 12.9326 | Italy | 218
Works | West | Tripoli | Education | Rehabilitation of School | Phase 1 | 11390.6868 | 11382.3892 | Completed | PO + Contract issuance done | 2018-11-13 | Substantial completion / handover done | 2018-12-08 | 2018-12-15 | 2019-06-19 | Completed | School | 98720 | 32.7631 | 13.0927 | Italy | 218
Works | West | Tripoli | Education | Rehabilitation of School | Phase 1 | 22372.5643 | 22266.6352 | Completed | PO + Contract issuance done | 2018-11-13 | Substantial completion / handover done | 2018-12-08 | 2018-12-15 | 2019-06-19 | Completed | School | 98720 | 32.645 | 13.0211 | Italy | 218
Works | West | Tripoli | Education | Rehabilitation of School | Phase 1 | 23789.2299 | 23789.2299 | Completed | PO + Contract issuance done | 2018-10-26 | Substantial completion / handover done | 2018-11-25 | 2018-12-02 | 2019-05-21 | Completed | School | 98720 | 32.7132 | 13.0671 | Japan | 207
Works | West | Tripoli | Education | Rehabilitation of School | Phase 1 | 31429.847 | 31429.8683 | Completed | PO + Contract issuance done | 2018-10-26 | Substantial completion / handover done | 2018-11-25 | 2018-12-02 | 2019-05-21 | Completed | School | 98720 | 32.6883 | 13.0584 | Japan | 207
Works | West | Tripoli | Education | Rehabilitation of School | Phase 1 | 11533.9807 | 11533.9807 | Completed | PO + Contract issuance done | 2018-10-26 | Substantial completion / handover done | 2018-11-25 | 2018-12-02 | 2019-05-21 | Completed | School | 98720 | 32.6382 | 13.0653 | Japan | 207
Goods | West | Tripoli | Health | Suppy of Medical Equipment | Phase 1 | 16185.2753 | 13443.3095 | Completed | PO + Contract issuance done | 2019-01-29 | Substantial completion / handover done |  |  | 2020-11-05 | Completed | Medical Equipment | 98720 |  |  | Norway | 646
Goods | West | Tripoli | Health | Suppy of Medical Equipment | Phase 1 | 13781.797 | 11447.0072 | Completed | PO + Contract issuance done | 2019-01-29 | Substantial completion / handover done |  |  | 2020-11-05 | Completed | Medical Equipment | 98720 |  |  | Norway | 646
Goods | West | Tripoli | Health | Suppy of Medical Equipment | Phase 1 | 14030.0043 | 11653.1654 | Completed | PO + Contract issuance done | 2019-01-29 | Substantial completion / handover done |  |  | 2020-11-05 | Completed | Medical Equipment | 98720 |  |  | Norway | 646
Goods | West | Tripoli | Health | Suppy of Medical Equipment | Phase 1 | 17552.4881 | 14578.9013 | Completed | PO + Contract issuance done | 2019-01-29 | Substantial completion / handover done |  |  | 2020-11-05 | Completed | Medical Equipment | 98720 |  |  | Norway | 646
Goods | West | Tripoli | Health | Suppy of Medical Equipment | Phase 1 | 19267.1612 | 16003.0896 | Completed | PO + Contract issuance done | 2019-01-29 | Substantial completion / handover done |  |  | 2020-11-05 | Completed | Medical Equipment | 98720 |  |  | Norway | 646
Works | West | Tripoli | Education | Rehabilitation of School | Phase 1 | 19369.1527 | 17494.3623 | Completed | PO + Contract issuance done | 2018-11-10 | Substantial completion / handover done | 2018-12-10 | 2018-12-17 | 2019-09-04 | Completed | School | 98720 | 32.574 | 13.279 | Japan | 298
Works | West | Tripoli | Education | Rehabilitation of School | Phase 1 | 20778.1929 | 16418.0588 | Completed | PO + Contract issuance done | 2018-11-10 | Substantial completion / handover done | 2018-12-10 | 2018-12-17 | 2019-09-04 | Completed | School | 98720 | 32.607 | 13.241 | Japan | 298
Works | West | Tripoli | Education | Rehabilitation of School | Phase 1 | 21503.2046 | 26582.7247 | Completed | PO + Contract issuance done | 2018-11-10 | Substantial completion / handover done | 2018-12-10 | 2018-12-17 | 2019-09-04 | Completed | School | 98720 | 32.591 | 13.223 | Japan | 298
Works | West | Tripoli | Education | Rehabilitation of School | Phase 1 | 14244.1067 | 15463.5977 | Completed | PO + Contract issuance done | 2018-11-22 | Substantial completion / handover done | 2018-12-09 | 2018-12-16 | 2020-01-05 | Completed | School | 112158 | 32.666 | 13.292 | EU | 409
Works | West | Tripoli | Education | Rehabilitation of School | Phase 1 | 16630.0093 | 15419.6975 | Completed | PO + Contract issuance done | 2018-11-22 | Substantial completion / handover done | 2018-12-09 | 2018-12-16 | 2020-01-05 | Completed | School | 112158 | 32.616 | 13.277 | EU | 409
Works | West | Tripoli | Education | Rehabilitation of School | Phase 1 | 12006.3641 | 11824.8013 | Completed | PO + Contract issuance done | 2018-11-22 | Substantial completion / handover done | 2018-12-09 | 2018-12-16 | 2020-01-05 | Completed | School | 112158 | 32.529 | 13.257 | EU | 409
Goods | West | Tripoli | Health | Suppy of Medical Equipment | Phase 1 | 14985.9967 | 12447.2021 | Completed | PO + Contract issuance done | 2019-01-29 | Substantial completion / handover done |  |  | 2020-11-05 | Completed | Medical Equipment | 98720 |  |  | Norway | 646
Goods | West | Tripoli | Health | Suppy of Medical Equipment | Phase 1 | 13926.1055 | 11566.8682 | Completed | PO + Contract issuance done | 2019-01-29 | Substantial completion / handover done |  |  | 2020-11-05 | Completed | Medical Equipment | 98720 |  |  | Norway | 646
Goods | West | Tripoli | Health | Suppy of Medical Equipment | Phase 1 | 18086.0067 | 15022.0359 | Completed | PO + Contract issuance done | 2019-01-29 | Substantial completion / handover done |  |  | 2020-11-05 | Completed | Medical Equipment | 98720 |  |  | Norway | 646
Goods | West | Tripoli | Health | Suppy of Medical Equipment | Phase 1 | 17446.406 | 14490.7907 | Completed | PO + Contract issuance done | 2019-01-29 | Substantial completion / handover done |  |  | 2020-11-05 | Completed | Medical Equipment | 98720 |  |  | Norway | 646
Goods | West | Tripoli | Health | Suppy of Medical Equipment | Phase 1 | 16642.2566 | 13822.8731 | Completed | PO + Contract issuance done | 2019-01-29 | Substantial completion / handover done |  |  | 2020-11-05 | Completed | Medical Equipment | 98720 |  |  | Norway | 646
Works | West | Tripoli | Education | Rehabilitation of School | Phase 1 | 10951.4523 | 12378.8139 | Completed | PO + Contract issuance done | 2019-06-19 | Substantial completion / handover done | 2019-07-17 |  | 2019-11-19 | Completed | School | 112158 | 32.7426 | 13.7487 | EU | 153
Works | West | Tripoli | Education | Rehabilitation of School | Phase 1 | 27737.2207 | 26943.1223 | Completed | PO + Contract issuance done | 2019-06-19 | Substantial completion / handover done | 2019-07-17 |  | 2019-11-19 | Completed | School | 112158 | 32.3836 | 13.4458 | EU | 153
Works | West | Tripoli | Education | Rehabilitation of School | Phase 1 | 14832.2871 | 13882.0731 | Completed | PO + Contract issuance done | 2019-06-19 | Substantial completion / handover done | 2019-07-17 |  | 2019-11-19 | Completed | School | 112158 | 32.3928 | 13.3528 | EU | 153
Works | West | Tripoli | Education | Rehabilitation of School | Phase 1 | 27273.0948 | 81473.8084 | Completed | PO + Contract issuance done | 2019-06-19 | Substantial completion / handover done | 2019-07-17 | 2019-07-17 | 2019-11-16 | Completed | School | 112158 | 32.7335 | 13.7829 | EU | 150
Works | West | Tripoli | Education | Rehabilitation of School | Phase 1 | 23031.0173 | 0 | Completed | PO + Contract issuance done | 2019-06-19 | Substantial completion / handover done | 2019-07-17 | 2019-07-17 | 2019-11-16 | Completed | School | 112158 | 32.4454 | 13.3905 | EU | 150
Works | West | Tripoli | Education | Rehabilitation of School | Phase 1 | 21870.7068 | 0 | Completed | PO + Contract issuance done | 2019-06-19 | Substantial completion / handover done | 2019-07-17 | 2019-07-17 | 2020-07-27 | Completed | School | 112158 | 32.7117 | 13.6088 | EU | 404
Goods | West | Tripoli | Health | Suppy of Medical Equipment | Phase 1 | 14269.0552 | 11851.7185 | Completed | PO + Contract issuance done | 2019-01-29 | Substantial completion / handover done |  |  | 2020-11-05 | Completed | Medical Equipment | 98720 |  |  | Norway | 646
Goods | West | Tripoli | Health | Suppy of Medical Equipment | Phase 1 | 16858.5961 | 14002.5623 | Completed | PO + Contract issuance done | 2019-01-29 | Substantial completion / handover done |  |  | 2020-11-05 | Completed | Medical Equipment | 98720 |  |  | Norway | 646
Goods | West | Tripoli | Health | Suppy of Medical Equipment | Phase 1 | 17698.281 | 14699.9953 | Completed | PO + Contract issuance done | 2019-01-29 | Substantial completion / handover done |  |  | 2020-11-05 | Completed | Medical Equipment | 98720 |  |  | Norway | 646
Goods | West | Tripoli | Health | Suppy of Medical Equipment | Phase 1 | 13361.4867 | 11097.9022 | Completed | PO + Contract issuance done | 2019-01-29 | Substantial completion / handover done |  |  | 2020-11-05 | Completed | Medical Equipment | 98720 |  |  | Norway | 646
Goods | West | Tripoli | Health | Suppy of Medical Equipment | Phase 1 | 16635.4246 | 13817.1986 | Completed | PO + Contract issuance done | 2019-01-29 | Substantial completion / handover done |  |  | 2020-11-05 | Completed | Medical Equipment | 98720 |  |  | Norway | 646
Works | West | Tripoli | Education | Rehabilitation of School | Phase 1 | 31769.302 | 30368.4591 | Completed | PO + Contract issuance done | 2018-10-08 | Substantial completion / handover done | 2018-11-27 | 2018-12-04 | 2019-02-21 | Completed | School | 98720 | 32.8923 | 13.2012 | USA | 136
Works | West | Tripoli | Education | Rehabilitation of School | Phase 1 | 12824.7659 | 13003.9354 | Completed | PO + Contract issuance done | 2018-10-08 | Substantial completion / handover done | 2018-11-27 | 2018-12-04 | 2019-02-21 | Completed | School | 98720 | 32.8863 | 13.1956 | USA | 136
Works | West | Tripoli | Education | Rehabilitation of School | Phase 1 | 6853.6531 | 8088.2908 | Completed | PO + Contract issuance done | 2018-10-08 | Substantial completion / handover done | 2018-11-27 | 2018-12-04 | 2019-02-21 | Completed | School | 98720 | 32.8879 | 13.1959 | USA | 136
Works | West | Tripoli | Education | Rehabilitation of School | Phase 1 | 15428.8372 | 14839.6812 | Completed | PO + Contract issuance done | 2018-11-18 | Substantial completion / handover done | 2018-12-14 | 2018-12-21 | 2019-04-15 | Completed | School | 112158 | 32.8914 | 13.1755 | Germany | 148
Works | West | Tripoli | Education | Rehabilitation of School | Phase 1 | 19520.6115 | 19515.8539 | Completed | PO + Contract issuance done | 2018-11-18 | Substantial completion / handover done | 2018-12-14 | 2018-12-21 | 2019-04-15 | Completed | School | 98720 | 32.8791 | 13.1952 | Italy | 148
Works | West | Tripoli | Education | Rehabilitation of School | Phase 1 | 16909.3048 | 17226.5456 | Completed | PO + Contract issuance done | 2018-11-18 | Substantial completion / handover done | 2018-12-14 | 2018-12-21 | 2019-04-15 | Completed | School | 98720 | 32.8889 | 13.1859 | Italy | 148
Goods | West | Tripoli | Health | Suppy of Medical Equipment | Phase 1 | 13469.2018 | 11187.3691 | Completed | PO + Contract issuance done | 2019-01-29 | Substantial completion / handover done |  |  | 2020-11-05 | Completed | Medical Equipment | 98720 |  |  | Norway | 646
Goods | West | Tripoli | Health | Suppy of Medical Equipment | Phase 1 | 18436.1915 | 15312.8955 | Completed | PO + Contract issuance done | 2019-01-29 | Substantial completion / handover done |  |  | 2020-11-05 | Completed | Medical Equipment | 98720 |  |  | Norway | 646
Goods | West | Tripoli | Health | Suppy of Medical Equipment | Phase 1 | 17466.1045 | 14507.152 | Completed | PO + Contract issuance done | 2019-01-29 | Substantial completion / handover done |  |  | 2020-11-05 | Completed | Medical Equipment | 98720 |  |  | Norway | 646
Goods | West | Tripoli | Health | Suppy of Medical Equipment | Phase 1 | 18750.7196 | 15574.139 | Completed | PO + Contract issuance done | 2019-01-29 | Substantial completion / handover done |  |  | 2020-11-05 | Completed | Medical Equipment | 98720 |  |  | Norway | 646
Goods | West | Tripoli | Health | Suppy of Medical Equipment | Phase 1 | 13651.1856 | 11338.5229 | Completed | PO + Contract issuance done | 2019-01-29 | Substantial completion / handover done |  |  | 2020-11-05 | Completed | Medical Equipment | 98720 |  |  | Norway | 646
Works | West | Tripoli | Education | Rehabilitation of School | Phase 1 | 75494.0486 | 75303.8163 | Completed | PO + Contract issuance done | 2019-10-17 | Substantial completion / handover done | 2020-06-17 |  | 2020-10-26 | Completed | School | 112158 | 32.5708 | 13.1691 | EU | 375
Works | West | Tripoli | Education | Rehabilitation of School | Phase 1 | 0 | 0 | Completed | PO + Contract issuance done | 2019-10-17 | Substantial completion / handover done | 2020-06-17 |  | 2020-10-26 | Completed | School | 112158 | 32.3389 | 13.1603 | EU | 375
Works | West | Tripoli | Education | Rehabilitation of School | Phase 1 | 0 | 0 | Completed | PO + Contract issuance done | 2019-10-17 | Substantial completion / handover done | 2020-06-17 |  | 2020-10-26 | Completed | School | 112158 | 32.5368 | 13.1734 | EU | 375
Works | West | Tripoli | Education | Rehabilitation of School | Phase 1 | 61943.3145 | 61893.8213 | Completed | PO + Contract issuance done | 2019-11-03 | Substantial completion / handover done | 2020-06-17 |  | 2020-10-26 | Completed | School | 112158 | 32.3417 | 13.0838 | EU | 358
Works | West | Tripoli | Education | Rehabilitation of School | Phase 1 | 0 | 0 | Completed | PO + Contract issuance done | 2019-11-03 | Substantial completion / handover done | 2020-06-17 |  | 2020-10-26 | Completed | School | 112158 | 32.452 | 13.1584 | EU | 358
Works | West | Tripoli | Education | Rehabilitation of School | Phase 1 | 0 | 0 | Completed | PO + Contract issuance done | 2019-11-03 | Substantial completion / handover done | 2020-06-17 |  | 2020-10-26 | Completed | School | 112158 | 32.317 | 13.106 | EU | 358
Goods | West | Tripoli | Health | Suppy of Medical Equipment | Phase 1 | 14917.7555 | 12390.5217 | Completed | PO + Contract issuance done | 2019-01-29 | Substantial completion / handover done |  |  | 2020-11-05 | Completed | Medical Equipment | 98720 |  |  | Norway | 646
Goods | West | Tripoli | Health | Suppy of Medical Equipment | Phase 1 | 16156.6243 | 13419.5124 | Completed | PO + Contract issuance done | 2019-01-29 | Substantial completion / handover done |  |  | 2020-11-05 | Completed | Medical Equipment | 98720 |  |  | Norway | 646
Goods | West | Tripoli | Health | Suppy of Medical Equipment | Phase 1 | 17925.2096 | 14888.4796 | Completed | PO + Contract issuance done | 2019-01-29 | Substantial completion / handover done |  |  | 2020-11-05 | Completed | Medical Equipment | 98720 |  |  | Norway | 646
Goods | West | Tripoli | Health | Suppy of Medical Equipment | Phase 1 | 17686.9993 | 14690.6248 | Completed | PO + Contract issuance done | 2019-01-29 | Substantial completion / handover done |  |  | 2020-11-05 | Completed | Medical Equipment | 98720 |  |  | Norway | 646
Goods | West | Tripoli | Health | Suppy of Medical Equipment | Phase 1 | 19300.7007 | 16030.9472 | Completed | PO + Contract issuance done | 2019-01-29 | Substantial completion / handover done |  |  | 2020-11-05 | Completed | Medical Equipment | 98720 |  |  | Norway | 646
Works | West | Tripoli | Education | Rehabilitation of School | Phase 1 | 13178.9726 | 13176.5504 | Completed | PO + Contract issuance done | 2018-11-07 | Substantial completion / handover done | 2018-12-07 | 2018-12-14 | 2019-03-18 | Completed | School | 98720 | 32.8413 | 13.2152 | Japan | 131
Works | West | Tripoli | Education | Rehabilitation of School | Phase 1 | 14803.9867 | 14795.8888 | Completed | PO + Contract issuance done | 2018-11-07 | Substantial completion / handover done | 2018-12-07 | 2018-12-14 | 2019-03-18 | Completed | School | 98720 | 32.8496 | 13.2057 | Japan | 131
Works | West | Tripoli | Education | Rehabilitation of School | Phase 1 | 28254.2658 | 22679.7541 | Completed | PO + Contract issuance done | 2018-11-07 | Substantial completion / handover done | 2018-12-07 | 2018-12-14 | 2019-03-18 | Completed | School | 98720 | 32.8321 | 13.2366 | Japan | 131
Works | West | Tripoli | Education | Rehabilitation of School | Phase 1 | 15508.6319 | 15435.5452 | Completed | PO + Contract issuance done | 2018-11-20 | Substantial completion / handover done | 2018-11-27 | 2018-12-04 | 2019-03-18 | Completed | School | 112158 | 32.8019 | 13.2824 | EU | 118
Works | West | Tripoli | Education | Rehabilitation of School | Phase 1 | 25666.4618 | 25526.6334 | Completed | PO + Contract issuance done | 2018-11-20 | Substantial completion / handover done | 2018-11-27 | 2018-12-04 | 2019-03-18 | Completed | School | 112158 | 32.8591 | 13.207 | EU | 118
Works | West | Tripoli | Education | Rehabilitation of School | Phase 1 | 17989.1687 | 17874.8339 | Completed | PO + Contract issuance done | 2018-11-20 | Substantial completion / handover done | 2018-11-27 | 2018-12-04 | 2019-03-18 | Completed | School | 112158 | 32.8185 | 13.2342 | EU | 118
Goods | West | Tripoli | Health | Suppy of Medical Equipment | Phase 1 | 17656.1978 | 14665.0414 | Completed | PO + Contract issuance done | 2019-01-29 | Substantial completion / handover done |  |  | 2020-11-05 | Completed | Medical Equipment | 98720 |  |  | Norway | 646
Goods | West | Tripoli | Health | Suppy of Medical Equipment | Phase 1 | 16458.697 | 13670.4106 | Completed | PO + Contract issuance done | 2019-01-29 | Substantial completion / handover done |  |  | 2020-11-05 | Completed | Medical Equipment | 98720 |  |  | Norway | 646
Goods | West | Tripoli | Health | Suppy of Medical Equipment | Phase 1 | 14409.3876 | 11968.277 | Completed | PO + Contract issuance done | 2019-01-29 | Substantial completion / handover done |  |  | 2020-11-05 | Completed | Medical Equipment | 98720 |  |  | Norway | 646
Goods | West | Tripoli | Health | Suppy of Medical Equipment | Phase 1 | 15626.2975 | 12979.0288 | Completed | PO + Contract issuance done | 2019-01-29 | Substantial completion / handover done |  |  | 2020-11-05 | Completed | Medical Equipment | 98720 |  |  | Norway | 646
Goods | West | Tripoli | Health | Suppy of Medical Equipment | Phase 1 | 14730.4721 | 12234.9662 | Completed | PO + Contract issuance done | 2019-01-29 | Substantial completion / handover done |  |  | 2020-11-05 | Completed | Medical Equipment | 98720 |  |  | Norway | 646
Works | West | Tripoli | Education | Rehabilitation of School | Phase 1 | 16510.1221 | 16028.7177 | Completed | PO + Contract issuance done | 2018-10-23 | Substantial completion / handover done | 2018-11-22 | 2018-11-29 | 2019-03-20 | Completed | School | 112158 | 32.8559 | 13.0955 | Germany | 148
Works | West | Tripoli | Education | Rehabilitation of School | Phase 1 | 20019.7251 | 19752.8116 | Completed | PO + Contract issuance done | 2018-10-23 | Substantial completion / handover done | 2018-11-22 | 2018-11-29 | 2019-03-12 | Completed | School | 112158 | 32.8652 | 13.1258 | Germany | 140
Works | West | Tripoli | Education | Rehabilitation of School | Phase 1 | 11625.4187 | 11131.5974 | Completed | PO + Contract issuance done | 2018-10-23 | Substantial completion / handover done | 2018-11-22 | 2018-11-29 | 2019-03-11 | Completed | School | 112158 | 32.8466 | 13.1321 | Germany | 139
Works | West | Tripoli | Education | Rehabilitation of School | Phase 1 | 14154.495 | 13722.3623 | Completed | PO + Contract issuance done | 2018-10-19 | Substantial completion / handover done | 2018-11-17 | 2018-11-24 | 2019-03-01 | Completed | School | 98720 | 32.8433 | 13.1171 | Japan | 133
Works | West | Tripoli | Education | Rehabilitation of School | Phase 1 | 14166.367 | 14398.5314 | Completed | PO + Contract issuance done | 2018-10-19 | Substantial completion / handover done | 2018-11-17 | 2018-11-24 | 2019-03-01 | Completed | School | 98720 | 32.7907 | 13.0874 | Japan | 133
Works | West | Tripoli | Education | Rehabilitation of School | Phase 1 | 24212.3092 | 24466.2761 | Completed | PO + Contract issuance done | 2018-10-19 | Substantial completion / handover done | 2018-11-17 | 2018-11-24 | 2019-03-01 | Completed | School | 98720 | 32.8504 | 13.116 | Japan | 133
Goods | West | Tripoli | Health | Suppy of Medical Equipment | Phase 1 | 14736.7288 | 12240.163 | Completed | PO + Contract issuance done | 2019-01-29 | Substantial completion / handover done |  |  | 2020-11-05 | Completed | Medical Equipment | 98720 |  |  | Norway | 646
Goods | West | Tripoli | Health | Suppy of Medical Equipment | Phase 1 | 18396.284 | 15279.7488 | Completed | PO + Contract issuance done | 2019-01-29 | Substantial completion / handover done |  |  | 2020-11-05 | Completed | Medical Equipment | 98720 |  |  | Norway | 646
Goods | West | Tripoli | Health | Suppy of Medical Equipment | Phase 1 | 18290.5866 | 15191.9577 | Completed | PO + Contract issuance done | 2019-01-29 | Substantial completion / handover done |  |  | 2020-11-05 | Completed | Medical Equipment | 98720 |  |  | Norway | 646
Goods | West | Tripoli | Health | Suppy of Medical Equipment | Phase 1 | 15015.8308 | 12471.982 | Completed | PO + Contract issuance done | 2019-01-29 | Substantial completion / handover done |  |  | 2020-11-05 | Completed | Medical Equipment | 98720 |  |  | Norway | 646
Goods | West | Tripoli | Health | Suppy of Medical Equipment | Phase 1 | 15289.7019 | 12699.4563 | Completed | PO + Contract issuance done | 2019-01-29 | Substantial completion / handover done |  |  | 2020-11-05 | Completed | Medical Equipment | 98720 |  |  | Norway | 646
Works | West | Tripoli | Education | Rehabilitation of School | Phase 1 | 59538.941 | 59510.5617 | Completed | PO + Contract issuance done | 2019-08-25 | Substantial completion / handover done | 2020-06-17 |  | 2021-01-03 | Completed | School | 112158 | 32.6823 | 13.1248 | South Korea | 497
Works | West | Tripoli | Education | Rehabilitation of School | Phase 1 | 0 | 0 | Completed | PO + Contract issuance done | 2019-08-25 | Substantial completion / handover done | 2020-06-17 |  | 2021-01-03 | Completed | School | 112158 | 32.691 | 13.1505 | South Korea | 497
Works | West | Tripoli | Education | Rehabilitation of School | Phase 1 | 0 | 0 | Completed | PO + Contract issuance done | 2019-08-25 | Substantial completion / handover done | 2020-06-17 |  | 2021-01-03 | Completed | School | 112158 | 32.5998 | 13.2125 | South Korea | 497
Works | West | Tripoli | Education | Rehabilitation of School | Phase 1 | 18724.2139 | 28189.6352 | Completed | PO + Contract issuance done | 2018-11-26 | Substantial completion / handover done | 2018-12-16 | 2018-12-23 | 2020-04-19 | Completed | School | 112158 | 32.6823 | 13.1248 | EU | 510
Works | West | Tripoli | Education | Rehabilitation of School | Phase 1 | 14801.9705 | 0 | Completed | PO + Contract issuance done | 2018-11-26 | Substantial completion / handover done | 2018-12-16 | 2018-12-23 | 2020-04-19 | Completed | School | 112158 | 32.6912 | 13.1506 | EU | 510
Works | West | Tripoli | Education | Rehabilitation of School | Phase 1 | 24460.4964 | 29809.0586 | Completed | PO + Contract issuance done | 2018-11-26 | Substantial completion / handover done | 2018-12-16 | 2018-12-23 | 2020-04-19 | Completed | School | 112158 |  |  | EU | 510
Goods | West | Tripoli | Health | Suppy of Medical Equipment | Phase 1 | 18868.7622 | 15672.1839 | Completed | PO + Contract issuance done | 2019-01-29 | Substantial completion / handover done |  |  | 2020-11-05 | Completed | Medical Equipment | 98720 |  |  | Norway | 646
Goods | West | Tripoli | Health | Suppy of Medical Equipment | Phase 1 | 14734.5187 | 12238.3272 | Completed | PO + Contract issuance done | 2019-01-29 | Substantial completion / handover done |  |  | 2020-11-05 | Completed | Medical Equipment | 98720 | 32.6183 | 13.2229 | Norway | 646
Goods | West | Tripoli | Health | Suppy of Medical Equipment | Phase 1 | 17829.57 | 14809.0424 | Completed | PO + Contract issuance done | 2019-01-29 | Substantial completion / handover done |  |  | 2020-11-05 | Completed | Medical Equipment | 98720 |  |  | Norway | 646
Goods | West | Tripoli | Health | Suppy of Medical Equipment | Phase 1 | 15595.4381 | 12953.3973 | Completed | PO + Contract issuance done | 2019-01-29 | Substantial completion / handover done |  |  | 2020-11-05 | Completed | Medical Equipment | 98720 |  |  | Norway | 646
Goods | West | Tripoli | Health | Suppy of Medical Equipment | Phase 1 | 16627.589 | 13810.6904 | Completed | PO + Contract issuance done | 2019-01-29 | Substantial completion / handover done |  |  | 2020-11-05 | Completed | Medical Equipment | 98720 |  |  | Norway | 646
Works | West | Tripoli | Education | Rehabilitation of School | Phase 1 | 15275.6486 | 11745.3079 | Completed | PO + Contract issuance done | 2018-11-27 | Substantial completion / handover done | 2018-12-12 | 2018-12-19 | 2019-03-26 | Completed | School | 112158 | 32.302 | 13.268 | USA | 119
Works | West | Tripoli | Education | Rehabilitation of School | Phase 1 | 19723.1583 | 16133.1428 | Completed | PO + Contract issuance done | 2018-11-27 | Substantial completion / handover done | 2018-12-12 | 2018-12-19 | 2019-03-26 | Completed | School | 112158 | 32.381 | 13.229 | USA | 119
Works | West | Tripoli | Education | Rehabilitation of School | Phase 1 | 16927.7367 | 22991.798 | Completed | PO + Contract issuance done | 2018-11-27 | Substantial completion / handover done | 2018-12-12 | 2018-12-19 | 2019-03-26 | Completed | School | 112158 | 32.467 | 13.256 | USA | 119
Works | West | Tripoli | Education | Rehabilitation of School | Phase 1 | 12426.7494 | 11798.1004 | Completed | PO + Contract issuance done | 2018-11-19 | Substantial completion / handover done | 2018-12-19 | 2018-12-26 | 2019-11-07 | Completed | School | 112158 | 32.408 | 13.228 | USA | 353
Works | West | Tripoli | Education | Rehabilitation of School | Phase 1 | 28157.5774 | 31251.58 | Completed | PO + Contract issuance done | 2018-11-19 | Substantial completion / handover done | 2018-12-19 | 2018-12-26 | 2019-11-07 | Completed | School | 112158 | 32.299 | 13.269 | USA | 353
Works | West | Tripoli | Education | Rehabilitation of School | Phase 1 | 17114.5776 | 14562.596 | Completed | PO + Contract issuance done | 2018-11-19 | Substantial completion / handover done | 2018-12-19 | 2018-12-26 | 2019-11-07 | Completed | School | 112158 | 32.444 | 13.283 | USA | 353
Goods | West | Tripoli | Health | Suppy of Medical Equipment | Phase 1 | 14514.8175 | 12055.8459 | Completed | PO + Contract issuance done | 2019-01-29 | Substantial completion / handover done |  |  | 2020-11-05 | Completed | Medical Equipment | 98720 |  |  | Norway | 646
Goods | West | Tripoli | Health | Suppy of Medical Equipment | Phase 1 | 18055.8305 | 14996.9718 | Completed | PO + Contract issuance done | 2019-01-29 | Substantial completion / handover done |  |  | 2020-11-05 | Completed | Medical Equipment | 98720 |  |  | Norway | 646
Goods | West | Tripoli | Health | Suppy of Medical Equipment | Phase 1 | 18967.5173 | 15754.2088 | Completed | PO + Contract issuance done | 2019-01-29 | Substantial completion / handover done |  |  | 2020-11-05 | Completed | Medical Equipment | 98720 |  |  | Norway | 646
Goods | West | Tripoli | Health | Suppy of Medical Equipment | Phase 1 | 18257.7441 | 15164.6791 | Completed | PO + Contract issuance done | 2019-01-29 | Substantial completion / handover done |  |  | 2020-11-05 | Completed | Medical Equipment | 98720 |  |  | Norway | 646
Goods | West | Tripoli | Health | Suppy of Medical Equipment | Phase 1 | 15854.6724 | 13168.7144 | Completed | PO + Contract issuance done | 2019-01-29 | Substantial completion / handover done |  |  | 2020-11-05 | Completed | Medical Equipment | 98720 |  |  | Norway | 646
Works | West | Tripoli | Education | Rehabilitation of School | Phase 1 | 26281.3261 | 26281.3261 | Completed | PO + Contract issuance done | 2018-11-08 | Substantial completion / handover done | 2018-11-15 | 2018-11-22 | 2019-04-25 | Completed | School | 98720 | 32.9051 | 13.2551 | South Korea | 168
Works | West | Tripoli | Education | Rehabilitation of School | Phase 1 | 20010.9067 | 20010.9067 | Completed | PO + Contract issuance done | 2018-11-08 | Substantial completion / handover done | 2018-11-15 | 2018-11-22 | 2019-04-25 | Completed | School | 98720 | 32.887 | 13.2304 | South Korea | 168
Works | West | Tripoli | Education | Rehabilitation of School | Phase 1 | 23505.1749 | 23428.9771 | Completed | PO + Contract issuance done | 2018-11-08 | Substantial completion / handover done | 2018-11-15 | 2018-11-22 | 2019-04-25 | Completed | School | 98720 | 32.8935 | 13.2385 | South Korea | 168
Works | West | Tripoli | Education | Rehabilitation of School | Phase 1 | 24237.4217 | 21192.9305 | Completed | PO + Contract issuance done | 2018-10-26 | Substantial completion / handover done | 2018-11-02 | 2018-11-09 | 2019-03-06 | Completed | School | 98720 | 32.9033 | 13.2385 | Japan | 131
Works | West | Tripoli | Education | Rehabilitation of School | Phase 1 | 9422.2217 | 12381.0544 | Completed | PO + Contract issuance done | 2018-10-26 | Substantial completion / handover done | 2018-11-02 | 2018-11-09 | 2019-03-06 | Completed | School | 98720 | 32.8893 | 13.2371 | Japan | 131
Works | West | Tripoli | Education | Rehabilitation of School | Phase 1 | 9558.5693 | 9899.476 | Completed | PO + Contract issuance done | 2018-10-26 | Substantial completion / handover done | 2018-11-02 | 2018-11-09 | 2019-03-06 | Completed | School | 98720 | 32.8905 | 13.2442 | Japan | 131
Goods | West | Tripoli | Health | Suppy of Medical Equipment | Phase 1 | 18397.3976 | 15280.6737 | Completed | PO + Contract issuance done | 2019-01-29 | Substantial completion / handover done |  |  | 2020-11-05 | Completed | Medical Equipment | 98720 |  |  | Norway | 646
Goods | West | Tripoli | Health | Suppy of Medical Equipment | Phase 1 | 15182.2779 | 12610.2311 | Completed | PO + Contract issuance done | 2019-01-29 | Substantial completion / handover done |  |  | 2020-11-05 | Completed | Medical Equipment | 98720 |  |  | Norway | 646
Goods | West | Tripoli | Health | Suppy of Medical Equipment | Phase 1 | 16349.0705 | 13579.356 | Completed | PO + Contract issuance done | 2019-01-29 | Substantial completion / handover done |  |  | 2020-11-05 | Completed | Medical Equipment | 98720 |  |  | Norway | 646
Goods | West | Tripoli | Health | Suppy of Medical Equipment | Phase 1 | 18021.1994 | 14968.2077 | Completed | PO + Contract issuance done | 2019-01-29 | Substantial completion / handover done |  |  | 2020-11-05 | Completed | Medical Equipment | 98720 |  |  | Norway | 646
Goods | West | Tripoli | Health | Suppy of Medical Equipment | Phase 1 | 16967.759 | 14093.2318 | Completed | PO + Contract issuance done | 2019-01-29 | Substantial completion / handover done |  |  | 2020-11-05 | Completed | Medical Equipment | 98720 |  |  | Norway | 646
Goods | West | Tripoli | Health | Supply of Generators | Phase 1 | 29789.1274 | 32398.6414 | Completed | PO + Contract issuance done | 2018-10-03 | Substantial completion / handover done |  |  | 2019-06-30 | Completed | Generator | 98720 |  |  | Germany | 270
Works | West | Tripoli | Education | Rehabilitation of School | Phase 1 | 16541.2735 | 50421.2077 | Completed | PO + Contract issuance done | 2018-07-19 | Substantial completion / handover done | 2018-08-18 | 2018-08-25 | 2018-12-05 | Completed | School | 98720 | 32.7706 | 13.4718 | South Korea | 139
Works | West | Tripoli | Education | Rehabilitation of School | Phase 1 | 15342.0877 | 0 | Completed | PO + Contract issuance done | 2018-07-19 | Substantial completion / handover done | 2018-08-18 | 2018-08-25 | 2018-12-05 | Completed | School | 98720 | 32.7574 | 13.3102 | South Korea | 139
Works | West | Tripoli | Education | Rehabilitation of School | Phase 1 | 18574.321 | 0 | Completed | PO + Contract issuance done | 2018-07-19 | Substantial completion / handover done | 2018-08-18 | 2018-08-25 | 2018-12-05 | Completed | School | 98720 | 32.8803 | 13.3077 | South Korea | 139
Works | West | Tripoli | Education | Rehabilitation of School | Phase 1 | 15692.3531 | 61533.4183 | Completed | PO + Contract issuance done | 2018-07-19 | Substantial completion / handover done | 2018-08-18 | 2018-08-25 | 2018-12-05 | Completed | School | 98720 | 32.8685 | 13.3605 | South Korea | 139
Works | West | Tripoli | Education | Rehabilitation of School | Phase 1 | 22142.3559 | 0 | Completed | PO + Contract issuance done | 2018-07-19 | Substantial completion / handover done | 2018-08-18 | 2018-08-25 | 2018-12-05 | Completed | School | 98720 | 32.8906 | 13.3343 | South Korea | 139
Works | West | Tripoli | Education | Rehabilitation of School | Phase 1 | 19728.0663 | 0 | Completed | PO + Contract issuance done | 2018-07-19 | Substantial completion / handover done | 2018-08-18 | 2018-08-25 | 2018-12-05 | Completed | School | 98720 | 32.7937 | 13.4407 | South Korea | 139
Goods | West | Tripoli | Health | Suppy of Medical Equipment | Phase 1 | 17457.6614 | 14500.1393 | Completed | PO + Contract issuance done | 2019-01-29 | Substantial completion / handover done |  |  | 2020-11-05 | Completed | Medical Equipment | 98720 |  |  | Norway | 646
Goods | West | Tripoli | Health | Suppy of Medical Equipment | Phase 1 | 15787.8673 | 13113.2268 | Completed | PO + Contract issuance done | 2019-01-29 | Substantial completion / handover done |  |  | 2020-11-05 | Completed | Medical Equipment | 98720 |  |  | Norway | 646
Goods | West | Tripoli | Health | Suppy of Medical Equipment | Phase 1 | 18753.1627 | 15576.1682 | Completed | PO + Contract issuance done | 2019-01-29 | Substantial completion / handover done |  |  | 2020-11-05 | Completed | Medical Equipment | 98720 |  |  | Norway | 646
Goods | West | Tripoli | Health | Suppy of Medical Equipment | Phase 1 | 15739.4144 | 13072.9825 | Completed | PO + Contract issuance done | 2019-01-29 | Substantial completion / handover done |  |  | 2020-11-05 | Completed | Medical Equipment | 98720 |  |  | Norway | 646
Goods | West | Tripoli | Health | Suppy of Medical Equipment | Phase 1 | 13084.8945 | 10868.1677 | Completed | PO + Contract issuance done | 2019-01-29 | Substantial completion / handover done |  |  | 2020-11-05 | Completed | Medical Equipment | 98720 |  |  | Norway | 646
Goods | East | Ajdabiya | Public Infrastructure and Services | Supply of Fire Fighting Trucks | Broadening | 317229.6216 | 254588.6258 | Completed | PO + Contract issuance done | 2020-06-25 | Substantial completion / handover done |  |  | 2021-05-07 | Completed | Firetruck | 112158 |  |  | Germany | 316
Goods | East | Ajdabiya | Solid Waste Management | Supply of Garbage Trucks | Broadening | 73765.7355 | 55611.6428 | Completed | PO + Contract issuance done | 2020-06-02 | Substantial completion / handover done |  |  | 2021-06-11 | Completed | Garbage truck | 112158 |  |  | South Korea | 374
Works | West | Bani Walid | Education | Rehabilitation of University | Deepening | 114678.1224 | 0 | Completed | [6 empty] | In Development | University
Works | West | Bani Walid | Education | Rehabilitation of University | Deepening | 153942.0278 | 0 | Completed | [6 empty] | In Development | University
Works | West | Bani Walid | Education | Rehabilitation of University | Deepening | 209612.5858 | 0 | Completed | [6 empty] | In Development | University |  | 31.7441 | 14.0092
Works | West | Bani Walid | Education | Rehabilitation of University | Deepening | 69950.8798 | 69950.8798 | Completed | PO + Contract issuance done | 2021-03-25 | Substantial completion / handover done | 2021-06-10 | 2021-06-20 | 2021-10-04 | Completed | University | 122619 | 31.7573 | 14.0259 | EU | 193
Goods | West | Bani Walid | Energy | Provision of Power Cables | Deepening | 78551.5515 | 78551.5515 | Completed | PO + Contract issuance done | 2019-10-16 | Substantial completion / handover done |  |  | 2019-10-26 | Completed | Cable | 112158 |  |  | USA | 10
Goods | West | Bani Walid | WASH | Supply of Sewage Pumps | Deepening | 16823.4366 | 16823.4366 | Completed | PO + Contract issuance done | 2021-04-25 | Substantial completion / handover done |  |  | 2021-05-27 | Completed | Water Pump | 112158 |  |  | UK | 32
Goods | East | Benghazi | WASH | Supply of Sewage Pumps | Deepening | 223663.7513 | 192436.3738 | Completed | PO + Contract issuance done | 2019-09-15 | Substantial completion / handover done |  |  | 2020-06-22 | Completed | Sewage Pump | 112158 |  |  | EU | 281
Works | East | Benghazi | Health | Rehabilitation of Hospital | Deepening | 178772.9634 | 178745.3758 | Completed | PO + Contract issuance done | 2020-05-06 | Substantial completion / handover done | 2020-06-14 | 2020-07-30 | 2021-04-08 | Completed | Hospital | 112158 | 32.0769 | 20.0929 | Norway | 337
Works | East | Benghazi | Public Infrastructure and Services | Rehabilitation of Public Building | Deepening | 71681.3125 | 71681.3125 | Completed | PO + Contract issuance done | 2020-07-09 | Substantial completion / handover done | 2020-07-20 |  | 2020-12-18 | Completed | Public Infrastructure | 112158 | 32.1192 | 20.0597 | Germany | 162
Works | East | Benghazi | Education | Rehabilitation of School | Deepening | 96613.8627 | 96598.5476 | Completed | PO + Contract issuance done | 2019-12-18 | Substantial completion / handover done | 2019-12-23 |  | 2020-07-20 | Completed | School | 112158 | 32.1154 | 20.0647 | Germany | 215
Works | East | Benghazi | Education | Rehabilitation of School | Deepening | 103199.2487 | 102696.2501 | Completed | PO + Contract issuance done | 2020-06-18 | Substantial completion / handover done | 2020-07-27 |  | 2020-10-14 | Completed | School | 112158 | 32.1439 | 20.0867 | Japan | 118
Works | East | Benghazi | Energy | Supply and Installation of Solar Street Lights | Deepening | 818666.9299 | 818666.9299 | Completed | PO + Contract issuance done | 2020-01-09 | Substantial completion / handover done | 2020-06-29 | 2020-08-16 | 2021-06-10 | Completed | Solar Street Light | 112158 |  |  | Germany | 518
Works | East | Benghazi | Public Infrastructure and Services | Rehabilitation of Public Building | Deepening | 264169.7825 | 264137.2378 | Completed | PO + Contract issuance done | 2020-08-22 | Substantial completion / handover done |  | 2020-11-18 | 2021-04-10 | Completed | Public Infrastructure | 112158 | 32.1182 | 20.0578 | Norway | 231
Works | East | Benghazi | Health | Rehabilitation of Clinic | Deepening | 30429.8257 | 30429.8257 | Completed | PO + Contract issuance done | 2020-12-05 | Substantial completion / handover done | 2020-12-10 |  | 2021-02-11 | Completed | Clinic | 98720 |  |  | France | 68
Works | East | Benghazi | Energy | Rehabilitation of Substation | Deepening | 64118.0364 | 64118.0364 | Completed | PO + Contract issuance done | 2021-06-26 | Substantial completion / handover done |  | 2021-07-28 | 2021-11-28 | Completed | Substation | 112158 | 32.0362 | 20.044 | Libya | 155
Goods | East | Derna | Health | Supply of Ambulances | Broadening | 106921.7889 | 94675.6082 | Completed | PO + Contract issuance done | 2020-01-21 | Substantial completion / handover done |  |  | 2020-10-06 | Completed | Ambulance | 112158 |  |  | Germany | 259
Goods | East | Derna | Solid Waste Management | Supply of Garbage Trucks | Broadening | 196928.7857 | 148463.6901 | Completed | PO + Contract issuance done | 2020-06-02 | Substantial completion / handover done |  |  | 2021-06-11 | Completed | Garbage truck | 112158 |  |  | South Korea | 374
Goods | East | Derna | Public Infrastructure and Services | Supply of Fire Fighting Trucks | Broadening | 293705.452 | 235709.6006 | Completed | PO + Contract issuance done | 2020-06-25 | Substantial completion / handover done |  |  | 2021-05-07 | Completed | Firetruck | 112158 |  |  | Germany | 316
Goods | East | Derna | WASH | Supply of Pesticide Sprayer Trucks | Broadening | 71783.9434 | 59860.248 | Completed | PO + Contract issuance done | 2020-06-25 | Substantial completion / handover done |  |  | 2020-12-16 | Completed | Pesticide Sprayer | 98720 |  |  | France | 174
Goods | East | Derna | Health | Supply of Generators | Broadening | 102649.1587 | 38058.2589 | Completed | PO + Contract issuance done | 2020-06-25 | Substantial completion / handover done |  |  | 2021-01-28 | Completed | Incinerator | 121748 |  |  | Japan | 217
Goods | East | Derna | WASH | Supply of Water Pumps | Broadening | 46922.9368 | 41332.766 | Completed | PO + Contract issuance done | 2021-04-13 | Substantial completion / handover done |  |  | 2021-11-08 | Completed | Water Pump | 112158 | 32.752 | 22.6407 | UK | 209
Works | East | Derna | Public Infrastructure and Services | Rehabilitation of Public Market | Broadening | 134233.813 | 0 | Completed | PO + Contract issuance done | 2022-06-22 |  |  |  |  | Underway | Public Infrastructure | 127766 |  |  | Japan
Works | East | Derna | Education | Rehabilitation of School | Broadening | 87330.1285 | 78586.9386 | Completed | PO + Contract issuance done | 2020-12-27 | Substantial completion / handover done | 2021-01-25 | 2021-02-20 | 2021-07-14 | Completed | School | 112158 |  |  | Libya | 199
Goods | South | Ghat | WASH | Supply of Sewage Suction Trucks | Broadening | 363592.6138 | 325946.0496 | Completed | PO + Contract issuance done | 2019-07-23 | Substantial completion / handover done |  |  | 2020-11-12 | Completed | Sewage suction truck | 112158 | 24.9583 | 10.1756 | Japan | 478
Goods | South | Ghat | WASH | Supply of Sewage Suction Trucks | Broadening | 374792.9015 | 359748.2346 | Completed | PO + Contract issuance done | 2019-07-18 | Substantial completion / handover done |  |  | 2020-07-14 | Completed | Water Tanker | 112158 | 24.9583 | 10.1756 | Germany | 362
Goods | South | Ghat | WASH | Supply of Vehicles | Broadening | 201029.2099 | 197214.4927 | Completed | PO + Contract issuance done | 2019-07-25 | Substantial completion / handover done |  |  | 2019-12-18 | Completed | Vehicle | 112158 | 24.9583 | 10.1756 | USA | 146
Goods | South | Ghat | WASH | Supply of Pesticide Sprayer Trucks | Broadening | 97158.6195 | 87511.6719 | Completed | PO + Contract issuance done | 2019-07-23 | Substantial completion / handover done |  |  | 2020-03-18 | Completed | Pesticide Sprayer | 112158 | 24.9752 | 10.1849 | EU | 239
Goods | South | Ghat | WASH | Supply of Generators | Broadening | 172731.4441 | 172934.269 | Completed | PO + Contract issuance done | 2019-07-10 | Substantial completion / handover done |  |  | 2020-03-16 | Completed | Generator | 112158 | 24.97393889 24.96379722 24.95229444 24.97313056 24.96244444 24.93944444 24.94606389 24.88128333 24.89 24.91415278 25.0925 25.78479722 25.78435833 25.76058611 25.79748333 25.82989444 24.91415278 24.96423889 24.95082778 24.949925 24.97151944 | 10.07 10.18631389 10.040025 10.01979167 10.18905556 10.16656111 10.0769 10.186225 10.54 10.53444444 10.35299444 10.56254722 10.56076944 10.56488889 10.53606667 10.51439444 10.93833333 10.18750833 10.18582222 10.15880278 10.17559722 | Germany | 250
Goods | South | Ghat | WASH | Supply of Sewage Pumps | Broadening | 55961.6106 | 40306.2706 | Completed | PO + Contract issuance done | 2019-10-17 | Substantial completion / handover done |  |  | 2020-06-14 | Completed | Sewage Pump | 112158 | 24.96423889 24.95082778 24.949925 24.97151944 | 10.18750833 10.18582222 10.15880278 10.17559722 | EU | 241
Goods | South | Ghat | WASH | Supply of Water Pumps | Broadening | 27783.914 | 15823.0826 | Completed | PO + Contract issuance done | 2019-10-16 | Substantial completion / handover done |  |  | 2020-06-14 | Completed | Water Pump | 112158 | 24.9731 | 10.1847 | Germany | 242
Goods | South | Ghat | WASH | Supply of Sewage Pumps | Broadening | 128763.8334 | 122346.095 | Completed | PO + Contract issuance done | 2020-02-25 | Substantial completion / handover done |  |  | 2020-10-07 | Completed | Water Pump | 112158 | 24.97393889 24.96379722 24.95229444 24.97313056 24.96244444 24.93944444 24.94606389 24.88128333 24.89 24.91415278 25.0925 25.78479722 25.78435833 25.76058611 25.79748333 25.82989444 24.91415278 | 10.07 10.18631389 10.040025 10.01979167 10.18905556 10.16656111 10.0769 10.186225 10.54 10.53444444 10.35299444 10.56254722 10.56076944 10.56488889 10.53606667 10.51439444 10.93833333 | Japan | 225
Goods | South | Ghat | Public Infrastructure and Services | Supply of Personal Protection Equipment | Broadening | 41298.7263 | 40612.655 | Completed | PO + Contract issuance done | 2020-06-02 | Substantial completion / handover done |  |  | 2021-04-11 | Completed | PPE | 98720 | 24.9731 | 10.1847 | France | 313
Goods | South | Ghat | WASH | Supply of Generators | Broadening | 97709.6259 | 26098.8074 | Completed | PO + Contract issuance done | 2019-10-18 | Substantial completion / handover done |  |  | 2020-03-18 | Completed | Generator | 112158 | 24.9731 | 10.1847 | EU | 152
Goods | South | Ghat | Energy | Provision of Power Cables | Broadening | 117510.2966 | 117510.2966 | Completed | PO + Contract issuance done | 2019-07-30 | Substantial completion / handover done |  |  | 2019-09-23 | Completed | Cable | 112158 | 24.9641 | 10.1858 | USA | 55
Goods | South | Ghat | WASH | Supply of Equipment | Broadening | 2979.3837 | 2979.3837 | Completed | PO + Contract issuance done | 2020-08-14 | Substantial completion / handover done |  |  | 2021-05-11 | Completed | Mechanical equipment | 112158 | 24.9731 | 10.1847 | Germany | 270
Goods | South | Ghat | WASH | Supply of Sewage Pumps | Broadening | 35203.4835 | 0 | BOQ development stage | [6 empty] | In Development | Water Pump
Goods | South | Ghat | WASH | Supply of Pipes and Fittings | Broadening | 6654.4725 | 0 | BOQ development stage | [6 empty] | In Development | WASH equipment
Goods | South | Ghat | WASH | Supply of Pipes and Fittings | Broadening | 5362.0593 | 0 | BOQ development stage | [6 empty] | In Development | WASH equipment
Works | South | Kufra | WASH | Borehole Drilling | Broadening | 136946.6975 | 0 | Completed | PO + Contract issuance done |  |  | 2021-03-31 |  |  | With Procurement | Borehole drilling | 112158 | 24.3261916666667 24.2199388888889 | 23.1863083333333 23.2964083333333 | EU
Works | South | Kufra | Energy | Supply of transformers | Broadening | 78366.3954 | 0 | Completed |  | 2021-01-29 |  | 2021-03-02 |  |  | In Development | Transformers | 122619
Works | South | Kufra | Public Infrastructure and Services | Rehabilitation of Public Infrastructure | Broadening | 389741.5229 | 0 | Completed | [6 empty] | In Development | Public Infrastructure |  |  |  | Germany
Works | South | Kufra | Energy | Supply and Installation of Solar Street Lights | Broadening | 491795.6396 | 491795.6396 | Completed | PO + Contract issuance done | 2020-07-13 | Substantial completion / handover done | 2020-10-12 |  | 2021-04-08 | Completed | Solar Street Light | 112158 |  |  | Norway | 269
Works | South | Kufra | Public Infrastructure and Services | Rehabilitation of Public Infrastructure | Broadening | 53506.2274 | 0 | BOQ development stage | [6 empty] | In Development | Public Infrastructure
Goods | South | Kufra | Public Infrastructure and Services | Supply of Fire Fighting Trucks | Broadening | 105813.5355 | 0 | BOQ development stage | [6 empty] | In Development | Firetruck
Goods | South | Kufra | Public Infrastructure and Services | Supply of Vehicles | Broadening | 109731.3277 | 83759.588 | Completed | PO + Contract issuance done | 2020-05-20 | Substantial completion / handover done |  |  | 2021-05-25 | Completed | Mechanical equipment | 112158 |  |  | Germany | 370
Works | South | Kufra | Education | Rehabilitation of School | Broadening | 59891.7111 | 0 | To be initiated | [6 empty] | In Development | School
Works | South | Kufra | Education | Rehabilitation of School | Broadening | 80002.6808 | 0 | To be initiated | [6 empty] | In Development | School
Works | South | Sebha | Education | Rehabilitation of School | Deepening | 170476.0702 | 169882.5548 | Completed | PO + Contract issuance done | 2019-12-12 | Substantial completion / handover done | 2020-01-08 |  | 2020-08-27 | Completed | School | 112158 | 27.0283972222222 27.0254333333333 | 14.4411833333333 14.4364833333333 | Germany | 259
Works | South | Sebha | Education | Rehabilitation of School | Deepening | 171275.0155 | 171211.7498 | Completed | PO + Contract issuance done | 2019-10-17 | Substantial completion / handover done | 2019-10-31 |  | 2020-05-11 | Completed | School | 112158 | 27.0249 27.0266333333333 | 14.4323222222222 14.4330194444444 | EU | 207
Works | South | Sebha | Public Infrastructure and Services | Rehabilitation of Public Building | Deepening | 120593.649 | 119637.3806 | Completed | PO + Contract issuance done | 2019-11-14 | Substantial completion / handover done |  | 2019-11-12 | 2021-07-05 | Completed | Public Infrastructure | 112158 | 27.0461 | 14.4204 | Japan | 599
Works | South | Sebha | Education | Rehabilitation of School | Deepening | 88464.4522 | 0 | Completed | PO + Contract issuance done | 2022-08-10 | Work progress 0 - 25% | 2022-08-21 |  |  | Underway | School | 112158 | 27.0360833333333 27.0372916666667 | 14.411175 14.4127972222222 | Netherlands
Works | South | Sebha | Education | Rehabilitation of School | Deepening | 93331.9589 | 93217.4136 | Completed | PO + Contract issuance done | 2020-02-14 | Substantial completion / handover done | 2020-09-01 | 2020-09-08 | 2021-01-21 | Completed | School | 112158 | 27.04135 27.04985 | 14.430925 14.4158777777778 | Japan | 342
Works | South | Sebha | Education | Rehabilitation of School | Deepening | 42699.4298 | 42684.2269 | Completed | PO + Contract issuance done | 2020-03-27 | Substantial completion / handover done | 2020-09-29 |  | 2021-05-05 | Completed | School | 112158 | 26.4386 | 14.2736 | Germany | 404
Works | South | Sebha | Health | Rehabilitation of Clinic | Deepening | 79220.1052 | 0 | Completed | PO + Contract issuance done | 2022-01-20 | Work progress over 75% | 2022-02-01 |  |  | Underway | Clinic | 122619 | 27.0659 | 14.4197 | EU
Works | South | Sebha | Health | Rehabilitation of Clinic | Deepening | 172061.0102 | 172060.5773 | Completed | PO + Contract issuance done | 2020-01-12 | Substantial completion / handover done | 2020-01-20 |  | 2020-08-24 | Completed | Clinic | 112158 | 27.0135 | 14.4408 | Netherlands | 225
Works | South | Sebha | Health | Rehabilitation of Clinic | Deepening | 30876.7484 | 30853.9786 | Completed | PO + Contract issuance done | 2019-12-05 | Substantial completion / handover done | 2020-01-02 |  | 2020-05-03 | Completed | Clinic | 112158 | 27.0361 | 14.416 | EU | 150
Works | South | Sebha | Health | Rehabilitation of Clinic | Deepening | 52846.9318 | 52828.7775 | Completed | PO + Contract issuance done | 2019-12-06 | Substantial completion / handover done | 2020-01-19 | 2020-01-26 | 2021-01-10 | Completed | Clinic | 112158 | 27.0421 | 14.4037 | Japan | 401
Works | South | Sebha | Health | Rehabilitation of Clinic | Deepening | 48509.4381 | 49516.0643 | Completed | PO + Contract issuance done | 2020-06-26 | Substantial completion / handover done | 2020-09-06 | 2020-09-10 | 2021-01-05 | Completed | Clinic | 112158 | 27.0479444444444 27.0408166666667 | 14.4284694444444 14.4339111111111 | Germany | 193
Goods | South | Sebha | Health | Supply of Ambulances | Deepening | 44323.0031 | 31062.069 | Completed | PO + Contract issuance done | 2019-09-23 | Substantial completion / handover done |  |  | 2020-03-12 | Completed | Ambulance | 112158 | 26.4395 | 14.2745 | South Korea | 171
Works | South | Sebha | Health | Rehabilitation of Clinic | Deepening | 37043.1854 | 35793.8714 | Completed | PO + Contract issuance done | 2019-12-12 | Substantial completion / handover done | 2019-12-25 | 2020-01-02 | 2021-05-02 | Completed | Clinic | 98720 | 26.8786 | 14.4271 | Germany | 507
Goods | South | Sebha | WASH | Supply of Sewage Suction Trucks | Deepening | 322136.184 | 263166.2688 | Completed | PO + Contract issuance done | 2019-07-04 | Substantial completion / handover done |  |  | 2020-07-22 | Completed | Sewage suction truck | 112158 | 27.0382 | 14.4317 | Germany | 384
Goods | South | Sebha | WASH | Supply of Sewage Pumps | Deepening | 152954.5484 | 105231.3666 | Completed | PO + Contract issuance done | 2019-10-01 | Substantial completion / handover done |  |  | 2020-07-22 | Completed | Sewage Pump | 112158 | 27.0382 | 14.4317 | EU | 295
Works | South | Sebha | WASH | Supply of Generators | Deepening | 34072.903 | 34061.4657 | Completed | PO + Contract issuance done | 2020-06-21 | Substantial completion / handover done | 2020-09-03 | 2020-09-18 | 2020-12-20 | Completed | Public Infrastructure | 112158 | refer to list | refer to list | Germany | 182
Works | South | Sebha | Energy | Supply and Installation of Solar Street Lights | Deepening | 1985669.6754 | 1985669.6754 | Completed | PO + Contract issuance done | 2020-03-03 | Substantial completion / handover done | 2020-12-03 | 2020-12-10 | 2021-12-23 | Completed | Solar Street Light | 112158 | refer to list | refer to list | Germany | 660
Works | South | Sebha | Public Infrastructure and Services | Rehabilitation of Public Infrastructure | Deepening | 536641.9109 | 0 | Completed |  | 2020-04-11 |  |  |  |  | In Development | Public Infrastructure |  | 27.0266 | 14.4575 | Germany
Works | South | Sebha | Public Infrastructure and Services | Rehabilitation of Public Building | Deepening | 78290.2734 | 22795.9108 | Completed | PO + Contract issuance done | 2021-05-12 | Work progress over 75% | 2021-09-15 | 2021-10-25 |  | Underway | Public Infrastructure | 122619 | 27.0086 | 14.4385 | EU
Goods | South | Sebha | Energy | Provision of Power Cables | Deepening | 72812.1548 | 72812.1548 | Completed | PO + Contract issuance done | 2019-07-30 | Substantial completion / handover done |  |  | 2019-09-08 | Completed | Cable | 112158 | 27.0025 | 14.4613 | USA | 40
Works | West | Sirt | Education | Rehabilitation of School | Deepening | 201438.7187 | 176856.9766 | Completed | PO + Contract issuance done | 2020-04-15 | Substantial completion / handover done | 2020-04-26 |  | 2020-10-28 | Completed | School | 112158 | 31.1999 | 16.6083 | Germany | 196
Works | West | Sirt | Education | Rehabilitation of School | Deepening | 97582.5147 | 87824.2632 | Completed | PO + Contract issuance done | 2021-08-18 | Substantial completion / handover done |  |  | 2022-02-25 | Completed | School | 122619 | 31.2094 | 16.5861 | EU | 191
Works | West | Sirt | Education | Rehabilitation of School | Deepening | 120496.6297 | 120496.6297 | Completed | PO + Contract issuance done | 2020-11-06 | Substantial completion / handover done | 2020-11-16 |  | 2021-04-15 | Completed | School | 122619 | 31.2081 | 16.566 | EU | 160
Works | West | Sirt | Education | Rehabilitation of School | Deepening | 588620.0048 | 0 | To be initiated | [6 empty] | In Development | School
Goods | West | Sirt | Health | Supply of Generators | Deepening | 81271.1602 | 0 | Completed |  | 2022-04-06 |  |  |  |  | Underway | Generator | 122619 |  |  | EU
Goods | West | Sirt | WASH | Supply of Generators | Deepening | 66857.5586 | 0 | Completed | [6 empty] | In Development | Mechanical equipment
Goods | West | Sirt | WASH | Supply of Generators | Deepening | 102899.6752 | 0 | Completed |  | 2022-04-06 |  |  |  |  | Underway | Generator | 122619 |  |  | EU
Goods | West | Sirt | WASH | Supply of Water Pumps | Deepening | 38263.7573 | 0 | Completed | PO + Contract issuance done | 2022-07-21 |  |  |  |  | Underway | Water Pump | 112158 |  |  | South Korea
Goods | West | Sirt | Public Infrastructure and Services | Supply of Generators | Deepening | 88872.901 | 0 | Completed |  | 2022-04-06 |  |  |  |  | Underway | Vehicle | 112158 |  |  | Switzerland
Goods | West | Sirt | Public Infrastructure and Services | Supply of Generators | Deepening | 82658.7333 | 0 | Completed |  | 2022-04-06 |  |  |  |  | Underway | Pesticide Sprayer | 98720 |  |  | Norway
Goods | West | Sirt | Public Infrastructure and Services | Supply of Generators | Deepening | 104407.6817 | 0 | BOQ development stage | [6 empty] | In Development | Vehicle
Works | West | Sirt | Public Infrastructure and Services | Rehabilitation of Public Building | Deepening | 45237.432 | 45205.0352 | Completed | PO + Contract issuance done | 2021-04-17 | Substantial completion / handover done | 2021-04-22 | 2021-04-29 | 2021-09-14 | Completed | Public Infrastructure | 122619 | 31.2106 | 16.5867 | EU | 150
Goods | West | Sirt | Health | Supply of Generators | Deepening | 119327.8928 | 0 | Completed | [6 empty] | In Development | Generator
Works | West | Sirt | Education | Rehabilitation of School | Deepening | 137591.9731 | 0 | Completed | PO + Contract issuance done | 2022-09-03 | Site Handover done | 2022-09-04 |  |  | Underway | School | 127766 | 31.1952 | 16.5767 | Japan
Goods | West | Sirt | Health | Supply of Ambulances | Deepening | 71745.3018 | 0 | Completed |  | 2022-04-06 |  |  |  |  | Underway | Ambulance | 127766 |  |  | Japan
Goods | West | Tawergha | Health | Supply of Ambulances | Broadening | 39020.1104 | 0 | Completed | PO + Contract issuance done | 2018-12-01 | Substantial completion / handover done |  |  | 2019-08-28 | Completed | Ambulance | 112158 |  |  |  | 270
Works | West | Tawergha | Energy | Supply and Installation of Solar Street Lights | Broadening | 70864.4594 | 70864.4594 | Completed | PO + Contract issuance done | 2019-09-03 | Substantial completion / handover done |  |  | 2020-01-23 | Completed | Solar Street Light | 112158 |  |  | EU | 142
Works | West | Tawergha | Education | Rehabilitation of School | Broadening | 71058.6164 | 71058.6164 | Completed | PO + Contract issuance done | 2020-01-10 | Substantial completion / handover done | 2020-05-12 |  | 2020-07-07 | Completed | School | 112158 |  |  | Germany | 179
Works | West | Tawergha | Education | Rehabilitation of School | Broadening | 49876.2243 | 49868.2267 | Completed | PO + Contract issuance done | 2020-01-30 | Substantial completion / handover done | 2020-05-12 |  | 2020-07-27 | Completed | School | 112158 |  |  | Germany | 179
Works | West | Tawergha | Education | Rehabilitation of School | Broadening | 51601.3461 | 51582.3615 | Completed | PO + Contract issuance done | 2020-01-21 | Substantial completion / handover done | 2020-05-12 | 2020-05-16 | 2020-09-02 | Completed | School | 112158 |  |  | Germany | 225
Goods | West | Tawergha | Public Infrastructure and Services | Supply of Computer Equipment | Broadening | 23771.7569 | 23771.7569 | Completed | PO + Contract issuance done | 2020-04-29 | Substantial completion / handover done |  |  | 2020-10-31 | Completed | IT equipment | 112158 |  |  | Norway | 185
Works | West | Tawergha | Public Infrastructure and Services | Rehabilitation of Public Building | Broadening | 5900.5734 | 5828.0996 | Completed | PO + Contract issuance done | 2020-08-26 | Substantial completion / handover done | 2020-09-02 | 2020-09-02 | 2020-09-13 | Completed | Public Infrastructure | 112158 |  |  | Germany | 18
Works | West | Tawergha | Energy | Supply and Installation of Solar Street Lights | Broadening | 286228.1363 | 286228.1363 | Completed | PO + Contract issuance done | 2020-11-16 | Substantial completion / handover done | 2020-12-17 |  | 2021-08-23 | Completed | Solar Street Light | 122619 |  |  | EU | 280
Goods | West | Tawergha | WASH | Supply of Sewage Suction Trucks | Broadening | 112989.8825 | 110121.5559 | Completed | PO + Contract issuance done | 2020-12-31 | Substantial completion / handover done |  |  | 2022-03-22 | Completed | Sewage suction truck | 112158 |  |  | Libya | 446
Goods | West | Tawergha | WASH | Supply of Water Tankers | Broadening | 65857.6413 | 54251.7816 | Completed | PO + Contract issuance done | 2020-12-31 | Substantial completion / handover done |  |  | 2022-03-22 | Completed | Water Tanker | 112158 |  |  | Libya | 446
Goods | West | Tawergha | WASH | Supply of Pesticide Sprayer Trucks | Broadening | 64524.1107 | 54309.0603 | Completed | PO + Contract issuance done | 2020-12-31 | Substantial completion / handover done |  |  | 2021-09-08 | Completed | Pesticide Sprayer | 112158 |  |  | Libya | 251
Works | West | Tawergha | Health | Rehabilitation of Clinic | Broadening | 138433.2597 | 0 | Completed | PO + Contract issuance done | 2022-01-22 | Work progress 50% - 75% | 2022-02-03 |  |  | Underway | Clinic | 122619 |  |  | EU
Works | West | Tawergha | Public Infrastructure and Services | Cleaning Works and Removal of War Remnants | Broadening | 98419.046 | 98419.046 | Completed | PO + Contract issuance done | 2021-05-03 | Substantial completion / handover done | 2021-06-09 |  | 2021-08-25 | Completed | ERW removal | 112158 |  |  | UK | 114
Works | West | Tawergha | WASH | Supply of Water Pumps | Broadening | 218721.2029 | 0 | Completed | PO + Contract issuance done | 2022-06-14 | Site Handover done | 2022-06-22 |  |  | Underway | WASH equipment | 112158 |  |  | Libya
Goods | West | Tripoli | Solid Waste Management | Supply of Refuse Trailers | Deepening | 1715388.5235 | 1543358.5026 | Completed | PO + Contract issuance done | 2019-07-25 | Substantial completion / handover done |  |  | 2020-04-06 | Completed | Gargabe trailer | 112158 |  |  | Germany | 256
Goods | West | Tripoli | Solid Waste Management | Supply of Refuse Trailers | Deepening | 566802.2641 | 520509.7766 | Completed | PO + Contract issuance done | 2019-11-21 | Substantial completion / handover done |  |  | 2020-07-01 | Completed | Gargabe trailer | 112158 |  |  | EU | 223
Works | West | Tripoli | Public Infrastructure and Services | Supply & Installation of Eco-LED Street light | Deepening | 227413.8948 | 0 | Completed | PO + Contract issuance done | 2021-11-12 |  |  |  |  | Underway | LED Light | 127766 |  |  | Japan
Works | West | Tripoli | Public Infrastructure and Services | Rehabilitation of Public Infrastructure | Deepening | 651825.1801 | 361881.2438 | Completed | PO + Contract issuance done | 2021-06-20 | Work progress over 75% | 2021-09-29 |  |  | Underway | Public Infrastructure | 112158 |  |  | Libya
Works | West | Tripoli | Public Infrastructure and Services | Cleaning Works and Removal of War Remnants | Deepening | 46816.1396 | 46816.1396 | Completed | PO + Contract issuance done | 2020-12-30 | Substantial completion / handover done |  |  | 2021-03-31 | Completed | ERW removal | 112158 |  |  | Libya | 91
Works | West | Tripoli | Public Infrastructure and Services | Cleaning Works and Removal of War Remnants | Deepening | 107037.3674 | 56749.1877 | Completed | PO + Contract issuance done | 2021-04-08 | Substantial completion / handover done |  |  | 2022-08-09 | Completed | ERW removal | 112158 |  |  | UK | 488
Works | South | Ubari | Education | Rehabilitation of University | Deepening | 173128.6563 | 0 | Completed | [6 empty] | In Development | University |  | 26.5897 | 12.7684 | Germany
Works | South | Ubari | Education | Rehabilitation of University | Deepening | 155825.3897 | 155781.179 | Completed | PO + Contract issuance done | 2019-12-10 | Substantial completion / handover done |  | 2019-12-24 | 2020-10-04 | Completed | University | 112158 | 26.5903 | 12.7685 | Netherlands | 299
Works | South | Ubari | Public Infrastructure and Services | Rehabilitation of Public Building | Deepening | 345994.7089 | 345414.1489 | Completed | PO + Contract issuance done | 2019-11-01 | Substantial completion / handover done | 2019-11-10 |  | 2020-10-04 | Completed | Public Infrastructure | 112158 | 26.5959 | 12.7798 | EU | 338
Works | South | Ubari | Energy | Supply and Installation of Solar Street Lights | Deepening | 1000517.4706 | 1000517.4706 | Completed | PO + Contract issuance done | 2020-01-09 | Substantial completion / handover done |  | 2020-04-15 | 2020-11-26 | Completed | Solar Street Light | 112158 | 26.5896 | 12.7749 | Germany | 322
Works | South | Ubari | Public Infrastructure and Services | Rehabilitation of Public Infrastructure | Deepening | 224228.6433 | 201800.1467 | Completed | PO + Contract issuance done | 2020-12-24 | Substantial completion / handover done |  | 2021-04-06 | 2022-03-27 | Completed | Public Infrastructure | 112158 | 26.5877 | 12.7771 | Libya | 458
Works | South | Ubari | Public Infrastructure and Services | Rehabilitation of Public Infrastructure | Deepening | 20417.9506 | 20410.8381 | Completed | PO + Contract issuance done | 2021-02-06 | Substantial completion / handover done |  | 2021-02-21 | 2021-08-29 | Completed | Public Infrastructure | 112158 |  |  | South Korea | 204
Works | South | Ubari | Education | Rehabilitation of University | Deepening | 470870.2418 | 236025.3461 | Completed | PO + Contract issuance done | 2020-09-24 | Works completed | 2020-10-26 | 2021-02-01 |  | Underway | University | 112158 |  |  | UK
Goods | West | Tripoli | Covid-19 | Covid-19 Medical Equipment | Deepening | 13470.5847 | 13470.5847 | Completed | PO + Contract issuance done | 2019-12-05 | Substantial completion / handover done |  |  | 2020-08-31 | Completed |  | 112158 |  |  | Germany | 270
Goods | West | Tripoli | Covid-19 | Covid-19 Medical Equipment | Deepening | 86742.2231 | 0 | Completed | PO + Contract issuance done | 2019-07-15 | Substantial completion / handover done |  |  | 2020-04-10 | Completed | [5 empty] | 270
Goods | West | Tripoli | Covid-19 | Covid-19 Medical Equipment | Deepening | 0 | 0 | Completed | PO + Contract issuance done | 2020-01-19 | Substantial completion / handover done |  |  | 2020-10-15 | Completed | [5 empty] | 270
Goods | West | Tripoli | Covid-19 | Covid-19 Medical Equipment | Deepening | 59106.7783 | 0 | Completed | Advertisement period completed | [5 empty] | With Procurement |  |  |  |  | Japan
Works | South | Kufra | Covid-19 | Covid-19 Isolatin Centre | Broadening | 21792.5791 | 21074.1367 | Completed | PO + Contract issuance done | 2021-02-04 | Substantial completion / handover done | 2021-02-15 | 2021-02-28 | 2021-08-04 | Completed | Hospital | 122619 |  |  | EU | 181
Goods | South | Ghat | Covid-19 | Covid-19 Medical Equipment | Broadening | 63416.0389 | 0 | Completed | PO + Contract issuance done | 2020-04-06 | Substantial completion / handover done |  |  | 2021-01-01 | Completed | Medical Equipment |  |  |  | Germany | 270
Works | East | Derna | Covid-19 | Covid-19 Isolatin Centre | Broadening | 163477.9162 | 0 | Completed | PO + Contract issuance done | 2021-12-03 | Work progress 50% - 75% | 2021-12-18 |  |  | Underway | Hospital | 127766 |  |  | Japan
Goods | South | Sebha | Covid-19 | Covid-19 Medical Equipment | Deepening | 87511.2884 | 74622.4324 | Completed | PO + Contract issuance done | 2020-06-03 | Substantial completion / handover done |  |  | 2021-02-28 | Completed |  | 98720 |  |  | Norway | 270
Goods | East | Ajdabiya | Covid-19 | Covid-19 Medical Equipment | Broadening | 127602.9623 | 100640.1191 | Completed | PO + Contract issuance done | 2020-05-21 | Substantial completion / handover done |  |  | 2021-02-15 | Completed |  | 98720 |  |  | Norway | 270
Goods | West | Tripoli | Covid-19 | Covid-19 Medical Equipment | Deepening | 0 | 0 | Completed | PO + Contract issuance done | 2020-05-01 | Substantial completion / handover done |  |  | 2021-01-26 | Completed | [5 empty] | 270
Goods | West | Tripoli | Covid-19 | Covid-19 Medical Equipment | Deepening | 147392.8445 | 146918.6854 | Completed | PO + Contract issuance done | 2020-11-13 | Substantial completion / handover done |  |  | 2021-08-10 | Completed |  | 112158 |  |  | Germany | 270
Works | West | Tripoli | Covid-19 | Covid-19 Isolatin Centre | Deepening | 206275.3189 | 206275.3189 | Completed | PO + Contract issuance done | 2021-07-25 | Substantial completion / handover done |  |  | 2021-11-18 | Completed | Medical Equipment | 127766 |  |  | Japan | 116
Works | West | Tripoli | Covid-19 | Covid-19 Isolatin Centre | Deepening | 238260.0327 | 0 | To be initiated | [6 empty] | In Development | Medical Equipment

## donor_list
Before | After
C/S ROK | South Korea
Canada (DFATD) | Canada
Germany (KfW) | Germany
Germany(KfW) | Germany
Germany(MOFA) | Germany
Germay(KfW) | Germany
Gov't of Libya | Libya
KfW | Germany
START | Japan
SUSC | EU
UK (FCO) | UK
USAID | USA

## Master
SN | Works / Goods | Region | Location | Sector | Project | Funding Stage | Contracted Amount | Amount | Actual Expenditure (including admin fees) | Expenditure | Initial Phase Status | Procurement Phase Status | Contract Signing | Implementation Phase Status | Site handover date | Start Date | Actual completion date | Overall Status | Remarks | Remarks date | Proc plan ref | Type | Quantity | Donor Number | Donor | Project ID | Latitude | Longitude | Randarray | amount multiplier
1 |  |  | Sirt | Solid Waste Management |  | Phase 1 |  | 0 |  | 0 | [18 empty] | 0.5075 | 0.52262
2 | Goods | West | Sirt | Solid Waste Management | Supply of Garbage Trucks | Phase 1 | 851180.7353 | 592330.7558 | 851550.8713 | 592588.3309 | Completed | PO + Contract issuance done | 2017-10-01 | Substantial completion / handover done |  |  | 2018-07-24 | Completed | Delivered on 24 July 2018 |  | Completed | Garbage truck | 8 | 10159 717 | EU C/S ROK | 98720 | 31.2103 | 16.4923 | 0.57162 | 0.69589
3 | Goods | West | Sirt | Solid Waste Management | Supply of Garbage Trucks | Phase 1 | 1200000 | 885386.3895 |  | 0 | To be initiated | [6 empty] | In Development | With Project | 2020-02-14 | Further Funding | Truck | 8 | [5 empty] | 0.72237 | 0.73782
4 | Goods | West | Sirt | Solid Waste Management | Supply of Garbage Trucks | Phase 1 | 800000 | 505202.5674 |  | 0 | To be initiated | [6 empty] | In Development | With Project | 2020-02-14 | Further Funding | Garbage truck | 8 | [5 empty] | 0.6597 | 0.6315
5 | Goods | West | Sirt | Solid Waste Management | Supply of Garbage Trucks | Phase 1 | 1500000 | 794730.1535 |  | 0 | To be initiated | [6 empty] | In Development | With Project | 2020-02-14 | Further Funding | Truck | 10 | [5 empty] | 0.74352 | 0.52982
6 | Goods | West | Sirt | Solid Waste Management | Supply of Garbage Bins | Phase 1 | 90918.12 | 48357.8675 | 90918.12 | 48357.8675 | Completed | PO + Contract issuance done | 2017-10-01 | Substantial completion / handover done |  |  | 2018-07-26 | Completed | Delivered on 26 July 2018 |  | Completed | Garbage Bin | 200 | 10159 717 | EU C/S ROK | 98720 | 31.2096 | 16.4925 | 0.62979 | 0.53188
7 | Goods | West | Sirt | Solid Waste Management | Supply of Garbage Bins | Phase 1 | 40000 | 26331.5703 |  | 0 | To be initiated | [6 empty] | In Development | With Project | 2020-02-14 | Further Funding | Garbage Bin | 80 | [5 empty] | 0.68525 | 0.65829
8 | Goods | West | Sirt | WASH | Supply of Sewage Suction Trucks | Phase 1 | 300000 | 222241.0919 |  | 0 | To be initiated | [6 empty] | In Development | With Project | 2020-02-14 | Further Funding | Sewage suction truck | 2 | [5 empty] | 0.57228 | 0.7408
9 |  |  | Sirt | WASH |  | Phase 1 |  | 0 |  | 0 | [18 empty] | 0.64055 | 0.65722
10 |  |  | Sirt | Health |  | Phase 1 |  | 0 |  | 0 | [18 empty] | 0.58882 | 0.72689
11 | Works | West | Sirt | Health | Rehabilitation of Clinic | Phase 1 | 133063 | 83941.1089 | 133063 | 83941.1089 | Completed | PO + Contract issuance done | 2018-03-29 | Substantial completion / handover done | 2018-04-09 | 2018-04-16 | 2018-08-28 | Completed | Delivered on 28 August 2018 |  | Completed | Clinic | 1 | 10159 11410 | EU UK | 98720 | 31.198 | 16.576 | 0.57708 | 0.63084
12 | Goods | West | Sirt | Health | Supply of Freezers | Phase 1 | 70018 | 48281.9072 | 70018 | 48281.9072 | Completed | PO + Contract issuance done | 2020-10-10 | Substantial completion / handover done | 2020-10-22 | 2020-10-28 | 2021-03-28 | Completed | Completed and handed over on 28 March 2021. Site handed over to contractor on 22 Oct 2020. Contract issued on 10 October 2020 | 2021-03-31 | Completed | Other health building | 1 | 112 | France | 98720 | 31.184 | 16.582 | 0.55367 | 0.68956
13 | Goods | West | Sirt | Health | Supply of Ambulances | Phase 1 | 146466.603 | 85445.3144 | 159591.33 | 93101.9842 | Completed | PO + Contract issuance done | 2017-02-01 | Substantial completion / handover done |  |  | 2017-12-31 | Completed | Only 3 regular ambulances delivered as "test case" for transportation to Sirt; initially remaining totals were subject to reset. Khalifa confirmed on 24 Feb 2020 that remaining 9 needs to be delivered as well | 2020-02-24 | Completed | Ambulance | 3 | 717 | C/S ROK | 98720 | 31.1876 | 16.5897 | 0.73711 | 0.58338
14 | Works | West | Sirt | Health | Rehabilitation of Clinic | Phase 1 | 90000 | 49276.8937 |  | 0 | BOQ development stage | [6 empty] | In Development | Khalifa informed back in Jan 2021 that health sector authorities have reconfirmed that they need this rehabilitation. A letter stating the same was shared. | 2021-06-24 | Further Funding | Clinic | 1 | [5 empty] | 0.73417 | 0.54752
15 | Works | West | Sirt | Health | Rehabilitation of Clinic | Phase 1 | 56100 | 39032.8204 | 56100 | 39032.8204 | Completed | PO + Contract issuance done | 2019-08-05 | Substantial completion / handover done | 2019-09-03 |  | 2020-03-22 | Completed | Substantially handed over on 22 March 2020 | 2020-04-15 | Completed | Clinic | 1 | 717 | C/S ROK | 112158 | 31.2083 | 16.5711 | 0.59653 | 0.69577
16 | Works | West | Sirt | Health | Rehabilitation of Clinic | Phase 1 | 33570 | 18984.6069 | 33570 | 18984.6069 | Completed | PO + Contract issuance done | 2018-12-07 | Substantial completion / handover done | 2019-01-03 | 2019-01-10 | 2019-03-31 | Completed | Completed on 31 March 2019 | 2019-04-11 | Completed | Clinic | 1 | 141 | Japan | 98720 | 31.1754 | 16.5944 | 0.62698 | 0.56552
17 | Works | West | Sirt | Health | Rehabilitation of Clinic | Phase 1 | 35047 | 23862.1006 | 35047 | 23862.1006 | Completed | PO + Contract issuance done | 2019-07-05 | Substantial completion / handover done |  |  | 2019-10-28 | Completed | Substantial handover on 28 Oct 2019 | 2019-11-07 | Completed | Clinic | 1 | 10283 | Germay(KfW) | 112158 | 31.2089 | 16.5596 | 0.56724 | 0.68086
18 | Works | West | Sirt | Health | Rehabilitation of Clinic | Phase 1 | 31550 | 18463.3032 | 31720 | 18562.7885 | Completed | PO + Contract issuance done | 2018-11-13 | Substantial completion / handover done | 2018-11-30 | 2018-12-07 | 2019-03-15 | Completed |  | 2019-04-11 | Completed | Clinic | 1 | 10159 | EU | 112158 | 31.1886 | 16.4173 | 0.60921 | 0.58521
19 |  |  | Sirt | Education |  | Phase 1 |  | 0 |  | 0 | [18 empty] | 0.65846 | 0.71262
20 | Works | West | Sirt | Education | Rehabilitation of School | Phase 1 | 134250 | 89867.9497 | 132692 | 88825.0129 | Completed | PO + Contract issuance done | 2017-11-11 | Substantial completion / handover done | 2017-11-20 | 2017-11-27 | 2018-02-05 | Completed | Completed in 2018 |  | Completed | School | 1 | 10283 | Germay(KfW) | 98720 | 31.2079 | 16.5728 | 0.52752 | 0.66941
21 | Works | West | Sirt | Education | Rehabilitation of School | Phase 1 | 77279 | 39672.1347 | 77279 | 39672.1347 | Completed | PO + Contract issuance done | 2018-07-25 | Substantial completion / handover done | 2017-09-06 | 2017-09-13 | 2018-12-25 | Completed | School completed in 2017 Roof completed in 2018 |  | Completed | School | 1 | 10283 141 | Germay(KfW) + Japan | 98720 | 31.2052 | 16.5972 | 0.60241 | 0.51336
22 | Works | West | Sirt | Education | Rehabilitation of School | Phase 1 | 69504 | 43275.2108 | 69203 | 43087.7994 | Completed | PO + Contract issuance done | 2017-11-16 | Substantial completion / handover done | 2017-12-02 | 2017-12-09 | 2018-07-28 | Completed | Completed in 2018. Contract was ammended and the budget is the full amount |  | Completed | School | 1 | 10283 717 | Germany (KfW) C/S ROK | 98720 | 31.2067 | 16.5877 | 0.57745 | 0.62263
23 | Works | West | Sirt | Education | Rehabilitation of School | Phase 1 | 144166 | 81050.6416 | 144166 | 81050.6416 | Completed | PO + Contract issuance done | 2017-11-09 | Substantial completion / handover done | 2017-11-19 | 2017-11-26 | 2018-03-25 | Completed | Completed in 2018 |  | Completed | School | 1 | 10283 | Germay(KfW) | 98720 | 31.2101 | 16.5703 | 0.61585 | 0.5622
24 | Works | West | Sirt | Education | Rehabilitation of School | Phase 1 | 114166 | 58317.7648 | 114166 | 58317.7648 | Completed | PO + Contract issuance done | 2017-12-17 | Substantial completion / handover done | 2017-12-25 | 2018-01-01 | 2018-04-24 | Completed | Completed in 2018 |  | Completed | School | 1 | 10159 10283 | EU Germany (KfW) | 98720 112158 | 31.2099 | 16.5862 | 0.69853 | 0.51082
25 | Works | West | Sirt | Education | Rehabilitation of School | Phase 1 | 309030 | 198566.2847 | 308922 | 198496.8897 | Completed | PO + Contract issuance done | 2018-11-08 | Substantial completion / handover done | 2018-11-30 | 2018-12-04 | 2019-04-04 | Completed |  | 2019-04-11 | Completed | School | 1 | 12113 | Canada (DFATD) | 98720 | 31.1778 | 16.5967 | 0.54709 | 0.64255
26 | Works | West | Sirt | Education | Rehabilitation of School | Phase 1 | 60000 | 30779.8454 | 59830 | 30692.6358 | Completed | PO + Contract issuance done | 2018-11-13 | Substantial completion / handover done | 2018-11-30 | 2018-12-07 | 2019-03-15 | Completed |  | 2019-04-11 | Completed | School | 1 | 10159 | EU | 112158 | 31.1874 | 16.4175 | 0.64835 | 0.513
27 | Works | West | Sirt | Education | Rehabilitation of School | Phase 1 | 268305 | 177684.7519 | 268305 | 177684.7519 | Completed | PO + Contract issuance done | 2019-05-27 | Substantial completion / handover done | 2019-06-11 |  | 2019-10-20 | Completed | Handed over on 20 Oct 2019. | 2019-10-21 | Completed | School | 1 | 10159 | EU | 112158 | 31.2073 | 16.5791 | 0.65347 | 0.66225
28 | Works | West | Sirt | Education | Rehabilitation of School | Phase 1 | 266037 | 190090.894 | 266037 | 190090.894 | Completed | PO + Contract issuance done | 2018-11-13 | Substantial completion / handover done | 2018-11-28 | 2018-12-06 | 2019-04-14 | Completed |  | 2019-04-11 | Completed | School | 1 | 187 | Norway | 98720 | 31.2067 | 16.5604 | 0.56162 | 0.71453
29 | Works | West | Sirt | Education | Rehabilitation of School | Phase 1 |  | 0 |  | 0 | To be initiated | [6 empty] | Cancelled | End user to identify/Pending Sirt reset. Reconciled in new list | 2020-02-17 | Cancelled | [7 empty] | 0.69522 | 0.57246
30 | Works | West | Sirt | Education | Rehabilitation of School | Phase 1 |  | 0 |  | 0 | To be initiated | [6 empty] | Cancelled | End user to identify/Pending Sirt reset. Reconciled in new list | 2020-02-17 | Cancelled | [7 empty] | 0.55654 | 0.72366
31 | Works | West | Sirt | Education | Rehabilitation of School | Phase 1 |  | 0 |  | 0 | To be initiated | [6 empty] | Cancelled | End user to identify/Pending Sirt reset. Reconciled in new list | 2020-02-17 | Cancelled | [7 empty] | 0.62534 | 0.709
32 | Works | West | Sirt | Education | Rehabilitation of School | Phase 1 | 65975 | 36440.281 | 65975 | 36440.281 | Completed | PO + Contract issuance done | 2018-12-11 | Substantial completion / handover done | 2018-12-31 | 2019-01-07 | 2019-03-27 | Completed |  | 2019-04-11 | Completed | Other Educational building | 1 | 11410 | UK (FCO) | 98720 | 31.1992 | 16.594 | 0.52636 | 0.55233
33 | Works | West | Sirt | Education | Rehabilitation of School | Phase 1 | 283601 | 190689.5227 | 283601 | 190689.5227 | Completed | PO + Contract issuance done | 2019-05-27 | Substantial completion / handover done | 2019-09-02 | 2019-09-09 | 2019-12-25 | Completed | substantial completion monitoring visit done on 25 dec 2019 | 2020-01-09 | Completed | Other Educational building | 1 | 10159 | EU | 112158 | 31.2093 | 16.5869 | 0.59683 | 0.67239
34 | Works | West | Sirt | Education | Rehabilitation of School | Phase 1 | 387160 | 224318.402 | 387160 | 224318.402 | Completed | PO + Contract issuance done | 2019-05-21 | Substantial completion / handover done |  | 2019-06-03 | 2019-12-08 | Completed | Substantial handover on 5 Nov 2019 | 2019-11-06 | Completed | Other Educational building | 1 | 182 10159 | Netherlands Germay(KfW) | 112158 | 31.2088 | 16.5709 | 0.59418 | 0.57939
35 |  |  | Sirt | Health |  | Phase 1 |  | 0 |  | 0 | Completed | [17 empty] | 0.74338 | 0.65229
36 | Goods | West | Sirt | Health | Supply of Ambulances | Phase 1 | 97644.402 | 65089.0348 | 123945.18 | 82620.9385 | Completed | PO + Contract issuance done | 2017-02-01 | Substantial completion / handover done |  |  | 2017-12-31 | Completed | Delivered on XXXX |  | Completed | Ambulance | 2 |  |  | 98720 | 31.1838 | 16.5843 | 0.70251 | 0.66659
37 | Goods | West | Sirt | Health | Supply of Medical Waste incinerator | Phase 1 | 86505 | 44166.1126 | 90887.34 | 46403.5662 | Completed | PO + Contract issuance done | 2017-11-03 | Substantial completion / handover done |  |  | 2017-12-31 | Completed | Delivered in 2017. Pending installtion due to visa issues related to technician | 2019-11-22 | Completed | Incinerator | 1 | 11410 | UK (FCO) | 98720 | 31.1838 | 16.5843 | 0.63973 | 0.51056
38 |  |  | Sirt |  |  | Phase 1 |  | 0 |  | 0 | [18 empty] | 0.65424 | 0.71887
39 |  | West | Sirt | WASH | Supply of Sewage Pumps | Phase 1 |  | 0 |  | 0 | [7 empty] | Cancelled | Handed over to USAID for implementation, Pending Sirt reset |  | Cancelled | [7 empty] | 0.72237 | 0.72883
40 |  | West | Sirt | WASH | Supply of Sewage Pumps | Phase 1 |  | 0 |  | 0 | [7 empty] | Cancelled | Handed over to USAID for implementation, Pending Sirt reset |  | Cancelled | [7 empty] | 0.65787 | 0.63296
41 |  | West | Sirt | WASH | Supply of Electrical Equipment | Phase 1 |  | 0 |  | 0 | [7 empty] | Cancelled | Handed over to USAID for implementation, Pending Sirt reset |  | Cancelled | [7 empty] | 0.69522 | 0.7233
42 | Works | West | Bani Walid | Education | Rehabilitation of School | Phase 1 | 30005 | 22486.0766 | 133815 | 100282.431 | Completed | PO + Contract issuance done | 2019-05-20 | Substantial completion / handover done |  |  | 2019-10-17 | Completed | Substantial handover on 17 Oct 2019 | 2019-10-24 | Completed | School | 1 | 10159 | EU | 112158 | 31.3886 | 13.7567 | 0.71619 | 0.74941
43 | Works | West | Bani Walid | Education | Rehabilitation of School | Phase 1 | 43400 | 24729.7433 |  | 0 | Completed | PO + Contract issuance done | 2019-05-20 | Substantial completion / handover done |  |  | 2019-10-17 | Completed | Substantial handover on 17 Oct 2019 | 2019-10-24 | Completed | School | 1 | 10159 | EU | 112158 | 31.7519 | 14.0185 | 0.57142 | 0.56981
44 | Works | West | Bani Walid | Education | Rehabilitation of School | Phase 1 | 60410 | 32171.5696 |  | 0 | Completed | PO + Contract issuance done | 2019-05-20 | Substantial completion / handover done |  |  | 2019-10-17 | Completed | Substantial handover on 17 Oct 2019 | 2019-10-24 | Completed | School | 1 | 10159 | EU | 112158 | 31.7501 | 14.0152 | 0.61516 | 0.53255
45 | Works | West | Bani Walid | Education | Rehabilitation of School | Phase 1 | 46796 | 33698.0155 | 42116.4 | 30328.2139 | Completed | PO + Contract issuance done | 2019-05-04 | Substantial completion / handover done | 2019-07-21 |  | 2019-11-26 | Completed | Handed over on 26 Nov 2019, signed docs received on 16 Jan 2020 | 2020-01-16 | Completed | School | 1 | 10159 | EU | 112158 | 31.7456 | 14.0097 | 0.55853 | 0.7201
46 | Works | West | Bani Walid | Education | Rehabilitation of School | Phase 1 | 51198 | 26253.0344 | 46078.2 | 23627.731 | Completed | PO + Contract issuance done | 2019-05-04 | Substantial completion / handover done | 2019-07-21 |  | 2019-11-26 | Completed | Handed over on 26 Nov 2019, signed docs received on 16 Jan 2020 | 2020-01-16 | Completed | School | 1 | 10159 | EU | 112158 | 31.8306 | 14.0875 | 0.51514 | 0.51277
47 | Works | West | Bani Walid | Education | Rehabilitation of School | Phase 1 | 57327 | 36574.4226 | 51594.3 | 32916.9803 | Completed | PO + Contract issuance done | 2019-05-04 | Substantial completion / handover done | 2019-07-21 |  | 2019-11-26 | Completed | Handed over on 26 Nov 2019, signed docs received on 16 Jan 2020 | 2020-01-16 | Completed | School | 1 | 10159 | EU | 112158 | 31.7327 | 14.4851 | 0.65981 | 0.638
48 | Works | West | Bani Walid | Health | Rehabilitation of Clinic | Phase 1 | 100800 | 54801.1425 | 100800 | 54801.1425 | Completed | PO + Contract issuance done | 2018-10-12 | Substantial completion / handover done | 2018-10-16 | 2018-10-23 | 2019-01-02 | Completed | 100% complete | contract signed on 11 Oct | Completed | Other health building | 1 | 10480 | USAID | 98720 | 31.7586 | 14.0285 | 0.50981 | 0.54366
49 | Works | West | Bani Walid | Education | Rehabilitation of School | Phase 1 | 71385 | 46925.9017 | 71385 | 46925.9017 | Completed | PO + Contract issuance done | 2018-11-16 | Substantial completion / handover done | 2018-12-05 | 2018-12-12 | 2019-02-05 | Completed | 100% complete | Contract signed 16th Nov 2018 | Completed | School | 1 | 10480 | USAID | 112158 | 31.775 | 13.9959 | 0.50458 | 0.65736
50 | Goods | West | Bani Walid | Health | Supply of Ambulances | Phase 1 | 99840.2353 | 72330.5088 | 110777.5433 | 80254.1786 | Completed | PO + Contract issuance done | 2018-02-01 | Substantial completion / handover done |  |  | 2018-12-31 | Completed | Delivered on XXXX |  | Completed | Ambulance | 2 | 717 95 | C/S ROK Denmark | 98720 | 31.7564 | 14.0268 | 0.52722 | 0.72446
51 | Goods | West | Bani Walid | Health | Supply of Generators | Phase 1 | 211682.1478 | 127786.2971 | 229682.2905 | 138652.4547 | Completed | PO + Contract issuance done | 2017-04-01 | Substantial completion / handover done |  |  | 2018-02-15 | Completed | Delivered on 15 Feb 2018 |  | Completed | Generator | 4 | 10283 141 | Germay(KfW) Japan | 98720 | 31.757 | 14.0269 | 0.62761 | 0.60367
52 | Goods | West | Bani Walid | Health | Supply of Furniture | Phase 1 |  | 0 |  | 0 | To be initiated | [6 empty] | Cancelled | MoH verbally agreed that they will supply. Letter received on 13 July 2020 confirming cancellation of this project. | 2020-07-15 | Cancelled | [7 empty] | 0.65638 | 0.74143
53 | Goods | West | Bani Walid | Health | Supply of Freezers | Phase 1 |  | 0 |  | 0 | To be initiated | [6 empty] | Cancelled | MoH verbally agreed that they will supply. Letter received on 13 July 2020 confirming cancellation of this project. | 2020-07-15 | Cancelled | [7 empty] | 0.58134 | 0.57719
54 | Works | West | Bani Walid | Health | Rehabilitation of Hospital | Phase 1 |  | 0 |  | 0 | Site survey done | [6 empty] | Cancelled |  | 2018-11-02 | Cancelled | [7 empty] | 0.64564 | 0.63951
55 | Works | West | Bani Walid | Health | Rehabilitation of Hospital | Phase 1 |  | 0 |  | 0 | Site survey done | [6 empty] | Cancelled |  | 2018-11-02 | Cancelled | [7 empty] | 0.54872 | 0.67937
56 | Works | West | Bani Walid | Health | Rehabilitation of Hospital | Phase 1 |  | 0 |  | 0 | Site survey done | [6 empty] | Cancelled |  | 2018-11-02 | Cancelled | [7 empty] | 0.57204 | 0.5518
57 | Goods | West | Bani Walid | Health | Supply of Generators | Phase 1 | 71060.2903 | 36197.9821 | 71060.2903 | 36197.9821 | Completed | PO + Contract issuance done | 2017-07-01 | Substantial completion / handover done |  |  | 2018-05-24 | Completed | Delivered on 24 May 2018 |  | Completed | Generator | 1 | 117 137 | Germany(MOFA) Italy | 98720 | 31.7565 | 14.0277 | 0.51613 | 0.5094
58 | Works | West | Bani Walid | Health | Rehabilitation of Hospital | Phase 1 |  | 0 |  | 0 | Site survey done | [6 empty] | Cancelled |  | 2018-11-02 | Cancelled | [7 empty] | 0.65124 | 0.60196
59 | Works | West | Bani Walid | Health | Rehabilitation of Hospital | Phase 1 |  | 0 |  | 0 | Site survey done | [6 empty] | Cancelled |  | 2018-11-02 | Cancelled | [7 empty] | 0.71802 | 0.72435
60 | Works | West | Bani Walid | Health | Rehabilitation of Hospital | Phase 1 |  | 0 |  | 0 | Site survey done | [6 empty] | Cancelled |  | 2018-11-02 | Cancelled | [7 empty] | 0.60996 | 0.55032
61 | Works | West | Bani Walid | Health | Rehabilitation of Hospital | Phase 1 | 536264 | 372308.841 | 479015.19 | 332563.0477 | Completed | PO + Contract issuance done | 2019-11-08 | Substantial completion / handover done | 2020-08-09 | 2020-08-19 | 2021-03-15 | Completed | Works completed as of 15 March 2021.Signed handover documents shared on 7 Sep 2021. Rehabilitation activites started on 19 August 2020. To rehabilitate the Isolation Centre, to address immediate COVID-19 priority, instead of rehabilitating Bani Walid General Hospital. Variation order (VO) submitted for approval. | 2021-10-01 | Completed | Hospital | 1 | 10283 182 | Germay(KfW) Netherlands | 112158 | 31.7568 | 14.0276 | 0.69311 | 0.69426
62 | Goods | West | Bani Walid | Health | Supply of Ambulances | Phase 1 | 49920.1177 | 25069.3892 | 64164.2567 | 32222.6549 | Completed | PO + Contract issuance done | 2018-02-01 | Substantial completion / handover done |  |  | 2018-12-31 | Completed | Delivered on XXXX |  | Completed | Ambulance | 1 | 717 95 | C/S ROK Denmark | 98720 | 31.7564 | 14.0268 | 0.63452 | 0.50219
63 | Goods | West | Bani Walid | Health | Supply of Generators | Phase 1 | 197238.25 | 103892.803 | 100364.213 | 52865.605 | Completed | PO + Contract issuance done | 2019-02-17 | Substantial completion / handover done |  |  | 2019-10-03 | Completed | Delivered to Bani Walid on 3 Oct 2019 | 2019-10-09 | Completed | Water Pump | 4 | 10480 10283 | USAID Germany(KfW) | 98720 112158 | 31.7565 | 14.0277 | 0.64625 | 0.52674
64 | Goods | West | Bani Walid | Health | Supply of Generators | Phase 1 |  | 0 |  | 0 | To be initiated | [6 empty] | Cancelled | MoH verbally agreed that they will supply. Letter received on 13 July 2020 confirming cancellation of this project. | 2020-07-15 | Cancelled | [7 empty] | 0.55763 | 0.69541
65 | Goods | West | Bani Walid | Solid Waste Management | Supply of Garbage Trucks | Phase 1 | 242112.88 | 163907.0147 | 309322.14 | 209406.7385 | Completed | PO + Contract issuance done | 2017-04-01 | Substantial completion / handover done |  |  | 2018-02-08 | Completed | Delivered on 2018 |  | Completed | Garbage truck | 2 | 117 95 | Germany(MOFA) Denmark | 98720 | 31.7307 | 14.0492 | 0.73197 | 0.67699
66 | Goods | West | Bani Walid | Public Infrastructure and Services | Supply of Generators | Phase 1 | 49074.8327 | 34328.485 | 49074.8327 | 34328.485 | Completed | PO + Contract issuance done | 2017-07-01 | Substantial completion / handover done |  |  | 2018-05-24 | Completed | Delivered on 24 May 2018 |  | Completed | Generator | 1 | 117 137 | Germany(MOFA) Italy | 98720 | 31.7562 | 14.0222 | 0.63929 | 0.69951
67 | Goods | West | Bani Walid | WASH | Supply of Pesticide Sprayer Trucks | Phase 1 | 77749.49 | 40108.2276 | 71103.61 | 36679.8518 | Completed | PO + Contract issuance done | 2018-03-28 | Substantial completion / handover done |  |  | 2018-12-31 | Completed | Delivered on XXXX |  | Completed | Pesticide Sprayer | 2 | 10159 95 | EU Denmark | 98720 | 31.7513 | 13.9893 | 0.7141 | 0.51586
68 | Goods | West | Bani Walid | Public Infrastructure and Services | Supply of Vehicles | Phase 1 |  | 0 |  | 0 | To be initiated | [6 empty] | Cancelled | Confirmed by Mehdi | 2020-02-17 | Cancelled | [7 empty] | 0.57849 | 0.64119
69 | Goods | West | Bani Walid | Public Infrastructure and Services | Supply of Vehicles | Phase 1 |  | 0 |  | 0 | To be initiated | [6 empty] | Cancelled | Confirmed by Mehdi | 2020-02-17 | Cancelled | [7 empty] | 0.62216 | 0.69139
70 | Goods | West | Bani Walid | WASH | Supply of Water Pumps | Phase 1 | 280221.1316 | 188132.6661 | 255944.03 | 171833.696 | Completed | PO + Contract issuance done | 2018-06-24 | Substantial completion / handover done |  |  | 2019-04-01 | Completed | Delivered to Bani Walid on 1st April 2019 |  | Completed | Water Pump | 7 | 137 11410 | Italy UK (FCO) | 98720 | 31.7522 | 14.02 | 0.52779 | 0.67137
71 | Goods | West | Bani Walid | WASH | Supply of Water Pumps | Phase 1 | 7848.17 | 4014.6021 | 7554.95 | 3864.6102 | Completed | PO + Contract issuance done | 2018-06-24 | Substantial completion / handover done |  |  | 2019-05-12 | Completed | Pumps delivered to Bani Walid on 12 May 2019 | 2019-05-14 | Completed | Water Pump | 6 | 137 10480 | Italy USAID | 98720 112158 | 31.7522 | 14.02 | 0.56165 | 0.51153
72 | Goods | West | Bani Walid | WASH | Supply of Generators | Phase 1 | 160000 | 116435.076 |  | 0 | Completed | PO + Contract issuance done | 2018-10-01 | Substantial completion / handover done |  |  | 2019-06-27 | Completed | Delivered on 27 June 2019 | 2020-02-17 | Completed | Generator | 1 |  |  |  | 31.7522 | 14.02 | 0.69564 | 0.72772
73 | Goods | West | Bani Walid | WASH | Supply of Generators | Phase 1 | 35805.5488 | 20771.5693 | 35805.5488 | 20771.5693 | Completed | PO + Contract issuance done | 2018-06-24 | Substantial completion / handover done |  |  | 2019-02-10 | Completed | Delivered to Bani Walid on 10/02/2019. Transfer of title signed by Mayor. |  | Completed | Generator | 2 | 10159 717 141 | EU C/S ROK Japan | 98720 | 31.7522 | 14.02 | 0.65412 | 0.58012
74 | Goods | West | Bani Walid | WASH | Supply of Sewage Suction Trucks | Phase 1 | 173959.928 | 128746.7868 | 160728.16 | 118954.028 | Completed | PO + Contract issuance done | 2018-06-05 | Substantial completion / handover done |  |  | 2019-04-03 | Completed | Delivered to Bani Walid on 3 April 2019. | 2019-05-07 | Completed | Sewage suction truck | 1 | 10159 141 | EU Japan | 98720 | 31.7522 | 14.02 | 0.60037 | 0.74009
75 | Goods | West | Bani Walid | WASH | Maintenance of Vehicles | Phase 1 |  | 0 |  | 0 | To be initiated | [6 empty] | Cancelled | Confirmed by Mehdi | 2020-02-17 | Cancelled | [7 empty] | 0.51095 | 0.68076
76 | Goods | West | Bani Walid | Education | Provision of Educational Equipment | Phase 1 | 52920.537 | 36395.8889 | 57420.5726 | 39490.7706 | Completed | PO + Contract issuance done | 2018-02-01 | Substantial completion / handover done |  |  | 2018-12-31 | Completed | Delivered on 2018 | 2019-07-08 | Completed | Generator | 1 | 10283 141 | Germay(KfW) Japan | 98720 | 31.7545 | 14.0255 | 0.55742 | 0.68775
77 | Works | East | Benghazi | Health | Rehabilitation of Hospital | Phase 1 | 87817 | 63702.1437 | 87817 | 63702.1437 | Completed | PO + Contract issuance done | 2017-05-12 | Substantial completion / handover done | 2017-05-23 |  | 2017-09-27 | Completed | Completed in 2017 |  | Completed | Hospital | 1 | 10159 | EU | 98720 | 32.203 | 20.1809 | 0.59251 | 0.7254
78 | Works | East | Benghazi | Health | Rehabilitation of Clinic | Phase 1 | 41423 | 21610.9857 | 41423 | 21610.9857 | Completed | PO + Contract issuance done | 2017-01-29 | Substantial completion / handover done | 2017-02-13 |  | 2017-06-20 | Completed | Completed in 2017 |  | Completed | Clinic | 1 | 137 | Italy | 98720 | 32.0506 | 20.1103 | 0.68528 | 0.52171
79 | Works | East | Benghazi | Health | Rehabilitation of Clinic | Phase 1 | 44566 | 24889.0186 | 44566 | 24889.0186 | Completed | PO + Contract issuance done | 2017-05-31 | Substantial completion / handover done |  |  | 2017-09-13 | Completed | Completed in 2017 |  | Completed | Clinic | 1 | 112 | France | 98720 | 32.0291 | 20.0696 | 0.55461 | 0.55848
80 | Works | East | Benghazi | Health | Rehabilitation of Clinic | Phase 1 | 101496 | 64109.371 | 101496 | 64109.371 | Completed | PO + Contract issuance done | 2016-11-22 | Substantial completion / handover done | 2016-12-01 |  | 2017-02-20 | Completed | Completed in 2017 |  | Completed | Clinic | 1 | 137 | Italy | 98720 | 32.0535 | 20.1093 | 0.70512 | 0.63164
81 | Works | East | Benghazi | Public Infrastructure and Services | Rehabilitation of Public Building | Phase 1 | 115718 | 59611.6499 | 115204.04 | 59346.8855 | Completed | PO + Contract issuance done | 2016-11-22 | Substantial completion / handover done | 2016-11-30 |  | 2017-02-26 | Completed | Completed in 2017 |  | Completed | Public Infrastructure | 1 | 137 | Italy | 98720 | 32.098 | 20.1839 | 0.50991 | 0.51515
82 | Works | East | Benghazi | Public Infrastructure and Services | Rehabilitation of Public Building | Phase 1 | 31442 | 21498.213 | 31442 | 21498.213 | Completed | PO + Contract issuance done | 2016-12-31 | Substantial completion / handover done | 2017-01-08 |  | 2017-05-01 | Completed | Completed in 2017 |  | Completed | Public Infrastructure | 1 | 137 | Italy | 98720 | 32.114 | 20.0756 | 0.70613 | 0.68374
83 | Works | East | Benghazi | Public Infrastructure and Services | Rehabilitation of Public Infrastructure | Phase 1 | 145000 | 81854.0188 | 145000 | 81854.0188 | Completed | PO + Contract issuance done | 2017-08-01 | Substantial completion / handover done |  |  | 2017-11-03 | Completed | DLP completed End Nov 2018 | 2019-04-17 | Completed | Public Infrastructure | 1 | 10283 | Germay(KfW) | 98720 | 32.1065 | 20.0792 | 0.53889 | 0.56451
84 | Works | East | Benghazi | Education | Rehabilitation of School | Phase 1 | 117265.5 | 82857.1478 | 117265.5 | 82857.1478 | Completed | PO + Contract issuance done | 2017-06-14 | Substantial completion / handover done |  |  | 2017-10-10 | Completed | Completed in 2017 |  | Completed | School | 1 | 187 10283 | Norway Germany(KfW) | 98720 | 32.0543 | 20.0367 | 0.60795 | 0.70658
85 | Works | East | Benghazi | Energy | Rehabilitation of Substation | Phase 1 | 98300 | 57047.1025 | 98300 | 57047.1025 | Completed | PO + Contract issuance done | 2017-04-20 | Substantial completion / handover done |  |  | 2017-08-29 | Completed | Completed in 2017 |  | Completed | Substation | 1 | 10159 | EU | 98720 | 32.099 | 20.1318 | 0.66462 | 0.58034
86 | Works | East | Benghazi | Energy | Rehabilitation of Substation | Phase 1 | 262325 | 135536.4762 | 262325 | 135536.4762 | Completed | PO + Contract issuance done | 2017-05-20 | Substantial completion / handover done |  |  | 2017-08-30 | Completed | Completed in 2017 |  | Completed | Substation | 1 | 141 151 | Japan Gov't of Libya | 98720 112158 | 32.1039 | 20.1548 | 0.6527 | 0.51667
87 | Goods | East | Benghazi | Solid Waste Management | Supply of Garbage Trucks | Phase 1 | 561057.2 | 412574.3701 | 579407.2 | 426068.0739 | Completed | PO + Contract issuance done | 2016-02-01 | Substantial completion / handover done |  |  | 2016-12-10 | Completed |  |  | Completed | Garbage truck | 5 | 117 | Germany(MOFA) | 98720 |  |  | 0.55519 | 0.73535
88 | Goods | East | Benghazi | Solid Waste Management | Supply of Garbage Bins | Phase 1 | 42699 | 24457.4494 | 42699 | 24457.4494 | Completed | PO + Contract issuance done | 2017-10-01 | Substantial completion / handover done |  |  | 2018-07-26 | Completed |  |  | Completed | Garbage Bin | 30 | 117 | Germany(MOFA) | 98720 |  |  | 0.62699 | 0.57279
89 | Goods | East | Benghazi | Health | Supply of Ambulances | Phase 1 | 132438.024 | 70167.3835 | 477284.51 | 252871.5261 | Completed | PO + Contract issuance done | 2016-02-01 | Substantial completion / handover done |  |  | 2016-12-05 | Completed |  |  | Completed | Ambulance | 2 | 117 137 | Germany(MOFA) Italy | 98720 | 32.0773 | 20.0979 | 0.74934 | 0.52981
90 | Goods | East | Benghazi | Health | Supply of Ambulances | Phase 1 | 66219.012 | 42893.4279 | é | #VALUE! | Completed | PO + Contract issuance done | 2016-02-01 | Substantial completion / handover done |  |  | 2016-12-05 | Completed |  |  | Completed | Ambulance | 1 | 117 137 | Germany(MOFA) Italy | 98720 | 32.051 | 20.1107 | 0.68322 | 0.64775
91 | Goods | East | Benghazi | Health | Supply of Ambulances | Phase 1 | 132438.024 | 67281.7589 | é | #VALUE! | Completed | PO + Contract issuance done | 2016-02-01 | Substantial completion / handover done |  |  | 2016-12-05 | Completed |  |  | Completed | Ambulance | 2 | 117 137 | Germany(MOFA) Italy | 98720 | 32.1101 | 20.0897 | 0.64748 | 0.50802
92 | Goods | East | Benghazi | Health | Supply of Ambulances | Phase 1 | 132438.024 | 81043.4658 | é | #VALUE! | Completed | PO + Contract issuance done | 2016-02-01 | Substantial completion / handover done |  |  | 2016-12-05 | Completed | Delivered on 5 Dec 2016 |  | Completed | Ambulance | 2 | 117 137 | Germany(MOFA) Italy | 98720 | 32.114 | 20.0755 | 0.52667 | 0.61194
93 | Goods | East | Benghazi | Health | Supply of Ambulances | Phase 1 | 66219.012 | 36325.8095 | é | #VALUE! | Completed | PO + Contract issuance done | 2016-02-01 | Substantial completion / handover done |  |  | 2016-12-05 | Completed |  |  | Completed | Ambulance | 1 | 117 137 | Germany(MOFA) Italy | 98720 | 32.0199 | 20.1239 | 0.58813 | 0.54857
94 | Goods | East | Benghazi | Health | Supply of Generators | Phase 1 | 49074.8327 | 35565.9272 | 49074.8327 | 35565.9272 | Completed | PO + Contract issuance done | 2016-04-01 | Substantial completion / handover done |  |  | 2017-02-04 | Completed | Delivered on 4 Feb 2017 |  | Completed | Generator | 1 | 117 137 | Germany(MOFA) Italy | 98720 | 32.2031 | 20.1806 | 0.66642 | 0.72473
95 | Goods | East | Benghazi | Public Infrastructure and Services | Supply of Generators | Phase 1 | 49074.8327 | 31202.0612 | 49074.8327 | 31202.0612 | Completed | PO + Contract issuance done | 2016-04-01 | Substantial completion / handover done |  |  | 2017-02-01 | Completed | Delivered on 1 Feb 2017 |  | Completed | Generator | 1 | 117 137 | Germany(MOFA) Italy | 98720 | 32.114 | 20.0756 | 0.73058 | 0.63581
96 | Goods | East | Benghazi | Health | Suppy of Medical Equipment | Phase 1 |  | 0 |  | 0 | [7 empty] | Cancelled | End user suspended agreement, now pending Benghazi stocktake |  | Cancelled | [7 empty] | 0.65616 | 0.50196
97 | Goods | East | Benghazi | Health | Suppy of Medical Equipment | Phase 1 | 234436.47 | 137656.0454 | 260940.84 | 153218.8406 | Completed | PO + Contract issuance done | 2017-06-30 | Substantial completion / handover done |  |  | 2018-12-31 | Completed |  |  | Completed | Medical Equipment | 1 | 141 10159 | Japan EU | 98720 | 32.0535 | 20.1093 | 0.5837 | 0.58718
98 | Goods | East | Benghazi | Health | Supply of Solar Panels | Phase 1 | 202480.2125 | 132320.1948 | 202480.2125 | 132320.1948 | Completed | PO + Contract issuance done | 2016-08-24 | Substantial completion / handover done |  |  | 2016-12-31 | Completed | Delivered on XXXX |  | Completed | Solar Panels | 1 | 117 10283 10159 | Germany(MOFA) Norway EU | 98720 | 32.0773 | 20.0979 | 0.51119 | 0.6535
99 | Goods | East | Benghazi | Health | Supply of Solar Panels | Phase 1 | 202708.2125 | 104547.6456 | 202708.2125 | 104547.6456 | Completed | PO + Contract issuance done | 2016-08-24 | Substantial completion / handover done |  |  | 2016-12-31 | Completed | Delivered on XXXX |  | Completed | Solar Panels | 1 | 117 10283 10159 | Germany(MOFA) Norway EU | 98720 | 32.077 | 20.0927 | 0.6346 | 0.51575
100 | Goods | East | Benghazi | Health | Supply of Solar Panels | Phase 1 | 196364.0625 | 103709.529 | 196364.0625 | 103709.529 | Completed | PO + Contract issuance done | 2016-08-24 | Substantial completion / handover done |  |  | 2016-12-31 | Completed | Delivered on XXXX |  | Completed | Solar Panels | 1 | 117 10283 10159 | Germany(MOFA) Norway EU | 98720 | 32.1101 | 20.0897 | 0.54358 | 0.52815
101 | Goods | East | Benghazi | Health | Supply of Solar Panels | Phase 1 | 202309.2125 | 101892.1184 | 202309.2125 | 101892.1184 | Completed | PO + Contract issuance done | 2016-08-24 | Substantial completion / handover done |  |  | 2016-12-31 | Completed |  |  | Completed | Solar Panels | 1 | 117 10283 10159 | Germany(MOFA) Norway EU | 98720 | 32.2031 | 20.1806 | 0.58461 | 0.50365
102 | Goods | East | Benghazi | Public Infrastructure and Services | Supply of Vehicles | Phase 1 | 123616.67 | 72661.6633 | 123616.67 | 72661.6633 | Completed | PO + Contract issuance done | 2017-06-06 | Substantial completion / handover done |  |  | 2017-12-31 | Completed | Delivered on XXXX |  | Completed | Vehicle | 1 | 141 10283 | Japan Germay(KfW) | 98720 | 32.114 | 20.0755 | 0.50965 | 0.5878
103 | Goods | East | Benghazi | Public Infrastructure and Services | Supply of Vehicles | Phase 1 | 38431.4 | 27753.2166 | 38431.4 | 27753.2166 | Completed | PO + Contract issuance done | 2017-09-08 | Substantial completion / handover done |  |  | 2017-12-31 | Completed |  |  | Completed | Boat | 2 | 10283 | Germay(KfW) | 98720 | 32.114 | 20.0755 | 0.55366 | 0.72215
104 | Works | East | Benghazi | Energy | Supply and Installation of Solar Street Lights | Phase 1 | 884284.81 | 644011.005 | 818390.26 | 596021.0193 | Completed | PO + Contract issuance done | 2017-04-20 | Substantial completion / handover done |  |  | 2019-09-01 | Completed | Substantial handover done on 1 Sep 2019. | 2019-10-08 | Completed | Solar Street Light | 12 | 10159 717 10283 141 187 | EU C/S ROK Germay(KfW) Japan Norway | 98720 112158 | 32.0068 | 20.1297 | 0.54027 | 0.72828
105 | Goods | East | Benghazi | WASH | Supply of Sewage Pumps | Phase 1 | 380117.86 | 209917.9152 | 374230.18 | 206666.4776 | Completed | PO + Contract issuance done | 2017-08-10 | Substantial completion / handover done |  |  | 2018-12-31 | Completed | Completed in 2018 |  | Completed | Sewage Pump | 6 | 10480 10283 95 10159 | USAID Germany (KfW) Denmark EU | 98720 112158 |  |  | 0.7399 | 0.55224
106 | Goods | East | Benghazi | WASH | Supply of Water Pumps | Phase 1 | 259186.64 | 175389.6954 | 259186.64 | 175389.6954 | Completed | PO + Contract issuance done | 2017-08-14 | Substantial completion / handover done |  |  | 2018-12-31 | Completed | Delivered on XXXX |  | Completed | Water Pump | 1 | 10480 95 | USAID Denmark | 112158 98720 | 32.0749 | 20.2307 | 0.66941 | 0.67669
107 | Goods | East | Benghazi | Health | Supply of Generators | Phase 1 | 71060.2903 | 46846.7377 | 71060.2903 | 46846.7377 | Completed | PO + Contract issuance done | 2016-04-01 | Substantial completion / handover done |  |  | 2017-02-01 | Completed |  |  | Completed | Generator | 1 | 117 137 | Germany(MOFA) Italy | 98720 | 32.0502 | 20.1101 | 0.61281 | 0.65925
108 | Goods | East | Benghazi | Health | Supply of Generators | Phase 1 | 71060.2903 | 38443.6482 | 71060.2903 | 38443.6482 | Completed | PO + Contract issuance done | 2016-04-01 | Substantial completion / handover done |  |  | 2017-02-01 | Completed |  |  | Completed | Generator | 1 | 117 137 | Germany(MOFA) Italy | 98720 | 32.0199 | 20.1239 | 0.68282 | 0.541
109 | Goods | West | Kikla | Health | Supply of Ambulances | Phase 1 | 132438.024 | 91831.4441 | 106394.21 | 73772.8762 | Completed | PO + Contract issuance done | 2016-04-01 | Substantial completion / handover done |  |  | 2017-02-01 | Completed | Delivered on Feb 2017 |  | Completed | Ambulance | 2 | 117 137 | Germany(MOFA) Italy | 98720 | 32.0654 | 12.6953 | 0.60065 | 0.69339
110 | Goods | West | Kikla | Health | Suppy of Medical Equipment | Phase 1 | 333688.05 | 229796.3655 | 332731.05 | 229137.3214 | Completed | PO + Contract issuance done | 2018-11-21 | Substantial completion / handover done |  |  | 2019-12-16 | Completed | Installation and training pending. Site visit in early 2020 couldn't be conducted due to security situation. Coordinatioin with GPU Copenhagen will be done to ascertain when this can be done. Delivered to Kikla on 16 Dec 2019 | 2020-06-10 | Completed | Medical Equipment | 1 | 187 | Norway | 98720 | 32.0645 | 12.6905 | 0.72568 | 0.68866
111 | Works | West | Kikla | Health | Rehabilitation of Hospital | Phase 1 | 459251 | 242458.9372 | 459251 | 242458.9372 | Completed | PO + Contract issuance done | 2017-07-03 | Substantial completion / handover done | 2017-06-14 | 2017-06-21 | 2018-02-17 | Completed | Substantial handover in 17 Feb 2018 |  | Completed | Hospital | 1 | 10283 | Germay(KfW) | 98720 | 32.0645 | 12.6905 | 0.66363 | 0.52794
112 | Works | West | Kikla | Health | Rehabilitation of Hospital | Phase 1 | 15525 | 11350.9158 | 15525 | 11350.9158 | Completed | PO + Contract issuance done | 2018-03-07 | Substantial completion / handover done | 2018-03-30 | 2018-04-06 | 2018-05-08 | Completed |  |  | Completed | Other health building | 1 | 11410 | UK (FCO) | 98720 | 32.0651 | 12.6908 | 0.72375 | 0.73114
113 | Works | West | Kikla | Health | Rehabilitation of Hospital | Phase 1 | 126762 | 67748.8884 | 126762 | 67748.8884 | Completed | PO + Contract issuance done | 2017-05-22 | Substantial completion / handover done | 2017-06-04 | 2017-06-11 | 2017-10-11 | Completed | Completed in 2017 |  | Completed | Hospital | 1 | 141 | Japan | 98720 | 32.065 | 12.6897 | 0.66725 | 0.53446
114 | Goods | West | Kikla | Public Infrastructure and Services | Supply of Fire Fighting Trucks | Phase 1 | 196117.04 | 122240.9885 | 204075.18 | 127201.3473 | Completed | PO + Contract issuance done | 2016-02-01 | Substantial completion / handover done |  |  | 2016-11-17 | Completed | Delivered on 2016 |  | Completed | Firetruck | 1 | 117 | Germany(MOFA) | 98720 | 32.0654 | 12.6953 | 0.61128 | 0.62331
115 | Goods | West | Kikla | Public Infrastructure and Services | Supply of IT Equipment | Phase 1 | 19475 | 10397.6038 | 19270 | 10288.1553 | Completed | PO + Contract issuance done | 2017-02-03 | Substantial completion / handover done |  |  | 2017-02-23 | Completed | Delivered on 2017 |  | Completed | IT equipment | 1 | 137 | Italy | 98720 | 32.0654 | 12.6953 | 0.67511 | 0.53389
116 | Goods | West | Kikla | Public Infrastructure and Services | Supply of Solar Power System | Phase 1 | 13963 | 9555.4975 | 13963 | 9555.4975 | Completed | PO + Contract issuance done | 2016-12-29 | Substantial completion / handover done |  |  | 2017-12-31 | Completed | Delivered on XXXX |  | Completed | Solar backup | 1 | 137 | Italy | 98720 | 32.0654 | 12.6953 | 0.72811 | 0.68434
117 | Goods | West | Kikla | Public Infrastructure and Services | Supply of Sport Equipment | Phase 1 | 64413 | 46842.0703 | 64413 | 46842.0703 | Completed | PO + Contract issuance done | 2017-05-01 | Substantial completion / handover done |  |  | 2018-02-09 | Completed | Delivered on Feb 2018 |  | Completed | Sports equipment | 1 | 10283 | Germay(KfW) | 98720 | 32.0654 | 12.6953 | 0.67851 | 0.72721
118 | Works | West | Kikla | Public Infrastructure and Services | Rehabilitation of Public Building | Phase 1 | 76370 | 44231.4687 | 76370 | 44231.4687 | Completed | PO + Contract issuance done | 2017-03-02 | Substantial completion / handover done | 2017-03-13 | 2017-03-20 | 2017-05-14 | Completed | Completed in 2017 |  | Completed | Public Infrastructure | 1 | 10159 | EU | 98720 | 32.0277 | 12.7078 | 0.59671 | 0.57917
119 | Goods | West | Kikla | Energy | Provision of Power Cables | Phase 1 | 98149.6654 | 56751.4917 | 98149.6654 | 56751.4917 | Completed | PO + Contract issuance done | 2016-05-01 | Substantial completion / handover done |  |  | 2017-02-01 | Completed | Delivered on Feb 2017 |  | Completed | Generator | 2 | 117 137 | Germany(MOFA) Italy | 98720 | 32.0654 | 12.6953 | 0.74987 | 0.57821
120 | Goods | West | Kikla | Education | Provision of Educational Equipment | Phase 1 | 92919.17 | 50964.9357 | 92919.17 | 50964.9357 | Completed | PO + Contract issuance done | 2017-10-18 | Substantial completion / handover done |  |  | 2017-12-31 | Completed | Delivered on XXXX |  | Completed | Educational equipment | 1 | 10283 | Germay(KfW) | 98720 | 32.0654 | 12.6953 | 0.60506 | 0.54849
121 | Goods | West | Kikla | Education | Provision of Educational Equipment | Phase 1 | é | #VALUE! | é | #VALUE! | Completed | PO + Contract issuance done | 2017-10-18 | Substantial completion / handover done |  |  | 2017-12-31 | Completed | budget merged with school funriture for Kikla |  | Completed | Educational equipment | 1 | 10283 | Germay(KfW) | 98720 | 32.0654 | 12.6953 | 0.54272 | 0.50373
122 | Goods | West | Kikla | Education | Provision of Educational Equipment | Phase 1 | 30308 | 19649.2888 | 30308 | 19649.2888 | Completed | PO + Contract issuance done | 2017-02-02 | Substantial completion / handover done |  |  | 2017-12-31 | Completed | Delivered on XXXX |  | Completed | Educational equipment | 1 | 137 | Italy | 98720 | 32.0654 | 12.6953 | 0.62031 | 0.64832
123 | Goods | West | Kikla | Education | Provision of Educational Equipment | Phase 1 | 82383 | 59775.6587 | 82383 | 59775.6587 | Completed | PO + Contract issuance done | 2016-05-01 | Substantial completion / handover done |  |  | 2017-02-01 | Completed | Delivered on Feb 2017 |  | Completed | Educational equipment | 1 | 117 | Germany(MOFA) | 98720 | 32.0654 | 12.6953 | 0.72884 | 0.72558
124 | Goods | West | Kikla | Education | Provision of Educational Equipment | Phase 1 | 17447.72 | 12380.9721 | 17447.72 | 12380.9721 | Completed | PO + Contract issuance done | 2017-10-02 | Substantial completion / handover done |  |  | 2018-07-31 | Completed | FF on 17 July 2018 |  | Completed | Educational equipment | 1 | 10159 717 | EU C/S ROK | 98720 | 32.0654 | 12.6953 | 0.5479 | 0.7096
125 | Works | West | Kikla | Education | Rehabilitation of University | Phase 1 | 134500 | 75085.0675 | 134500 | 75085.0675 | Completed | PO + Contract issuance done | 2017-03-02 | Substantial completion / handover done | 2017-03-13 | 2017-03-20 | 2017-05-24 | Completed | DLP completed |  | Completed | University | 1 | 10159 | EU | 98720 | 32.058 | 12.6977 | 0.67015 | 0.55825
126 | Works | West | Kikla | Education | Rehabilitation of University | Phase 1 | 20825 | 10835.798 | 20825 | 10835.798 | Completed | PO + Contract issuance done | 2018-03-07 | Substantial completion / handover done | 2018-03-30 | 2018-04-06 | 2018-05-08 | Completed | Completed in 2018 |  | Completed | Other Educational building | 1 | 11410 | UK (FCO) | 98720 | 32.059 | 12.6961 | 0.5088 | 0.52033
127 | Goods | West | Kikla | Education | Provision of Educational Equipment | Phase 1 | 4280 | 2571.5796 | 4280 | 2571.5796 | Completed | PO + Contract issuance done | 2017-02-13 | Substantial completion / handover done |  |  | 2017-02-23 | Completed | Delivered on 2017 |  | Completed | Educational equipment | 1 | 10283 | Germay(KfW) | 98720 | 32.0654 | 12.6953 | 0.6381 | 0.60084
128 | Works | South | Sebha | Education | Rehabilitation of University | Phase 1 | 147800 | 77277.6724 | 147723.41 | 77237.6271 | Completed | PO + Contract issuance done | 2017-11-30 | Substantial completion / handover done | 2017-12-15 | 2017-12-24 | 2018-10-02 | Completed | Handover in first week of October 2018 |  | Completed | Other Educational building | 1 | 95 | Denmark | 98720 | 27.0446 | 14.4386 | 0.67715 | 0.52285
129 | Works | South | Sebha | Education | Rehabilitation of University | Phase 1 | 63613 | 43322.5222 | 69974.3 | 47654.7744 | Completed | PO + Contract issuance done | 2017-07-11 | Substantial completion / handover done | 2017-07-22 | 2017-07-29 | 2018-07-01 | Completed | Completed on 1 July 2018 |  | Completed | University | 1 | 10283 | Germay(KfW) | 98720 | 27.0395 | 14.4434 | 0.69969 | 0.68103
130 | Goods | South | Sebha | WASH | Supply of Sewage Pumps | Phase 1 | 527947.45 | 315980.9816 | 444986.68 | 266328.2642 | Completed | PO + Contract issuance done | 2018-06-21 | Substantial completion / handover done |  |  | 2019-09-14 | Completed | Payment done. Handed over on 14 Sep 2019 | 2019-09-24 | Completed | Water Pump | 35 | 112 12113 10480 141 | France Canada (DFATD) USAID Japan | 98720 112158 | refer to list | refer to list | 0.5925 | 0.59851
131 | Goods | South | Sebha | WASH | Supply of Generators | Phase 1 | 447915.2213 | 274942.4398 | 447915.2213 | 274942.4398 | Completed | PO + Contract issuance done | 2018-06-19 | Substantial completion / handover done |  |  | 2019-09-02 | Completed | Handed over on 2 Sep 2019. | 2019-09-25 | Completed | Generator | 30 | 10159 717 10283 | EU C/S ROK Germay(KfW) | 98720 112158 | refer to list | refer to list | 0.69029 | 0.61383
132 | Works | South | Sebha | WASH | Supply of Generators | Phase 1 | 260636.5 | 169184.8762 | 260636.6 | 169184.9411 | Completed | PO + Contract issuance done | 2019-03-10 | Substantial completion / handover done | 2019-03-20 | 2019-03-30 | 2019-08-10 | Completed | Substantial handover done on 10 aug 2019 | 2019-09-25 | Completed | Public Infrastructure | 1 | 10159 141 | EU Japan | 112158 | refer to list | refer to list | 0.73803 | 0.64912
133 | Goods | South | Sebha | WASH | Supply of Sewage Pumps | Phase 1 | 163494.4368 | 109439.5069 | 163613.2468 | 109519.0356 | Completed | PO + Contract issuance done | 2018-05-23 | Substantial completion / handover done |  |  | 2019-08-27 | Completed | Handed over on 27 August 2019 | 2019-08-28 | Completed | Sewage Pump | 2 | 10159 10283 10480 | EU Germany (KfW) USAID | 98720 112158 | 27.0404 | 14.4295 | 0.57521 | 0.66938
134 | Goods | South | Sebha | WASH | Supply of Sewage Pumps | Phase 1 | 207853.95 | 151431.2888 | 177388.42 | 129235.7304 | Completed | PO + Contract issuance done | 2018-09-24 | Substantial completion / handover done |  |  | 2019-08-28 | Completed | Handed over on 28 Aug 2019. 10 control panels were handed over to General Company of Water and Wastewater (GCWW) on 28 Dec 2020. | 2021-02-01 | Completed | Sewage Pump | 10 | 10480 137 141 11410 | USAID Italy Japan UK (FCO) | 98720 112158 | 27.0423 | 14.4394 | 0.64375 | 0.72855
135 | Works | South | Sebha | Education | Rehabilitation of School | Phase 1 | 304593.9 | 224243.4156 |  | 0 | Completed | Advertisement period ongoing | [5 empty] | With Procurement | Readvertised on 18 July 2022 with deadline on 31 July 2022. On 12 July 2022, BOQ was confirmed by Ali and readvertisement request officially submitted to PU with all required documents. On 20 June 2022, After a meeting with Engineering and Procurement unit, an email was shared with Procurement Unit to request readvertisement of this case. BoQ to be revised by Ali and share with PU. Under evaluation. Advertised on 6 Jan 2022 with deadline on 21 Jan 2022. Request submitted through PROMPT on 23 December 2021. | 2022-07-18 | With Procurement | School | 6 | 187 | Norway | 112158 | 27.0266333333333 27.0360833333333 27.0334138888889 27.0401583333333 27.0456 27.0222 | 14.4330194444444 14.411175 14.4601861111111 14.4233194444444 14.4361944444444 14.4569416666667 | 0.53388 | 0.7362
136 | Goods | South | Sebha | Education | Provision of Educational Equipment | Phase 1 |  | 0 |  | 0 | To be initiated | [6 empty] | Cancelled | Pending Sebha reset/ cancelled as these were included in deepening school projects | 2020-02-05 | Cancelled | [7 empty] | 0.69171 | 0.71294
137 | Goods | South | Sebha | Education | Provision of Educational Equipment | Phase 1 |  | 0 |  | 0 | To be initiated | [6 empty] | Cancelled | Pending Sebha reset/ cancelled as these were included in deepening school projects | 2020-02-05 | Cancelled | [7 empty] | 0.64807 | 0.64113
138 | Goods | South | Sebha | Health | Supply of Freezers | Phase 1 | 71800 | 37105.7613 | 71300 | 36847.3646 | Completed | PO + Contract issuance done | 2018-02-22 | Substantial completion / handover done |  |  | 2018-12-31 | Completed | only enough budget for one 9-body freezer |  | Completed | Freezers | 1 | 10159 | EU | 98720 | 27.0262 | 14.4383 | 0.5054 | 0.51679
139 | Works | South | Sebha | Health | Rehabilitation of Clinic | Phase 1 | 32212 | 23418.2493 | 32135 | 23362.27 | Completed | PO + Contract issuance done | 2017-12-03 | Substantial completion / handover done | 2017-12-15 | 2017-12-23 | 2018-02-01 | Completed | Completed in 2018 |  | Completed | Hospital | 1 | 10283 | Germay(KfW) | 98720 | 27.0249 | 14.4398 | 0.7264 | 0.727
140 | Goods | South | Sebha | Health | Supply of Medical Waste incinerator | Phase 1 |  | 0 |  | 0 | [7 empty] | Cancelled | The neighbourhood eventually refused the incinerator because it would produce an awful smell | 2019-04-19 | Cancelled | [7 empty] | 0.70452 | 0.55553
141 | Works | South | Ubari | Education | Rehabilitation of School | Phase 1 | 717720 | 383091.5783 | 716131.7 | 382243.8043 | Completed | PO + Contract issuance done | 2017-04-20 | Substantial completion / handover done | 2017-05-03 | 2017-05-10 | 2017-11-07 | Completed | DLP completed 24 March 2019 | 2019-04-16 | Completed | School | 1 | 10159 | EU | 98720 | 26.5947 | 12.78 | 0.50428 | 0.53376
142 | Works | South | Ubari | Education | Rehabilitation of School | Phase 1 | 454863 | 305252.9461 | 453501.19 | 304339.0522 | Completed | PO + Contract issuance done | 2017-04-21 | Substantial completion / handover done | 2017-07-16 | 2017-07-23 | 2017-12-31 | Completed | Completed in 2017 |  | Completed | School | 1 | 10283 | Germay(KfW) | 98720 | 26.5939 | 12.7797 | 0.68348 | 0.67109
143 | Works | South | Ubari | Education | Rehabilitation of School | Phase 1 | 220600 | 111125.5113 | 220468.68 | 111059.3598 | Completed | PO + Contract issuance done | 2017-03-13 | Substantial completion / handover done | 2017-05-02 | 2017-05-09 | 2017-09-06 | Completed | DLP completed Nov end 2018 |  | Completed | School | 1 | 10283 10480 | KfW USAID | 98720 | 26.5896 | 12.7711 | 0.55574 | 0.50374
144 | Works | South | Ubari | Education | Rehabilitation of School | Phase 1 | 515588.47 | 311395.5068 | 515539.43 | 311365.8885 | Completed | PO + Contract issuance done | 2017-07-07 | Substantial completion / handover done | 2017-07-27 | 2017-08-03 | 2017-12-01 | Completed | Completed in 2017 |  | Completed | School | 1 | 10283 | Germay(KfW) | 98720 | 26.5897 | 12.7695 | 0.73731 | 0.60396
145 | Works | South | Ubari | Health | Rehabilitation of Hospital | Phase 1 | 360401 | 266921.715 | 360401 | 266921.715 | Completed | PO + Contract issuance done | 2017-03-01 | Substantial completion / handover done | 2017-03-12 | 2017-03-19 | 2017-07-17 | Completed | Completed in 2017 |  | Completed | Hospital | 1 | 141 | Japan | 98720 | 26.5928 | 12.7629 | 0.61848 | 0.74062
146 | Goods | South | Ubari | Health | Suppy of Medical Equipment | Phase 1 | 88896.9318 | 55914.056 | 87282.15 | 54898.3966 | Completed | PO + Contract issuance done | 2018-11-07 | Substantial completion / handover done |  |  | 2019-08-22 | Completed | Transported from Tipoli to Ubari on 16 August 2019. Delivered on 22 Aug 2019 | 2019-08-23 | Completed | Medical Equipment | 1 | 141 95 | Japan Denmark | 98720 | 26.5928 | 12.7629 | 0.67785 | 0.62898
147 | Goods | South | Ubari | Health | Supply of Ambulances | Phase 1 | 95456.902 | 62002.5741 | 106394.21 | 69106.7357 | Completed | PO + Contract issuance done | 2016-02-01 | Substantial completion / handover done |  |  | 2017-12-31 | Completed | Delivered in 2017 |  | Completed | Ambulance | 2 | 717 | C/S ROK | 98720 | 26.5928 | 12.7629 | 0.56673 | 0.64953
148 | Goods | South | Ubari | Health | Supply of Generators | Phase 1 | 105487.5454 | 78445.163 | 105755.7954 | 78644.6454 | Completed | PO + Contract issuance done | 2016-02-01 | Substantial completion / handover done |  |  | 2017-12-31 | Completed | Delivered in 2017 |  | Completed | Generator | 2 | 117 137 141 | Germany(MOFA) Italy Japan | 98720 | 26.5904472222222 26.5858 | 12.8199638888889 12.7998694444444 | 0.66734 | 0.74364
149 | Goods | South | Ubari | Solid Waste Management | Supply of Garbage Trucks | Phase 1 | 123881.44 | 89838.3883 | 123737.78 | 89734.2066 | Completed | PO + Contract issuance done | 2017-05-01 | Substantial completion / handover done |  |  | 2019-02-28 | Completed | Delivered in Feb 2019 |  | Completed | Garbage truck | 1 | 117 141 | Germany(MOFA) Japan | 98720 | 26.5878 | 12.7739 | 0.67844 | 0.7252
150 | Works | South | Ubari | Public Infrastructure and Services | Rehabilitation of Public Building | Phase 1 | 96781 | 49698.3253 | 96781 | 49698.3253 | Completed | PO + Contract issuance done | 2017-03-08 | Substantial completion / handover done | 2017-03-13 | 2017-03-20 | 2017-07-18 | Completed | Completed in 2017 |  | Completed | Public Infrastructure | 1 | 10159 | EU | 98720 | 26.591 | 12.7665 | 0.60969 | 0.51351
151 | Goods | South | Ubari | Public Infrastructure and Services | Supply of IT Equipment | Phase 1 | 7275 | 4604.3633 | 7275 | 4604.3633 | Completed | PO + Contract issuance done | 2018-07-19 | Substantial completion / handover done |  |  | 2018-12-31 | Completed | Completed in 2018 |  | Completed | IT equipment | 1 | 141 | Japan | 98720 | 26.591 | 12.7665 | 0.55922 | 0.6329
152 | Goods | South | Ubari | Public Infrastructure and Services | Supply of Furniture | Phase 1 | 5035.75 | 3547.5029 | 5035.75 | 3547.5029 | Completed | PO + Contract issuance done | 2018-07-19 | Substantial completion / handover done |  |  | 2018-12-31 | Completed | Completed in 2018 |  | Completed | Other public equipment | 1 | 141 | Japan | 98720 | 26.591 | 12.7665 | 0.72229 | 0.70446
153 | Works | South | Ubari | Health | Rehabilitation of Hospital | Phase 1 | 19850 | 12065.774 | 19842 | 12060.9112 | Completed | PO + Contract issuance done | 2018-05-04 | Substantial completion / handover done |  |  | 2018-07-01 | Completed | Completed in 2018 |  | Completed | Other health building | 1 | 11410 | UK (FCO) | 98720 | 26.5904 | 12.82 | 0.59738 | 0.60785
154 | Works | South | Ubari | Health | Rehabilitation of Clinic | Phase 1 | 39400 | 24459.7206 | 39230.8 | 24354.6804 | Completed | PO + Contract issuance done | 2018-05-04 | Substantial completion / handover done |  |  | 2018-08-14 | Completed | Completed in 2018 |  | Completed | Other health building | 1 | 10480 | USAID | 98720 | 26.5858 | 12.7999 | 0.61058 | 0.62081
155 | Works | South | Ubari | Public Infrastructure and Services | Rehabilitation of Public Market | Phase 1 | 510620.09 | 314647.9422 | 510620.09 | 314647.9422 | Completed | PO + Contract issuance done | 2017-07-17 | Substantial completion / handover done | 2017-08-03 | 2017-08-10 | 2018-05-01 | Completed | Completed in 2018 |  | Completed | Public Infrastructure | 1 | 10283 | Germay(KfW) | 98720 | 26.5881 | 12.7777 | 0.71463 | 0.61621
156 | Goods | South | Ubari | WASH | Supply of Pesticide Sprayer Trucks | Phase 1 | 41380 | 30860.8006 | 38440 | 28668.1772 | Completed | PO + Contract issuance done | 2017-05-04 | Substantial completion / handover done |  |  | 2017-12-31 | Completed | Delivered in 2017 |  | Completed | Pesticide Sprayer | 1 | 10159 | EU | 98720 | 26.5878 | 12.7739 | 0.5155 | 0.74579
157 | Works | West | Tripoli | Health | Rehabilitation of Hospital | Phase 1 | 450605 | 324059.8005 | 450288.827 | 323832.4196 | Completed | PO + Contract issuance done | 2018-03-06 | Substantial completion / handover done | 2018-03-18 | 2019-07-01 | 2020-02-20 | Completed | Handed over on 20 Feb 2020. Works completed on 10 Dec 2019. | 2020-02-20 | Completed | Hospital | 1 | 11410 137 | UK (FCO) Italy | 98720 | 32.8804 | 13.1901 | 0.65275 | 0.71917
158 | Works | West | Tripoli | Health | Rehabilitation of Hospital | Phase 1 | 185699 | 100109.5081 | 185698.9 | 100109.4542 | Completed | PO + Contract issuance done | 2019-08-19 | Substantial completion / handover done | 2020-06-17 |  | 2021-01-27 | Completed | Works completed and handed over on 27 Jan 2021. | 2021-02-01 | Completed | Hospital | 1 | 10283 | Germay(KfW) | 112158 | 32.5583 | 13.1782 | 0.55057 | 0.5391
159 | Works | West | Tripoli | Health | Rehabilitation of Hospital | Phase 1 | 146172 | 78479.379 | 146165 | 78475.6207 | Completed | PO + Contract issuance done | 2019-06-18 | Substantial completion / handover done | 2019-07-24 |  | 2020-02-20 | Completed | Handed over on 20 Feb 2020 | 2020-02-20 | Completed | Hospital | 1 | 10159 | EU | 112158 | 32.8843 | 13.1629 | 0.64973 | 0.5369
160 | Works | West | Tripoli | Health | Rehabilitation of Hospital | Phase 1 | 225665 | 163688.9806 | 202969.89 | 147226.7936 | Completed | PO + Contract issuance done | 2020-09-09 | Substantial completion / handover done | 2020-10-01 | 2020-10-29 | 2021-06-09 | Completed | Handed over on 9 June 2021. Actual works completed on 27 Feb 2021 as recorded. Site handedover to contractor on 1 Oct 2020. Contract issued on 9 September 2020. | 2021-06-10 | Completed | Hospital | 1 | 10283 182 | Germay(KfW) Netherlands | 112158 | 32.8771 | 13.3963 | 0.57106 | 0.72536
161 | Works | West | Tripoli | Health | Rehabilitation of Hospital | Phase 1 | 120500 | 65609.0305 | 120478.47 | 65597.308 | Completed | PO + Contract issuance done | 2020-07-28 | Substantial completion / handover done | 2020-08-16 |  | 2021-09-16 | Completed | Completed and handed over on 16 September 2021. Site handed over on 16 August 2020. Contract issued on 28 July 2020. | 2021-09-21 | Completed | Hospital | 1 | 151 | Gov't of Libya | 112158 | 32.8545 | 13.1748 | 0.59968 | 0.54447
162 | Goods | West | Tripoli | WASH | Supply of Sewage Suction Trucks | Phase 1 | 1200933.85 | 828929.3374 | 1136368.22 | 784363.7313 | Completed | PO + Contract issuance done | 2018-10-14 | Substantial completion / handover done |  |  | 2019-07-12 | Completed | Handed over to municipalities of Souq Al Gomma, Tajoura, Abu Salim, Ein Zara and Janzour (12 July 2019) | 2019-06-03 | Completed | Sewage suction truck | 5 | 141 187 | Japan Norway | 98720 112158 |  |  | 0.64942 | 0.69024
163 | Goods | West | Tripoli | WASH | Supply of Sewage Suction Trucks | Phase 1 |  | 0 |  | 0 | [7 empty] | Cancelled | CANCELED by MoP. Email from Ala on 03/12/2018 | 2nd November 2018 | Cancelled | [7 empty] | 0.60975 | 0.52067
164 | Goods | West | Tripoli | WASH | Supply of Sewage Suction Trucks | Phase 1 |  | 0 |  | 0 | [7 empty] | Cancelled | CANCELED by MoP. Email from Ala on 03/12/2018 | 2nd November 2018 | Cancelled | [7 empty] | 0.62027 | 0.55827
165 | Goods | West | Tripoli | Solid Waste Management | Rehabilitation of Dump Yard | Phase 1 |  | 0 |  | 0 | BOQ development stage | [6 empty] | Cancelled | Stopped after municipality intervention/takeover. Pending clarity. | 2019-04-09 | Cancelled | [7 empty] | 0.55805 | 0.62879
| Goods | West | Tripoli | Solid Waste Management | Supply of Garbage Trucks | Phase 1 | 106235.5547 | 65984.2119 | 106328.0887 | 66041.6859 | Completed | PO + Contract issuance done | 2018-12-29 | Substantial completion / handover done |  |  | 2019-09-25 | Completed | Handed over on 25 Sep 2019 | 2019-09-26 | Completed | Garbage truck | 1 | 10159 717 | EU C/S ROK | 98720 |  |  | 0.54192 | 0.62111
167 | Works | West | Tripoli, Janzour | Education | Rehabilitation of School | Phase 1 | 26402 | 19194.8523 | 26402 | 19194.8523 | Completed | PO + Contract issuance done | 2018-07-30 | Substantial completion / handover done | 2018-08-29 | 2018-09-05 | 2018-12-02 | Completed | DLP effective till 2nd June 2019 | contract signed on 30th July | Completed | School | 1 | 187 | Norway | 98720 | 32.8453 | 13.0377 | 0.57341 | 0.72702
168 | Works | West | Tripoli, Janzour | Education | Rehabilitation of School | Phase 1 | 26402 | 18259.2486 | 26402 | 18259.2486 | Completed | PO + Contract issuance done | 2018-07-30 | Substantial completion / handover done | 2018-08-29 | 2018-09-05 | 2018-12-02 | Completed | DLP effective till 2nd June 2019 | contract signed on 30th July | Completed | School | 1 | 187 | Norway | 98720 | 32.7748 | 13.0042 | 0.57923 | 0.69159
169 | Works | West | Tripoli, Janzour | Education | Rehabilitation of School | Phase 1 | 26402 | 19605.3846 | 26402 | 19605.3846 | Completed | PO + Contract issuance done | 2018-07-30 | Substantial completion / handover done | 2018-08-29 | 2018-09-05 | 2018-12-02 | Completed | DLP effective till 2nd June 2019 | contract signed on 30th July | Completed | School | 1 | 187 | Norway | 98720 | 32.8388 | 13.0627 | 0.62626 | 0.74257
170 | Works | West | Tripoli, Janzour | Education | Rehabilitation of School | Phase 1 | 29600 | 19929.6341 | 29599.9767 | 19929.6184 | Completed | PO + Contract issuance done | 2018-05-10 | Substantial completion / handover done | 2018-05-25 | 2018-06-01 | 2018-10-25 | Completed | DLP completed 25th Apr 2019 | 2019-07-25 | Completed | School | 1 | 141 | Japan | 98720 | 32.8264 | 13.0168 | 0.5947 | 0.6733
171 | Works | West | Tripoli, Janzour | Education | Rehabilitation of School | Phase 1 | 29600 | 18698.7159 | 29599.9767 | 18698.7012 | Completed | PO + Contract issuance done | 2018-05-10 | Substantial completion / handover done | 2018-05-25 | 2018-06-01 | 2018-10-25 | Completed | DLP completed 25th Apr 2019 | 2019-07-25 | Completed | School | 1 | 141 | Japan | 98720 | 32.7918 | 12.9982 | 0.64309 | 0.63171
172 | Works | West | Tripoli, Janzour | Education | Rehabilitation of School | Phase 1 | 29600 | 20789.0693 | 29599.9767 | 20789.053 | Completed | PO + Contract issuance done | 2018-05-10 | Substantial completion / handover done | 2018-05-25 | 2018-06-01 | 2018-10-25 | Completed | DLP completed 25th Apr 2019 | 2019-07-25 | Completed | School | 1 | 141 | Japan | 98720 | 32.8268 | 12.9846 | 0.72346 | 0.70233
173 | Goods | West | Tripoli, Janzour | Health | Suppy of Medical Equipment | Phase 1 | 26010.0531 | 17209.1561 | 21603.6606 | 14293.7335 | Completed | PO + Contract issuance done | 2019-01-29 | Substantial completion / handover done |  |  | 2020-11-05 | Completed | Handover documents signed on 5 Nov 2020. Transfer of title lists equipment under Lot A & D delivered. Sensitive reagents (Lot B & C) not included. | 2020-11-11 | Completed | Medical Equipment | 1 | 187 12113 117 10480 | Norway Canada (DFATD) Germany (MOFA) USAID | 98720 112158 | 32.8107 | 13.0016 | 0.69366 | 0.66163
174 | Goods | West | Tripoli, Janzour | Health | Suppy of Medical Equipment | Phase 1 | 26010.0531 | 19313.3136 | 21603.6606 | 16041.4233 | Completed | PO + Contract issuance done | 2019-01-29 | Substantial completion / handover done |  |  | 2020-11-05 | Completed | Handover documents signed on 5 Nov 2020. Transfer of title lists equipment under Lot A & D delivered. Sensitive reagents (Lot B & C) not included. | 2020-11-11 | Completed | Medical Equipment | 1 | 187 12113 117 10480 | Norway Canada (DFATD) Germany (MOFA) USAID | 98720 112158 |  |  | 0.73791 | 0.74253
175 | Goods | West | Tripoli, Janzour | Health | Suppy of Medical Equipment | Phase 1 | 26010.0531 | 16276.3482 | 21603.6606 | 13518.9536 | Completed | PO + Contract issuance done | 2019-01-29 | Substantial completion / handover done |  |  | 2020-11-05 | Completed | Handover documents signed on 5 Nov 2020. Transfer of title lists equipment under Lot A & D delivered. Sensitive reagents (Lot B & C) not included. | 2020-11-11 | Completed | Medical Equipment | 1 | 187 12113 117 10480 | Norway Canada (DFATD) Germany (MOFA) USAID | 98720 112158 | 32.8424 | 13.0414 | 0.67965 | 0.62577
176 | Goods | West | Tripoli, Janzour | Health | Suppy of Medical Equipment | Phase 1 | 26010.0531 | 18454.5123 | 21603.6606 | 15328.1126 | Completed | PO + Contract issuance done | 2019-01-29 | Substantial completion / handover done |  |  | 2020-11-05 | Completed | Handover documents signed on 5 Nov 2020. Transfer of title lists equipment under Lot A & D delivered. Sensitive reagents (Lot B & C) not included. | 2020-11-11 | Completed | Medical Equipment | 1 | 187 12113 117 10480 | Norway Canada (DFATD) Germany (MOFA) USAID | 98720 112158 | 32.8106 | 12.9632 | 0.57016 | 0.70951
177 | Goods | West | Tripoli, Janzour | Health | Suppy of Medical Equipment | Phase 1 | 26010.0531 | 15021.9161 | 21603.6606 | 12477.0363 | Completed | PO + Contract issuance done | 2019-01-29 | Substantial completion / handover done |  |  | 2020-11-05 | Completed | Handover documents signed on 5 Nov 2020. Transfer of title lists equipment under Lot A & D delivered. Sensitive reagents (Lot B & C) not included. | 2020-11-11 | Completed | Medical Equipment | 1 | 187 12113 117 10480 | Norway Canada (DFATD) Germany (MOFA) USAID | 98720 112158 | 32.8335 | 13.0726 | 0.62562 | 0.57754
178 | Works | West | Tripoli, Abu Salim | Education | Rehabilitation of School | Phase 1 | 23467 | 13321.5449 | 21190.5 | 12029.2409 | Completed | PO + Contract issuance done | 2018-11-25 | Substantial completion / handover done | 2018-12-22 | 2018-12-29 | 2020-08-31 | Completed | Handed over on 31 August 2020. | 2020-08-31 | Completed | School | 1 | 187 | Norway | 98720 | 32.8548 | 13.1603 | 0.60812 | 0.56767
179 | Works | West | Tripoli, Abu Salim | Education | Rehabilitation of School | Phase 1 | 39665 | 21726.7418 | 40036.24 | 21930.0907 | Completed | PO + Contract issuance done | 2018-11-25 | Substantial completion / handover done | 2018-12-22 | 2018-12-29 | 2020-08-31 | Completed | Handed over on 31 August 2020. | 2020-08-31 | Completed | School | 1 | 187 | Norway | 98720 | 32.8466 | 13.1789 | 0.51038 | 0.54776
180 | Works | West | Tripoli, Abu Salim | Education | Rehabilitation of School | Phase 1 | 33147 | 18120.514 | 35030.5 | 19150.1694 | Completed | PO + Contract issuance done | 2018-11-25 | Substantial completion / handover done | 2018-12-22 | 2018-12-29 | 2020-08-31 | Completed | Handed over on 31 August 2020. | 2020-08-31 | Completed | School | 1 | 187 | Norway | 98720 | 32.8512 | 13.1838 | 0.63069 | 0.54667
181 | Works | West | Tripoli, Abu Salim | Education | Rehabilitation of School | Phase 1 | 33472 | 20556.3996 | 36280.8 | 22281.3881 | Completed | PO + Contract issuance done | 2018-11-08 | Substantial completion / handover done | 2018-11-15 | 2018-11-22 | 2019-03-15 | Completed | DLP effective till 15 Sep 2019 | 2019-04-18 | Completed | School | 1 | 141 | Japan | 98720 | 32.7943 | 13.1642 | 0.53463 | 0.61414
182 | Works | West | Tripoli, Abu Salim | Education | Rehabilitation of School | Phase 1 | 24152 | 12997.8016 | 19397.84 | 10439.2711 | Completed | PO + Contract issuance done | 2018-11-08 | Substantial completion / handover done | 2018-11-15 | 2018-11-22 | 2019-03-15 | Completed | DLP effective till 15 Sep 2020 | 2019-04-18 | Completed | School | 1 | 141 | Japan | 98720 | 32.8537 | 13.178 | 0.53429 | 0.53817
183 | Works | West | Tripoli, Abu Salim | Education | Rehabilitation of School | Phase 1 | 22747 | 12020.8707 | 24671.89 | 13038.0973 | Completed | PO + Contract issuance done | 2018-11-08 | Substantial completion / handover done | 2018-11-15 | 2018-11-22 | 2019-03-15 | Completed | DLP effective till 15 Sep 2021 | 2019-04-18 | Completed | School | 1 | 141 | Japan | 98720 | 32.7937 | 13.1425 | 0.66143 | 0.52846
184 | Goods | West | Tripoli, Abu Salim | Health | Suppy of Medical Equipment | Phase 1 | 26010.0531 | 13913.8822 | 21603.6606 | 11556.7157 | Completed | PO + Contract issuance done | 2019-01-29 | Substantial completion / handover done |  |  | 2020-11-05 | Completed | Handover documents signed on 5 Nov 2020. Transfer of title lists equipment under Lot A & D delivered. Sensitive reagents (Lot B & C) not included. | 2020-11-11 | Completed | Medical Equipment | 1 | 187 12113 117 10480 | Norway Canada (DFATD) Germany (MOFA) USAID | 98720 112158 |  |  | 0.5833 | 0.53494
185 | Goods | West | Tripoli, Abu Salim | Health | Suppy of Medical Equipment | Phase 1 | 26010.0531 | 17742.8509 | 21603.6606 | 14737.0145 | Completed | PO + Contract issuance done | 2019-01-29 | Substantial completion / handover done |  |  | 2020-11-05 | Completed | Handover documents signed on 5 Nov 2020. Transfer of title lists equipment under Lot A & D delivered. Sensitive reagents (Lot B & C) not included. | 2020-11-11 | Completed | Medical Equipment | 1 | 187 12113 117 10480 | Norway Canada (DFATD) Germany (MOFA) USAID | 98720 112158 |  |  | 0.67614 | 0.68215
186 | Goods | West | Tripoli, Abu Salim | Health | Suppy of Medical Equipment | Phase 1 | 26010.0531 | 18438.4903 | 21603.6606 | 15314.8048 | Completed | PO + Contract issuance done | 2019-01-29 | Substantial completion / handover done |  |  | 2020-11-05 | Completed | Handover documents signed on 5 Nov 2020. Transfer of title lists equipment under Lot A & D delivered. Sensitive reagents (Lot B & C) not included. | 2020-11-11 | Completed | Medical Equipment | 1 | 187 12113 117 10480 | Norway Canada (DFATD) Germany (MOFA) USAID | 98720 112158 |  |  | 0.52421 | 0.7089
187 | Goods | West | Tripoli, Abu Salim | Health | Suppy of Medical Equipment | Phase 1 | 26010.0531 | 15044.1656 | 21603.6606 | 12495.5165 | Completed | PO + Contract issuance done | 2019-01-29 | Substantial completion / handover done |  |  | 2020-11-05 | Completed | Handover documents signed on 5 Nov 2020. Transfer of title lists equipment under Lot A & D delivered. Sensitive reagents (Lot B & C) not included. | 2020-11-11 | Completed | Medical Equipment | 1 | 187 12113 117 10480 | Norway Canada (DFATD) Germany (MOFA) USAID | 98720 112158 |  |  | 0.60175 | 0.5784
188 | Goods | West | Tripoli, Abu Salim | Health | Suppy of Medical Equipment | Phase 1 | 26010.0531 | 16385.5998 | 21603.6606 | 13609.6969 | Completed | PO + Contract issuance done | 2019-01-29 | Substantial completion / handover done |  |  | 2020-11-05 | Completed | Handover documents signed on 5 Nov 2020. Transfer of title lists equipment under Lot A & D delivered. Sensitive reagents (Lot B & C) not included. | 2020-11-11 | Completed | Medical Equipment | 1 | 187 12113 117 10480 | Norway Canada (DFATD) Germany (MOFA) USAID | 98720 112158 |  |  | 0.55978 | 0.62997
189 | Works | West | Tripoli, Al-Swani | Education | Rehabilitation of School | Phase 1 | 14360 | 10393.9362 | 13360 | 9670.1245 | Completed | PO + Contract issuance done | 2018-11-13 | Substantial completion / handover done | 2018-12-08 | 2018-12-15 | 2019-06-19 | Completed |  | 2019-04-29 | Completed | School | 1 | 137 | Italy | 98720 | 32.7063 | 12.9326 | 0.51408 | 0.72381
190 | Works | West | Tripoli, Al-Swani | Education | Rehabilitation of School | Phase 1 | 17091 | 11390.6868 | 17078.55 | 11382.3892 | Completed | PO + Contract issuance done | 2018-11-13 | Substantial completion / handover done | 2018-12-08 | 2018-12-15 | 2019-06-19 | Completed |  | 2019-04-29 | Completed | School | 1 | 137 | Italy | 98720 | 32.7631 | 13.0927 | 0.6718 | 0.66647
191 | Works | West | Tripoli, Al-Swani | Education | Rehabilitation of School | Phase 1 | 32208.5 | 22372.5643 | 32056 | 22266.6352 | Completed | PO + Contract issuance done | 2018-11-13 | Substantial completion / handover done | 2018-12-08 | 2018-12-15 | 2019-06-19 | Completed |  | 2019-05-21 | Completed | School | 1 | 137 | Italy | 98720 | 32.645 | 13.0211 | 0.54184 | 0.69462
192 | Works | West | Tripoli, Al-Swani | Education | Rehabilitation of School | Phase 1 | 34740 | 23789.2299 | 34740 | 23789.2299 | Completed | PO + Contract issuance done | 2018-10-26 | Substantial completion / handover done | 2018-11-25 | 2018-12-02 | 2019-05-21 | Completed |  | 2019-05-21 | Completed | School | 1 | 141 | Japan | 98720 | 32.7132 | 13.0671 | 0.72311 | 0.68478
193 | Works | West | Tripoli, Al-Swani | Education | Rehabilitation of School | Phase 1 | 44169.14 | 31429.847 | 44169.17 | 31429.8683 | Completed | PO + Contract issuance done | 2018-10-26 | Substantial completion / handover done | 2018-11-25 | 2018-12-02 | 2019-05-21 | Completed |  | 2019-05-21 | Completed | School | 1 | 141 | Japan | 98720 | 32.6883 | 13.0584 | 0.62407 | 0.71158
194 | Works | West | Tripoli, Al-Swani | Education | Rehabilitation of School | Phase 1 | 20547.87 | 11533.9807 | 20547.87 | 11533.9807 | Completed | PO + Contract issuance done | 2018-10-26 | Substantial completion / handover done | 2018-11-25 | 2018-12-02 | 2019-05-21 | Completed |  | 2019-05-21 | Completed | School | 1 | 141 | Japan | 98720 | 32.6382 | 13.0653 | 0.55617 | 0.56132
195 | Goods | West | Tripoli, Al-Swani | Health | Suppy of Medical Equipment | Phase 1 | 26010.0531 | 16185.2753 | 21603.6606 | 13443.3095 | Completed | PO + Contract issuance done | 2019-01-29 | Substantial completion / handover done |  |  | 2020-11-05 | Completed | Handover documents signed on 5 Nov 2020. Transfer of title lists equipment under Lot A & D delivered. Sensitive reagents (Lot B & C) not included. | 2020-11-11 | Completed | Medical Equipment | 1 | 187 12113 117 10480 | Norway Canada (DFATD) Germany (MOFA) USAID | 98720 112158 |  |  | 0.68136 | 0.62227
196 | Goods | West | Tripoli, Al-Swani | Health | Suppy of Medical Equipment | Phase 1 | 26010.0531 | 13781.797 | 21603.6606 | 11447.0072 | Completed | PO + Contract issuance done | 2019-01-29 | Substantial completion / handover done |  |  | 2020-11-05 | Completed | Handover documents signed on 5 Nov 2020. Transfer of title lists equipment under Lot A & D delivered. Sensitive reagents (Lot B & C) not included. | 2020-11-11 | Completed | Medical Equipment | 1 | 187 12113 117 10480 | Norway Canada (DFATD) Germany (MOFA) USAID | 98720 112158 |  |  | 0.59528 | 0.52986
197 | Goods | West | Tripoli, Al-Swani | Health | Suppy of Medical Equipment | Phase 1 | 26010.0531 | 14030.0043 | 21603.6606 | 11653.1654 | Completed | PO + Contract issuance done | 2019-01-29 | Substantial completion / handover done |  |  | 2020-11-05 | Completed | Handover documents signed on 5 Nov 2020. Transfer of title lists equipment under Lot A & D delivered. Sensitive reagents (Lot B & C) not included. | 2020-11-11 | Completed | Medical Equipment | 1 | 187 12113 117 10480 | Norway Canada (DFATD) Germany (MOFA) USAID | 98720 112158 |  |  | 0.57989 | 0.53941
198 | Goods | West | Tripoli, Al-Swani | Health | Suppy of Medical Equipment | Phase 1 | 26010.0531 | 17552.4881 | 21603.6606 | 14578.9013 | Completed | PO + Contract issuance done | 2019-01-29 | Substantial completion / handover done |  |  | 2020-11-05 | Completed | Handover documents signed on 5 Nov 2020. Transfer of title lists equipment under Lot A & D delivered. Sensitive reagents (Lot B & C) not included. | 2020-11-11 | Completed | Medical Equipment | 1 | 187 12113 117 10480 | Norway Canada (DFATD) Germany (MOFA) USAID | 98720 112158 |  |  | 0.61231 | 0.67483
199 | Goods | West | Tripoli, Al-Swani | Health | Suppy of Medical Equipment | Phase 1 | 26010.0531 | 19267.1612 | 21603.6606 | 16003.0896 | Completed | PO + Contract issuance done | 2019-01-29 | Substantial completion / handover done |  |  | 2020-11-05 | Completed | Handover documents signed on 5 Nov 2020. Transfer of title lists equipment under Lot A & D delivered. Sensitive reagents (Lot B & C) not included. | 2020-11-11 | Completed | Medical Equipment | 1 | 187 12113 117 10480 | Norway Canada (DFATD) Germany (MOFA) USAID | 98720 112158 |  |  | 0.60894 | 0.74076
200 | Works | West | Tripoli, Sidi Al-Sayah | Education | Rehabilitation of School | Phase 1 | 32095 | 19369.1527 | 28988.442 | 17494.3623 | Completed | PO + Contract issuance done | 2018-11-10 | Substantial completion / handover done | 2018-12-10 | 2018-12-17 | 2019-09-04 | Completed | Damaged due to recent conflict. Completion certificate signed as per existing BoQ and SoW on 11 Aug 2020. Handed over on 4 Sep 2019. Handover docs received on 15 April 2020. Therefore, not reflected in 2019 Annual report. | 2020-08-13 | Completed | School | 1 | 141 137 | Japan Italy | 98720 112158 | 32.574 | 13.279 | 0.62533 | 0.60349
201 | Works | West | Tripoli, Sidi Al-Sayah | Education | Rehabilitation of School | Phase 1 | 34205 | 20778.1929 | 27027.36 | 16418.0588 | Completed | PO + Contract issuance done | 2018-11-10 | Substantial completion / handover done | 2018-12-10 | 2018-12-17 | 2019-09-04 | Completed | Damaged due to recent conflict. Completion certificate signed as per existing BoQ and SoW on 11 Aug 2020. Handed over on 4 Sep 2019. Handover docs received on 15 April 2020. Therefore, not reflected in 2019 Annual report. | 2020-08-13 | Completed | School | 1 | 141 137 | Japan Italy | 98720 112158 | 32.607 | 13.241 | 0.70428 | 0.60746
202 | Works | West | Tripoli, Sidi Al-Sayah | Education | Rehabilitation of School | Phase 1 | 37565 | 21503.2046 | 46438.662 | 26582.7247 | Completed | PO + Contract issuance done | 2018-11-10 | Substantial completion / handover done | 2018-12-10 | 2018-12-17 | 2019-09-04 | Completed | Damaged due to recent conflict. Completion certificate signed as per existing BoQ and SoW on 11 Aug 2020. Handed over on 4 Sep 2019. Handover docs received on 15 April 2020. Therefore, not reflected in 2019 Annual report. | 2020-08-13 | Completed | School | 1 | 141 137 | Japan Italy | 98720 112158 | 32.591 | 13.223 | 0.67749 | 0.57243
203 | Works | West | Tripoli, Sidi Al-Sayah | Education | Rehabilitation of School | Phase 1 | 22942 | 14244.1067 | 24906.15 | 15463.5977 | Completed | PO + Contract issuance done | 2018-11-22 | Substantial completion / handover done | 2018-12-09 | 2018-12-16 | 2020-01-05 | Completed | handed over on 5 jan 2020 | 2020-02-20 | Completed | School | 1 | 10159 | EU | 112158 | 32.666 | 13.292 | 0.74165 | 0.62087
204 | Works | West | Tripoli, Sidi Al-Sayah | Education | Rehabilitation of School | Phase 1 | 23155.1 | 16630.0093 | 21469.9 | 15419.6975 | Completed | PO + Contract issuance done | 2018-11-22 | Substantial completion / handover done | 2018-12-09 | 2018-12-16 | 2020-01-05 | Completed | handed over on 5 jan 2020 | 2020-02-20 | Completed | School | 1 | 10159 | EU | 112158 | 32.616 | 13.277 | 0.5351 | 0.7182
205 | Works | West | Tripoli, Sidi Al-Sayah | Education | Rehabilitation of School | Phase 1 | 20169 | 12006.3641 | 19864 | 11824.8013 | Completed | PO + Contract issuance done | 2018-11-22 | Substantial completion / handover done | 2018-12-09 | 2018-12-16 | 2020-01-05 | Completed | handed over on 5 jan 2020 | 2020-02-20 | Completed | School | 1 | 10159 | EU | 112158 | 32.529 | 13.257 | 0.68601 | 0.59529
206 | Goods | West | Tripoli, Sidi Al-Sayah | Health | Suppy of Medical Equipment | Phase 1 | 26010.0531 | 14985.9967 | 21603.6606 | 12447.2021 | Completed | PO + Contract issuance done | 2019-01-29 | Substantial completion / handover done |  |  | 2020-11-05 | Completed | Handover documents signed on 5 Nov 2020. Transfer of title lists equipment under Lot A & D delivered. Sensitive reagents (Lot B & C) not included. | 2020-11-11 | Completed | Medical Equipment | 1 | 187 12113 117 10480 | Norway Canada (DFATD) Germany (MOFA) USAID | 98720 112158 |  |  | 0.68901 | 0.57616
207 | Goods | West | Tripoli, Sidi Al-Sayah | Health | Suppy of Medical Equipment | Phase 1 | 26010.0531 | 13926.1055 | 21603.6606 | 11566.8682 | Completed | PO + Contract issuance done | 2019-01-29 | Substantial completion / handover done |  |  | 2020-11-05 | Completed | Handover documents signed on 5 Nov 2020. Transfer of title lists equipment under Lot A & D delivered. Sensitive reagents (Lot B & C) not included. | 2020-11-11 | Completed | Medical Equipment | 1 | 187 12113 117 10480 | Norway Canada (DFATD) Germany (MOFA) USAID | 98720 112158 |  |  | 0.67456 | 0.53541
208 | Goods | West | Tripoli, Sidi Al-Sayah | Health | Suppy of Medical Equipment | Phase 1 | 26010.0531 | 18086.0067 | 21603.6606 | 15022.0359 | Completed | PO + Contract issuance done | 2019-01-29 | Substantial completion / handover done |  |  | 2020-11-05 | Completed | Handover documents signed on 5 Nov 2020. Transfer of title lists equipment under Lot A & D delivered. Sensitive reagents (Lot B & C) not included. | 2020-11-11 | Completed | Medical Equipment | 1 | 187 12113 117 10480 | Norway Canada (DFATD) Germany (MOFA) USAID | 98720 112158 |  |  | 0.62259 | 0.69535
209 | Goods | West | Tripoli, Sidi Al-Sayah | Health | Suppy of Medical Equipment | Phase 1 | 26010.0531 | 17446.406 | 21603.6606 | 14490.7907 | Completed | PO + Contract issuance done | 2019-01-29 | Substantial completion / handover done |  |  | 2020-11-05 | Completed | Handover documents signed on 5 Nov 2020. Transfer of title lists equipment under Lot A & D delivered. Sensitive reagents (Lot B & C) not included. | 2020-11-11 | Completed | Medical Equipment | 1 | 187 12113 117 10480 | Norway Canada (DFATD) Germany (MOFA) USAID | 98720 112158 |  |  | 0.74281 | 0.67076
210 | Goods | West | Tripoli, Sidi Al-Sayah | Health | Suppy of Medical Equipment | Phase 1 | 26010.0531 | 16642.2566 | 21603.6606 | 13822.8731 | Completed | PO + Contract issuance done | 2019-01-29 | Substantial completion / handover done |  |  | 2020-11-05 | Completed | Handover documents signed on 5 Nov 2020. Transfer of title lists equipment under Lot A & D delivered. Sensitive reagents (Lot B & C) not included. | 2020-11-11 | Completed | Medical Equipment | 1 | 187 12113 117 10480 | Norway Canada (DFATD) Germany (MOFA) USAID | 98720 112158 |  |  | 0.60251 | 0.63984
211 | Works | West | Tripoli, Al-Garabouli | Education | Rehabilitation of School | Phase 1 | 19680 | 10951.4523 | 22245 | 12378.8139 | Completed | PO + Contract issuance done | 2019-06-19 | Substantial completion / handover done | 2019-07-17 |  | 2019-11-19 | Completed | Handed over on 19 Nov 2019 | 2020-02-20 | Completed | School | 1 | 10159 | EU | 112158 | 32.7426 | 13.7487 | 0.53263 | 0.55648
212 | Works | West | Tripoli, Al-Garabouli | Education | Rehabilitation of School | Phase 1 | 37741 | 27737.2207 | 36660.5 | 26943.1223 | Completed | PO + Contract issuance done | 2019-06-19 | Substantial completion / handover done | 2019-07-17 |  | 2019-11-19 | Completed | Handed over on 19 Nov 2019 | 2020-02-20 | Completed | School | 1 | 10159 | EU | 112158 | 32.3836 | 13.4458 | 0.55944 | 0.73494
213 | Works | West | Tripoli, Al-Garabouli | Education | Rehabilitation of School | Phase 1 | 25483 | 14832.2871 | 23850.46 | 13882.0731 | Completed | PO + Contract issuance done | 2019-06-19 | Substantial completion / handover done | 2019-07-17 |  | 2019-11-19 | Completed | Handed over on 19 Nov 2019 | 2020-02-20 | Completed | School | 1 | 10159 | EU | 112158 | 32.3928 | 13.3528 | 0.5358 | 0.58205
214 | Works | West | Tripoli, Al-Garabouli | Education | Rehabilitation of School | Phase 1 | 39353.3333 | 27273.0948 | 117561.5 | 81473.8084 | Completed | PO + Contract issuance done | 2019-06-19 | Substantial completion / handover done | 2019-07-17 | 2019-07-17 | 2019-11-16 | Completed | Completed back in Nov 2019, handover documents signed in July 2020 after completion of Al-Gwea school | 2020-09-29 | Completed | School | 1 | 10159 | EU | 112158 | 32.7335 | 13.7829 | 0.67776 | 0.69303
215 | Works | West | Tripoli, Al-Garabouli | Education | Rehabilitation of School | Phase 1 | 39353.3333 | 23031.0173 |  | 0 | Completed | PO + Contract issuance done | 2019-06-19 | Substantial completion / handover done | 2019-07-17 | 2019-07-17 | 2019-11-16 | Completed | Completed back in Nov 2019, handover documents signed in July 2020 after completion of Al-Gwea school | 2020-09-29 | Completed | School | 1 | 10159 | EU | 112158 | 32.4454 | 13.3905 | 0.63199 | 0.58524
216 | Works | West | Tripoli, Al-Garabouli | Education | Rehabilitation of School | Phase 1 | 39353.3333 | 21870.7068 |  | 0 | Completed | PO + Contract issuance done | 2019-06-19 | Substantial completion / handover done | 2019-07-17 | 2019-07-17 | 2020-07-27 | Completed | Completed on 27 July 2020 | 2020-09-29 | Completed | School | 1 | 10159 | EU | 112158 | 32.7117 | 13.6088 | 0.65821 | 0.55575
217 | Goods | West | Tripoli, Al-Garabouli | Health | Suppy of Medical Equipment | Phase 1 | 26010.0531 | 14269.0552 | 21603.6606 | 11851.7185 | Completed | PO + Contract issuance done | 2019-01-29 | Substantial completion / handover done |  |  | 2020-11-05 | Completed | Handover documents signed on 5 Nov 2020. Transfer of title lists equipment under Lot A & D delivered. Sensitive reagents (Lot B & C) not included. | 2020-11-11 | Completed | Medical Equipment | 1 | 187 12113 117 10480 | Norway Canada (DFATD) Germany (MOFA) USAID | 98720 112158 |  |  | 0.56481 | 0.5486
218 | Goods | West | Tripoli, Al-Garabouli | Health | Suppy of Medical Equipment | Phase 1 | 26010.0531 | 16858.5961 | 21603.6606 | 14002.5623 | Completed | PO + Contract issuance done | 2019-01-29 | Substantial completion / handover done |  |  | 2020-11-05 | Completed | Handover documents signed on 5 Nov 2020. Transfer of title lists equipment under Lot A & D delivered. Sensitive reagents (Lot B & C) not included. | 2020-11-11 | Completed | Medical Equipment | 1 | 187 12113 117 10480 | Norway Canada (DFATD) Germany (MOFA) USAID | 98720 112158 |  |  | 0.66109 | 0.64816
219 | Goods | West | Tripoli, Al-Garabouli | Health | Suppy of Medical Equipment | Phase 1 | 26010.0531 | 17698.281 | 21603.6606 | 14699.9953 | Completed | PO + Contract issuance done | 2019-01-29 | Substantial completion / handover done |  |  | 2020-11-05 | Completed | Handover documents signed on 5 Nov 2020. Transfer of title lists equipment under Lot A & D delivered. Sensitive reagents (Lot B & C) not included. | 2020-11-11 | Completed | Medical Equipment | 1 | 187 12113 117 10480 | Norway Canada (DFATD) Germany (MOFA) USAID | 98720 112158 |  |  | 0.53505 | 0.68044
220 | Goods | West | Tripoli, Al-Garabouli | Health | Suppy of Medical Equipment | Phase 1 | 26010.0531 | 13361.4867 | 21603.6606 | 11097.9022 | Completed | PO + Contract issuance done | 2019-01-29 | Substantial completion / handover done |  |  | 2020-11-05 | Completed | Handover documents signed on 5 Nov 2020. Transfer of title lists equipment under Lot A & D delivered. Sensitive reagents (Lot B & C) not included. | 2020-11-11 | Completed | Medical Equipment | 1 | 187 12113 117 10480 | Norway Canada (DFATD) Germany (MOFA) USAID | 98720 112158 |  |  | 0.66179 | 0.5137
221 | Goods | West | Tripoli, Al-Garabouli | Health | Suppy of Medical Equipment | Phase 1 | 26010.0531 | 16635.4246 | 21603.6606 | 13817.1986 | Completed | PO + Contract issuance done | 2019-01-29 | Substantial completion / handover done |  |  | 2020-11-05 | Completed | Handover documents signed on 5 Nov 2020. Transfer of title lists equipment under Lot A & D delivered. Sensitive reagents (Lot B & C) not included. | 2020-11-11 | Completed | Medical Equipment | 1 | 187 12113 117 10480 | Norway Canada (DFATD) Germany (MOFA) USAID | 98720 112158 |  |  | 0.60036 | 0.63958
222 | Works | West | Tripoli, Central Tripoli | Education | Rehabilitation of School | Phase 1 | 46800 | 31769.302 | 44736.39 | 30368.4591 | Completed | PO + Contract issuance done | 2018-10-08 | Substantial completion / handover done | 2018-11-27 | 2018-12-04 | 2019-02-21 | Completed | DLP effective till 21st Aug 2019 | 2019-04-11 | Completed | School | 1 | 10480 | USAID | 98720 | 32.8923 | 13.2012 | 0.50871 | 0.67883
223 | Works | West | Tripoli, Central Tripoli | Education | Rehabilitation of School | Phase 1 | 19040 | 12824.7659 | 19306 | 13003.9354 | Completed | PO + Contract issuance done | 2018-10-08 | Substantial completion / handover done | 2018-11-27 | 2018-12-04 | 2019-02-21 | Completed | DLP effective till 21st Aug 2019 | 2019-04-11 | Completed | School | 1 | 10480 | USAID | 98720 | 32.8863 | 13.1956 | 0.54917 | 0.67357
224 | Works | West | Tripoli, Central Tripoli | Education | Rehabilitation of School | Phase 1 | 9930 | 6853.6531 | 11718.82 | 8088.2908 | Completed | PO + Contract issuance done | 2018-10-08 | Substantial completion / handover done | 2018-11-27 | 2018-12-04 | 2019-02-21 | Completed | DLP effective till 21st Aug 2019 | 2019-04-11 | Completed | School | 1 | 10480 | USAID | 98720 | 32.8879 | 13.1959 | 0.65044 | 0.6902
225 | Works | West | Tripoli, Central Tripoli | Education | Rehabilitation of School | Phase 1 | 29108 | 15428.8372 | 27996.5 | 14839.6812 | Completed | PO + Contract issuance done | 2018-11-18 | Substantial completion / handover done | 2018-12-14 | 2018-12-21 | 2019-04-15 | Completed | Delayed handover due to conflict | 2019-04-29 | Completed | School | 1 | 10283 | Germay(KfW) | 112158 | 32.8914 | 13.1755 | 0.58599 | 0.53005
226 | Works | West | Tripoli, Central Tripoli | Education | Rehabilitation of School | Phase 1 | 30034 | 19520.6115 | 30026.68 | 19515.8539 | Completed | PO + Contract issuance done | 2018-11-18 | Substantial completion / handover done | 2018-12-14 | 2018-12-21 | 2019-04-15 | Completed | Delayed handover due to conflict | 2019-04-29 | Completed | School | 1 | 137 | Italy | 98720 | 32.8791 | 13.1952 | 0.55175 | 0.64995
227 | Works | West | Tripoli, Central Tripoli | Education | Rehabilitation of School | Phase 1 | 27610 | 16909.3048 | 28128 | 17226.5456 | Completed | PO + Contract issuance done | 2018-11-18 | Substantial completion / handover done | 2018-12-14 | 2018-12-21 | 2019-04-15 | Completed | Delayed handover due to conflict | 2019-04-29 | Completed | School | 1 | 137 | Italy | 98720 | 32.8889 | 13.1859 | 0.62416 | 0.61243
228 | Goods | West | Tripoli, Central Tripoli | Health | Suppy of Medical Equipment | Phase 1 | 26010.0531 | 13469.2018 | 21603.6606 | 11187.3691 | Completed | PO + Contract issuance done | 2019-01-29 | Substantial completion / handover done |  |  | 2020-11-05 | Completed | Handover documents signed on 5 Nov 2020. Transfer of title lists equipment under Lot A & D delivered. Sensitive reagents (Lot B & C) not included. | 2020-11-11 | Completed | Medical Equipment | 1 | 187 12113 117 10480 | Norway Canada (DFATD) Germany (MOFA) USAID | 98720 112158 |  |  | 0.68767 | 0.51785
229 | Goods | West | Tripoli, Central Tripoli | Health | Suppy of Medical Equipment | Phase 1 | 26010.0531 | 18436.1915 | 21603.6606 | 15312.8955 | Completed | PO + Contract issuance done | 2019-01-29 | Substantial completion / handover done |  |  | 2020-11-05 | Completed | Handover documents signed on 5 Nov 2020. Transfer of title lists equipment under Lot A & D delivered. Sensitive reagents (Lot B & C) not included. | 2020-11-11 | Completed | Medical Equipment | 1 | 187 12113 117 10480 | Norway Canada (DFATD) Germany (MOFA) USAID | 98720 112158 |  |  | 0.60562 | 0.70881
230 | Goods | West | Tripoli, Central Tripoli | Health | Suppy of Medical Equipment | Phase 1 | 26010.0531 | 17466.1045 | 21603.6606 | 14507.152 | Completed | PO + Contract issuance done | 2019-01-29 | Substantial completion / handover done |  |  | 2020-11-05 | Completed | Handover documents signed on 5 Nov 2020. Transfer of title lists equipment under Lot A & D delivered. Sensitive reagents (Lot B & C) not included. | 2020-11-11 | Completed | Medical Equipment | 1 | 187 12113 117 10480 | Norway Canada (DFATD) Germany (MOFA) USAID | 98720 112158 |  |  | 0.68635 | 0.67151
231 | Goods | West | Tripoli, Central Tripoli | Health | Suppy of Medical Equipment | Phase 1 | 26010.0531 | 18750.7196 | 21603.6606 | 15574.139 | Completed | PO + Contract issuance done | 2019-01-29 | Substantial completion / handover done |  |  | 2020-11-05 | Completed | Handover documents signed on 5 Nov 2020. Transfer of title lists equipment under Lot A & D delivered. Sensitive reagents (Lot B & C) not included. | 2020-11-11 | Completed | Medical Equipment | 1 | 187 12113 117 10480 | Norway Canada (DFATD) Germany (MOFA) USAID | 98720 112158 |  |  | 0.64875 | 0.7209
232 | Goods | West | Tripoli, Central Tripoli | Health | Suppy of Medical Equipment | Phase 1 | 26010.0531 | 13651.1856 | 21603.6606 | 11338.5229 | Completed | PO + Contract issuance done | 2019-01-29 | Substantial completion / handover done |  |  | 2020-11-05 | Completed | Handover documents signed on 5 Nov 2020. Transfer of title lists equipment under Lot A & D delivered. Sensitive reagents (Lot B & C) not included. | 2020-11-11 | Completed | Medical Equipment | 1 | 187 12113 117 10480 | Norway Canada (DFATD) Germany (MOFA) USAID | 98720 112158 |  |  | 0.50519 | 0.52484
233 | Works | West | Tripoli, Al-Ssabiaa | Education | Rehabilitation of School | Phase 1 | 105423.75 | 75494.0486 | 105158.1 | 75303.8163 | Completed | PO + Contract issuance done | 2019-10-17 | Substantial completion / handover done | 2020-06-17 |  | 2020-10-26 | Completed | Completed and handed over on Oct 2020. Site handed over on 17 June 2020. | 2020-10-28 | Completed | School | 1 | 10159 | EU | 112158 | 32.5708 | 13.1691 | 0.68978 | 0.7161
234 | Works | West | Tripoli, Al-Ssabiaa | Education | Rehabilitation of School | Phase 1 |  | 0 |  | 0 | Completed | PO + Contract issuance done | 2019-10-17 | Substantial completion / handover done | 2020-06-17 |  | 2020-10-26 | Completed | Completed and handed over on Oct 2020. Site handed over on 17 June 2020. | 2020-10-28 | Completed | School | 1 | 10159 | EU | 112158 | 32.3389 | 13.1603 | 0.69587 | 0.51816
235 | Works | West | Tripoli, Al-Ssabiaa | Education | Rehabilitation of School | Phase 1 |  | 0 |  | 0 | Completed | PO + Contract issuance done | 2019-10-17 | Substantial completion / handover done | 2020-06-17 |  | 2020-10-26 | Completed | Completed and handed over on Oct 2020. Site handed over on 17 June 2020. | 2020-10-28 | Completed | School | 1 | 10159 | EU | 112158 | 32.5368 | 13.1734 | 0.50407 | 0.51414
236 | Works | West | Tripoli, Al-Ssabiaa | Education | Rehabilitation of School | Phase 1 | 100124 | 61943.3145 | 100044 | 61893.8213 | Completed | PO + Contract issuance done | 2019-11-03 | Substantial completion / handover done | 2020-06-17 |  | 2020-10-26 | Completed | Completed and handed over on Oct 2020. Site handed over on 17 June 2020. | 2020-10-28 | Completed | School | 1 | 10159 | EU | 112158 | 32.3417 | 13.0838 | 0.56206 | 0.61867
237 | Works | West | Tripoli, Al-Ssabiaa | Education | Rehabilitation of School | Phase 1 |  | 0 |  | 0 | Completed | PO + Contract issuance done | 2019-11-03 | Substantial completion / handover done | 2020-06-17 |  | 2020-10-26 | Completed | Completed and handed over on Oct 2020. Site handed over on 17 June 2020. | 2020-10-28 | Completed | School | 1 | 10159 | EU | 112158 | 32.452 | 13.1584 | 0.62747 | 0.50993
238 | Works | West | Tripoli, Al-Ssabiaa | Education | Rehabilitation of School | Phase 1 |  | 0 |  | 0 | Completed | PO + Contract issuance done | 2019-11-03 | Substantial completion / handover done | 2020-06-17 |  | 2020-10-26 | Completed | Completed and handed over on Oct 2020. Site handed over on 17 June 2020. | 2020-10-28 | Completed | School | 1 | 10159 | EU | 112158 | 32.317 | 13.106 | 0.73035 | 0.69899
239 | Goods | West | Tripoli, Al-Ssabiaa | Health | Suppy of Medical Equipment | Phase 1 | 26010.0531 | 14917.7555 | 21603.6606 | 12390.5217 | Completed | PO + Contract issuance done | 2019-01-29 | Substantial completion / handover done |  |  | 2020-11-05 | Completed | Handover documents signed on 5 Nov 2020. Transfer of title lists equipment under Lot A & D delivered. Sensitive reagents (Lot B & C) not included. | 2020-11-11 | Completed | Medical Equipment | 1 | 187 12113 117 10480 | Norway Canada (DFATD) Germany (MOFA) USAID | 98720 112158 |  |  | 0.70373 | 0.57354
240 | Goods | West | Tripoli, Al-Ssabiaa | Health | Suppy of Medical Equipment | Phase 1 | 26010.0531 | 16156.6243 | 21603.6606 | 13419.5124 | Completed | PO + Contract issuance done | 2019-01-29 | Substantial completion / handover done |  |  | 2020-11-05 | Completed | Handover documents signed on 5 Nov 2020. Transfer of title lists equipment under Lot A & D delivered. Sensitive reagents (Lot B & C) not included. | 2020-11-11 | Completed | Medical Equipment | 1 | 187 12113 117 10480 | Norway Canada (DFATD) Germany (MOFA) USAID | 98720 112158 |  |  | 0.57378 | 0.62117
241 | Goods | West | Tripoli, Al-Ssabiaa | Health | Suppy of Medical Equipment | Phase 1 | 26010.0531 | 17925.2096 | 21603.6606 | 14888.4796 | Completed | PO + Contract issuance done | 2019-01-29 | Substantial completion / handover done |  |  | 2020-11-05 | Completed | Handover documents signed on 5 Nov 2020. Transfer of title lists equipment under Lot A & D delivered. Sensitive reagents (Lot B & C) not included. | 2020-11-11 | Completed | Medical Equipment | 1 | 187 12113 117 10480 | Norway Canada (DFATD) Germany (MOFA) USAID | 98720 112158 |  |  | 0.71099 | 0.68916
242 | Goods | West | Tripoli, Al-Ssabiaa | Health | Suppy of Medical Equipment | Phase 1 | 26010.0531 | 17686.9993 | 21603.6606 | 14690.6248 | Completed | PO + Contract issuance done | 2019-01-29 | Substantial completion / handover done |  |  | 2020-11-05 | Completed | Handover documents signed on 5 Nov 2020. Transfer of title lists equipment under Lot A & D delivered. Sensitive reagents (Lot B & C) not included. | 2020-11-11 | Completed | Medical Equipment | 1 | 187 12113 117 10480 | Norway Canada (DFATD) Germany (MOFA) USAID | 98720 112158 |  |  | 0.73146 | 0.68001
243 | Goods | West | Tripoli, Al-Ssabiaa | Health | Suppy of Medical Equipment | Phase 1 | 26010.0531 | 19300.7007 | 21603.6606 | 16030.9472 | Completed | PO + Contract issuance done | 2019-01-29 | Substantial completion / handover done |  |  | 2020-11-05 | Completed | Handover documents signed on 5 Nov 2020. Transfer of title lists equipment under Lot A & D delivered. Sensitive reagents (Lot B & C) not included. | 2020-11-11 | Completed | Medical Equipment | 1 | 187 12113 117 10480 | Norway Canada (DFATD) Germany (MOFA) USAID | 98720 112158 |  |  | 0.5778 | 0.74205
244 | Works | West | Tripoli, Ein Zara | Education | Rehabilitation of School | Phase 1 | 23233 | 13178.9726 | 23228.73 | 13176.5504 | Completed | PO + Contract issuance done | 2018-11-07 | Substantial completion / handover done | 2018-12-07 | 2018-12-14 | 2019-03-18 | Completed | DLP effective till 18 Sep 2019 | 2019-04-25 | Completed | School | 1 | 141 | Japan | 98720 | 32.8413 | 13.2152 | 0.7431 | 0.56725
245 | Works | West | Tripoli, Ein Zara | Education | Rehabilitation of School | Phase 1 | 28135 | 14803.9867 | 28119.61 | 14795.8888 | Completed | PO + Contract issuance done | 2018-11-07 | Substantial completion / handover done | 2018-12-07 | 2018-12-14 | 2019-03-18 | Completed | DLP effective till 18 Sep 2019 | 2019-04-25 | Completed | School | 1 | 141 | Japan | 98720 | 32.8496 | 13.2057 | 0.68683 | 0.52618
246 | Works | West | Tripoli, Ein Zara | Education | Rehabilitation of School | Phase 1 | 45334 | 28254.2658 | 36389.69 | 22679.7541 | Completed | PO + Contract issuance done | 2018-11-07 | Substantial completion / handover done | 2018-12-07 | 2018-12-14 | 2019-03-18 | Completed | DLP effective till 18 Sep 2019 | 2019-04-25 | Completed | School | 1 | 141 | Japan | 98720 | 32.8321 | 13.2366 | 0.57328 | 0.62325
247 | Works | West | Tripoli, Ein Zara | Education | Rehabilitation of School | Phase 1 | 27057 | 15508.6319 | 26929.49 | 15435.5452 | Completed | PO + Contract issuance done | 2018-11-20 | Substantial completion / handover done | 2018-11-27 | 2018-12-04 | 2019-03-18 | Completed | DLP effective till 18 Sep 2019 | 2019-04-25 | Completed | School | 1 | 10159 | EU | 112158 | 32.8019 | 13.2824 | 0.69398 | 0.57318
248 | Works | West | Tripoli, Ein Zara | Education | Rehabilitation of School | Phase 1 | 37240 | 25666.4618 | 37037.12 | 25526.6334 | Completed | PO + Contract issuance done | 2018-11-20 | Substantial completion / handover done | 2018-11-27 | 2018-12-04 | 2019-03-18 | Completed | DLP effective till 18 Sep 2019 | 2019-04-25 | Completed | School | 1 | 10159 | EU | 112158 | 32.8591 | 13.207 | 0.62828 | 0.68922
249 | Works | West | Tripoli, Ein Zara | Education | Rehabilitation of School | Phase 1 | 24702 | 17989.1687 | 24545 | 17874.8339 | Completed | PO + Contract issuance done | 2018-11-20 | Substantial completion / handover done | 2018-11-27 | 2018-12-04 | 2019-03-18 | Completed | DLP effective till 18 Sep 2019 | 2019-04-25 | Completed | School | 1 | 10159 | EU | 112158 | 32.8185 | 13.2342 | 0.59794 | 0.72825
250 | Goods | West | Tripoli, Ein Zara | Health | Suppy of Medical Equipment | Phase 1 | 26010.0531 | 17656.1978 | 21603.6606 | 14665.0414 | Completed | PO + Contract issuance done | 2019-01-29 | Substantial completion / handover done |  |  | 2020-11-05 | Completed | Handover documents signed on 5 Nov 2020. Transfer of title lists equipment under Lot A & D delivered. Sensitive reagents (Lot B & C) not included. | 2020-11-11 | Completed | Medical Equipment | 1 | 187 12113 117 10480 | Norway Canada (DFATD) Germany (MOFA) USAID | 98720 112158 |  |  | 0.66746 | 0.67882
251 | Goods | West | Tripoli, Ein Zara | Health | Suppy of Medical Equipment | Phase 1 | 26010.0531 | 16458.697 | 21603.6606 | 13670.4106 | Completed | PO + Contract issuance done | 2019-01-29 | Substantial completion / handover done |  |  | 2020-11-05 | Completed | Handover documents signed on 5 Nov 2020. Transfer of title lists equipment under Lot A & D delivered. Sensitive reagents (Lot B & C) not included. | 2020-11-11 | Completed | Medical Equipment | 1 | 187 12113 117 10480 | Norway Canada (DFATD) Germany (MOFA) USAID | 98720 112158 |  |  | 0.6099 | 0.63278
252 | Goods | West | Tripoli, Ein Zara | Health | Suppy of Medical Equipment | Phase 1 | 26010.0531 | 14409.3876 | 21603.6606 | 11968.277 | Completed | PO + Contract issuance done | 2019-01-29 | Substantial completion / handover done |  |  | 2020-11-05 | Completed | Handover documents signed on 5 Nov 2020. Transfer of title lists equipment under Lot A & D delivered. Sensitive reagents (Lot B & C) not included. | 2020-11-11 | Completed | Medical Equipment | 1 | 187 12113 117 10480 | Norway Canada (DFATD) Germany (MOFA) USAID | 98720 112158 |  |  | 0.64445 | 0.55399
253 | Goods | West | Tripoli, Ein Zara | Health | Suppy of Medical Equipment | Phase 1 | 26010.0531 | 15626.2975 | 21603.6606 | 12979.0288 | Completed | PO + Contract issuance done | 2019-01-29 | Substantial completion / handover done |  |  | 2020-11-05 | Completed | Handover documents signed on 5 Nov 2020. Transfer of title lists equipment under Lot A & D delivered. Sensitive reagents (Lot B & C) not included. | 2020-11-11 | Completed | Medical Equipment | 1 | 187 12113 117 10480 | Norway Canada (DFATD) Germany (MOFA) USAID | 98720 112158 |  |  | 0.66124 | 0.60078
254 | Goods | West | Tripoli, Ein Zara | Health | Suppy of Medical Equipment | Phase 1 | 26010.0531 | 14730.4721 | 21603.6606 | 12234.9662 | Completed | PO + Contract issuance done | 2019-01-29 | Substantial completion / handover done |  |  | 2020-11-05 | Completed | Handover documents signed on 5 Nov 2020. Transfer of title lists equipment under Lot A & D delivered. Sensitive reagents (Lot B & C) not included. | 2020-11-11 | Completed | Medical Equipment | 1 | 187 12113 117 10480 | Norway Canada (DFATD) Germany (MOFA) USAID | 98720 112158 |  |  | 0.55694 | 0.56634
255 | Works | West | Tripoli, Hay Al-Andoules | Education | Rehabilitation of School | Phase 1 | 24030 | 16510.1221 | 23329.33 | 16028.7177 | Completed | PO + Contract issuance done | 2018-10-23 | Substantial completion / handover done | 2018-11-22 | 2018-11-29 | 2019-03-20 | Completed | Handover recorded/completed much later than actual completion due to conflict | 2019-04-11 | Completed | School | 1 | 10283 | Germay(KfW) | 112158 | 32.8559 | 13.0955 | 0.69551 | 0.68706
256 | Works | West | Tripoli, Hay Al-Andoules | Education | Rehabilitation of School | Phase 1 | 32870 | 20019.7251 | 32431.76 | 19752.8116 | Completed | PO + Contract issuance done | 2018-10-23 | Substantial completion / handover done | 2018-11-22 | 2018-11-29 | 2019-03-12 | Completed | Handover recorded/completed much later than actual completion due to conflict | 2019-04-11 | Completed | School | 1 | 10283 | Germay(KfW) | 112158 | 32.8652 | 13.1258 | 0.50013 | 0.60906
257 | Works | West | Tripoli, Hay Al-Andoules | Education | Rehabilitation of School | Phase 1 | 16547.5 | 11625.4187 | 15844.6 | 11131.5974 | Completed | PO + Contract issuance done | 2018-10-23 | Substantial completion / handover done | 2018-11-22 | 2018-11-29 | 2019-03-11 | Completed | Handover recorded/completed much later than actual completion due to conflict | 2019-04-11 | Completed | School | 1 | 10283 | Germay(KfW) | 112158 | 32.8466 | 13.1321 | 0.60368 | 0.70255
258 | Works | West | Tripoli, Hay Al-Andoules | Education | Rehabilitation of School | Phase 1 | 23541 | 14154.495 | 22822.3 | 13722.3623 | Completed | PO + Contract issuance done | 2018-10-19 | Substantial completion / handover done | 2018-11-17 | 2018-11-24 | 2019-03-01 | Completed | 100% complete | 2019-03-26 | Completed | School | 1 | 141 | Japan | 98720 | 32.8433 | 13.1171 | 0.74742 | 0.60127
259 | Works | West | Tripoli, Hay Al-Andoules | Education | Rehabilitation of School | Phase 1 | 23181 | 14166.367 | 23560.9 | 14398.5314 | Completed | PO + Contract issuance done | 2018-10-19 | Substantial completion / handover done | 2018-11-17 | 2018-11-24 | 2019-03-01 | Completed | 100% complete | 2019-03-26 | Completed | School | 1 | 141 | Japan | 98720 | 32.7907 | 13.0874 | 0.71309 | 0.61112
260 | Works | West | Tripoli, Hay Al-Andoules | Education | Rehabilitation of School | Phase 1 | 32300 | 24212.3092 | 32638.8 | 24466.2761 | Completed | PO + Contract issuance done | 2018-10-19 | Substantial completion / handover done | 2018-11-17 | 2018-11-24 | 2019-03-01 | Completed | 100% complete | 2019-03-26 | Completed | School | 1 | 141 | Japan | 98720 | 32.8504 | 13.116 | 0.68131 | 0.74961
261 | Goods | West | Tripoli, Hay Al-Andoules | Health | Suppy of Medical Equipment | Phase 1 | 26010.0531 | 14736.7288 | 21603.6606 | 12240.163 | Completed | PO + Contract issuance done | 2019-01-29 | Substantial completion / handover done |  |  | 2020-11-05 | Completed | Handover documents signed on 5 Nov 2020. Transfer of title lists equipment under Lot A & D delivered. Sensitive reagents (Lot B & C) not included. | 2020-11-11 | Completed | Medical Equipment | 1 | 187 12113 117 10480 | Norway Canada (DFATD) Germany (MOFA) USAID | 98720 112158 |  |  | 0.70921 | 0.56658
262 | Goods | West | Tripoli, Hay Al-Andoules | Health | Suppy of Medical Equipment | Phase 1 | 26010.0531 | 18396.284 | 21603.6606 | 15279.7488 | Completed | PO + Contract issuance done | 2019-01-29 | Substantial completion / handover done |  |  | 2020-11-05 | Completed | Handover documents signed on 5 Nov 2020. Transfer of title lists equipment under Lot A & D delivered. Sensitive reagents (Lot B & C) not included. | 2020-11-11 | Completed | Medical Equipment | 1 | 187 12113 117 10480 | Norway Canada (DFATD) Germany (MOFA) USAID | 98720 112158 |  |  | 0.66998 | 0.70728
263 | Goods | West | Tripoli, Hay Al-Andoules | Health | Suppy of Medical Equipment | Phase 1 | 26010.0531 | 18290.5866 | 21603.6606 | 15191.9577 | Completed | PO + Contract issuance done | 2019-01-29 | Substantial completion / handover done |  |  | 2020-11-05 | Completed | Handover documents signed on 5 Nov 2020. Transfer of title lists equipment under Lot A & D delivered. Sensitive reagents (Lot B & C) not included. | 2020-11-11 | Completed | Medical Equipment | 1 | 187 12113 117 10480 | Norway Canada (DFATD) Germany (MOFA) USAID | 98720 112158 |  |  | 0.70872 | 0.70321
264 | Goods | West | Tripoli, Hay Al-Andoules | Health | Suppy of Medical Equipment | Phase 1 | 26010.0531 | 15015.8308 | 21603.6606 | 12471.982 | Completed | PO + Contract issuance done | 2019-01-29 | Substantial completion / handover done |  |  | 2020-11-05 | Completed | Handover documents signed on 5 Nov 2020. Transfer of title lists equipment under Lot A & D delivered. Sensitive reagents (Lot B & C) not included. | 2020-11-11 | Completed | Medical Equipment | 1 | 187 12113 117 10480 | Norway Canada (DFATD) Germany (MOFA) USAID | 98720 112158 |  |  | 0.55598 | 0.57731
265 | Goods | West | Tripoli, Hay Al-Andoules | Health | Suppy of Medical Equipment | Phase 1 | 26010.0531 | 15289.7019 | 21603.6606 | 12699.4563 | Completed | PO + Contract issuance done | 2019-01-29 | Substantial completion / handover done |  |  | 2020-11-05 | Completed | Handover documents signed on 5 Nov 2020. Transfer of title lists equipment under Lot A & D delivered. Sensitive reagents (Lot B & C) not included. | 2020-11-11 | Completed | Medical Equipment | 1 | 187 12113 117 10480 | Norway Canada (DFATD) Germany (MOFA) USAID | 98720 112158 |  |  | 0.66654 | 0.58784
266 | Works | West | Tripoli, Ben Gashir | Education | Rehabilitation of School | Phase 1 | 94954 | 59538.941 | 94908.74 | 59510.5617 | Completed | PO + Contract issuance done | 2019-08-25 | Substantial completion / handover done | 2020-06-17 |  | 2021-01-03 | Completed | Completed and handed over on 3 Jan 2021 | 2021-01-18 | Completed | School | 1 | 717 | C/S ROK | 112158 | 32.6823 | 13.1248 | 0.5979 | 0.62703
267 | Works | West | Tripoli, Ben Gashir | Education | Rehabilitation of School | Phase 1 |  | 0 |  | 0 | Completed | PO + Contract issuance done | 2019-08-25 | Substantial completion / handover done | 2020-06-17 |  | 2021-01-03 | Completed | Completed and handed over on 3 Jan 2021 | 2021-01-18 | Completed | School | 1 | 717 | C/S ROK | 112158 | 32.691 | 13.1505 | 0.56999 | 0.74237
268 | Works | West | Tripoli, Ben Gashir | Education | Rehabilitation of School | Phase 1 |  | 0 |  | 0 | Completed | PO + Contract issuance done | 2019-08-25 | Substantial completion / handover done | 2020-06-17 |  | 2021-01-03 | Completed | Completed and handed over on 3 Jan 2021 | 2021-01-18 | Completed | School | 1 | 717 | C/S ROK | 112158 | 32.5998 | 13.2125 | 0.60077 | 0.54806
269 | Works | West | Tripoli, Ben Gashir | Education | Rehabilitation of School | Phase 1 | 29966 | 18724.2139 | 45114.343 | 28189.6352 | Completed | PO + Contract issuance done | 2018-11-26 | Substantial completion / handover done | 2018-12-16 | 2018-12-23 | 2020-04-19 | Completed | Completion according to previous contract recorded and signed dated 19 April 2020 to close the contract. | 2021-09-01 | Completed | School | 1 | 10159 | EU | 112158 | 32.6823 | 13.1248 | 0.55518 | 0.62485
270 | Works | West | Tripoli, Ben Gashir | Education | Rehabilitation of School | Phase 1 | 26214 | 14801.9705 |  | 0 | Completed | PO + Contract issuance done | 2018-11-26 | Substantial completion / handover done | 2018-12-16 | 2018-12-23 | 2020-04-19 | Completed | Completion according to previous contract recorded and signed dated 19 April 2020 to close the contract. Repair works for substantial damage will be conducted under new contract, subject to additional funding. | 2021-09-01 | Completed | School | 1 | 10159 | EU | 112158 | 32.6912 | 13.1506 | 0.54445 | 0.56466
271 | Works | West | Tripoli, Ben Gashir | Education | Rehabilitation of School | Phase 1 | 42616 | 24460.4964 | 51934.467 | 29809.0586 | Completed | PO + Contract issuance done | 2018-11-26 | Substantial completion / handover done | 2018-12-16 | 2018-12-23 | 2020-04-19 | Completed | Completion according to previous contract recorded and signed dated 19 April 2020 to close the contract. | 2021-09-01 | Completed | School | 1 | 10159 | EU | 112158 |  |  | 0.55142 | 0.57397
272 | Goods | West | Tripoli, Ben Gashir | Health | Suppy of Medical Equipment | Phase 1 | 26010.0531 | 18868.7622 | 21603.6606 | 15672.1839 | Completed | PO + Contract issuance done | 2019-01-29 | Substantial completion / handover done |  |  | 2020-11-05 | Completed | Handover documents signed on 5 Nov 2020. Transfer of title lists equipment under Lot A & D delivered. Sensitive reagents (Lot B & C) not included. | 2020-11-11 | Completed | Medical Equipment | 1 | 187 12113 117 10480 | Norway Canada (DFATD) Germany (MOFA) USAID | 98720 112158 |  |  | 0.59787 | 0.72544
273 | Goods | West | Tripoli, Ben Gashir | Health | Suppy of Medical Equipment | Phase 1 | 26010.0531 | 14734.5187 | 21603.6606 | 12238.3272 | Completed | PO + Contract issuance done | 2019-01-29 | Substantial completion / handover done |  |  | 2020-11-05 | Completed | Handover documents signed on 5 Nov 2020. Transfer of title lists equipment under Lot A & D delivered. Sensitive reagents (Lot B & C) not included. | 2020-11-11 | Completed | Medical Equipment | 1 | 187 12113 117 10480 | Norway Canada (DFATD) Germany (MOFA) USAID | 98720 112158 | 32.6183 | 13.2229 | 0.5229 | 0.56649
274 | Goods | West | Tripoli, Ben Gashir | Health | Suppy of Medical Equipment | Phase 1 | 26010.0531 | 17829.57 | 21603.6606 | 14809.0424 | Completed | PO + Contract issuance done | 2019-01-29 | Substantial completion / handover done |  |  | 2020-11-05 | Completed | Handover documents signed on 5 Nov 2020. Transfer of title lists equipment under Lot A & D delivered. Sensitive reagents (Lot B & C) not included. | 2020-11-11 | Completed | Medical Equipment | 1 | 187 12113 117 10480 | Norway Canada (DFATD) Germany (MOFA) USAID | 98720 112158 |  |  | 0.73646 | 0.68549
275 | Goods | West | Tripoli, Ben Gashir | Health | Suppy of Medical Equipment | Phase 1 | 26010.0531 | 15595.4381 | 21603.6606 | 12953.3973 | Completed | PO + Contract issuance done | 2019-01-29 | Substantial completion / handover done |  |  | 2020-11-05 | Completed | Handover documents signed on 5 Nov 2020. Transfer of title lists equipment under Lot A & D delivered. Sensitive reagents (Lot B & C) not included. | 2020-11-11 | Completed | Medical Equipment | 1 | 187 12113 117 10480 | Norway Canada (DFATD) Germany (MOFA) USAID | 98720 112158 |  |  | 0.61136 | 0.59959
276 | Goods | West | Tripoli, Ben Gashir | Health | Suppy of Medical Equipment | Phase 1 | 26010.0531 | 16627.589 | 21603.6606 | 13810.6904 | Completed | PO + Contract issuance done | 2019-01-29 | Substantial completion / handover done |  |  | 2020-11-05 | Completed | Handover documents signed on 5 Nov 2020. Transfer of title lists equipment under Lot A & D delivered. Sensitive reagents (Lot B & C) not included. | 2020-11-11 | Completed | Medical Equipment | 1 | 187 12113 117 10480 | Norway Canada (DFATD) Germany (MOFA) USAID | 98720 112158 |  |  | 0.64188 | 0.63928
277 | Works | West | Tripoli, Souq Al-Khamees | Education | Rehabilitation of School | Phase 1 | 24300 | 15275.6486 | 18684.05 | 11745.3079 | Completed | PO + Contract issuance done | 2018-11-27 | Substantial completion / handover done | 2018-12-12 | 2018-12-19 | 2019-03-26 | Completed | Construction completed back in March 2019 but subastantial handover delayed due to start of conflict | 2019-11-22 | Completed | School | 1 | 10480 | USAID | 112158 | 32.302 | 13.268 | 0.60943 | 0.62863
278 | Works | West | Tripoli, Souq Al-Khamees | Education | Rehabilitation of School | Phase 1 | 31356.5 | 19723.1583 | 25648.98 | 16133.1428 | Completed | PO + Contract issuance done | 2018-11-27 | Substantial completion / handover done | 2018-12-12 | 2018-12-19 | 2019-03-26 | Completed | Construction completed back in March 2019 but subastantial handover delayed due to start of conflict | 2019-11-22 | Completed | School | 1 | 10480 | USAID | 112158 | 32.381 | 13.229 | 0.67858 | 0.629
279 | Works | West | Tripoli, Souq Al-Khamees | Education | Rehabilitation of School | Phase 1 | 31469.5 | 16927.7367 | 42742.89 | 22991.798 | Completed | PO + Contract issuance done | 2018-11-27 | Substantial completion / handover done | 2018-12-12 | 2018-12-19 | 2019-03-26 | Completed | Construction completed back in March 2019 but subastantial handover delayed due to start of conflict | 2019-11-22 | Completed | School | 1 | 10480 | USAID | 112158 | 32.467 | 13.256 | 0.52959 | 0.53791
280 | Works | West | Tripoli, Souq Al-Khamees | Education | Rehabilitation of School | Phase 1 | 21840 | 12426.7494 | 20735.15 | 11798.1004 | Completed | PO + Contract issuance done | 2018-11-19 | Substantial completion / handover done | 2018-12-19 | 2018-12-26 | 2019-11-07 | Completed | Construction completed back in april 2019 but subastantial handover delayed due to start of conflict | 2019-11-22 | Completed | School | 1 | 10480 10283 | USAID Germay(KfW) | 112158 | 32.408 | 13.228 | 0.63381 | 0.56899
281 | Works | West | Tripoli, Souq Al-Khamees | Education | Rehabilitation of School | Phase 1 | 40070 | 28157.5774 | 44472.96 | 31251.58 | Completed | PO + Contract issuance done | 2018-11-19 | Substantial completion / handover done | 2018-12-19 | 2018-12-26 | 2019-11-07 | Completed | Construction completed back in april 2019 but subastantial handover delayed due to start of conflict | 2019-11-22 | Completed | School | 1 | 10480 10283 | USAID Germay(KfW) | 112158 | 32.299 | 13.269 | 0.74746 | 0.70271
282 | Works | West | Tripoli, Souq Al-Khamees | Education | Rehabilitation of School | Phase 1 | 26575 | 17114.5776 | 22612.36 | 14562.596 | Completed | PO + Contract issuance done | 2018-11-19 | Substantial completion / handover done | 2018-12-19 | 2018-12-26 | 2019-11-07 | Completed | Construction completed back in april 2019 but subastantial handover delayed due to start of conflict | 2019-11-22 | Completed | School | 1 | 10480 10283 | USAID Germay(KfW) | 112158 | 32.444 | 13.283 | 0.63604 | 0.64401
283 | Goods | West | Tripoli, Souq Al-Khamees | Health | Suppy of Medical Equipment | Phase 1 | 26010.0531 | 14514.8175 | 21603.6606 | 12055.8459 | Completed | PO + Contract issuance done | 2019-01-29 | Substantial completion / handover done |  |  | 2020-11-05 | Completed | Handover documents signed on 5 Nov 2020. Transfer of title lists equipment under Lot A & D delivered. Sensitive reagents (Lot B & C) not included. | 2020-11-11 | Completed | Medical Equipment | 1 | 187 12113 117 10480 | Norway Canada (DFATD) Germany (MOFA) USAID | 98720 112158 |  |  | 0.71063 | 0.55805
284 | Goods | West | Tripoli, Souq Al-Khamees | Health | Suppy of Medical Equipment | Phase 1 | 26010.0531 | 18055.8305 | 21603.6606 | 14996.9718 | Completed | PO + Contract issuance done | 2019-01-29 | Substantial completion / handover done |  |  | 2020-11-05 | Completed | Handover documents signed on 5 Nov 2020. Transfer of title lists equipment under Lot A & D delivered. Sensitive reagents (Lot B & C) not included. | 2020-11-11 | Completed | Medical Equipment | 1 | 187 12113 117 10480 | Norway Canada (DFATD) Germany (MOFA) USAID | 98720 112158 |  |  | 0.62511 | 0.69419
285 | Goods | West | Tripoli, Souq Al-Khamees | Health | Suppy of Medical Equipment | Phase 1 | 26010.0531 | 18967.5173 | 21603.6606 | 15754.2088 | Completed | PO + Contract issuance done | 2019-01-29 | Substantial completion / handover done |  |  | 2020-11-05 | Completed | Handover documents signed on 5 Nov 2020. Transfer of title lists equipment under Lot A & D delivered. Sensitive reagents (Lot B & C) not included. | 2020-11-11 | Completed | Medical Equipment | 1 | 187 12113 117 10480 | Norway Canada (DFATD) Germany (MOFA) USAID | 98720 112158 |  |  | 0.53643 | 0.72924
286 | Goods | West | Tripoli, Souq Al-Khamees | Health | Suppy of Medical Equipment | Phase 1 | 26010.0531 | 18257.7441 | 21603.6606 | 15164.6791 | Completed | PO + Contract issuance done | 2019-01-29 | Substantial completion / handover done |  |  | 2020-11-05 | Completed | Handover documents signed on 5 Nov 2020. Transfer of title lists equipment under Lot A & D delivered. Sensitive reagents (Lot B & C) not included. | 2020-11-11 | Completed | Medical Equipment | 1 | 187 12113 117 10480 | Norway Canada (DFATD) Germany (MOFA) USAID | 98720 112158 |  |  | 0.74744 | 0.70195
287 | Goods | West | Tripoli, Souq Al-Khamees | Health | Suppy of Medical Equipment | Phase 1 | 26010.0531 | 15854.6724 | 21603.6606 | 13168.7144 | Completed | PO + Contract issuance done | 2019-01-29 | Substantial completion / handover done |  |  | 2020-11-05 | Completed | Handover documents signed on 5 Nov 2020. Transfer of title lists equipment under Lot A & D delivered. Sensitive reagents (Lot B & C) not included. | 2020-11-11 | Completed | Medical Equipment | 1 | 187 12113 117 10480 | Norway Canada (DFATD) Germany (MOFA) USAID | 98720 112158 |  |  | 0.50546 | 0.60956
288 | Works | West | Tripoli, Souq Al-Gomma | Education | Rehabilitation of School | Phase 1 | 35113 | 26281.3261 | 35113 | 26281.3261 | Completed | PO + Contract issuance done | 2018-11-08 | Substantial completion / handover done | 2018-11-15 | 2018-11-22 | 2019-04-25 | Completed | Delayed handover due to conflict | 2019-07-25 | Completed | School | 1 | 717 | C/S ROK | 98720 | 32.9051 | 13.2551 | 0.57584 | 0.74848
289 | Works | West | Tripoli, Souq Al-Gomma | Education | Rehabilitation of School | Phase 1 | 31253 | 20010.9067 | 31253 | 20010.9067 | Completed | PO + Contract issuance done | 2018-11-08 | Substantial completion / handover done | 2018-11-15 | 2018-11-22 | 2019-04-25 | Completed | Delayed handover due to conflict | 2019-07-25 | Completed | School | 1 | 717 | C/S ROK | 98720 | 32.887 | 13.2304 | 0.66257 | 0.64029
290 | Works | West | Tripoli, Souq Al-Gomma | Education | Rehabilitation of School | Phase 1 | 38578 | 23505.1749 | 38452.94 | 23428.9771 | Completed | PO + Contract issuance done | 2018-11-08 | Substantial completion / handover done | 2018-11-15 | 2018-11-22 | 2019-04-25 | Completed | Delayed handover due to conflict | 2019-07-25 | Completed | School | 1 | 717 | C/S ROK | 98720 | 32.8935 | 13.2385 | 0.53125 | 0.60929
291 | Works | West | Tripoli, Souq Al-Gomma | Education | Rehabilitation of School | Phase 1 | 41886 | 24237.4217 | 36624.65 | 21192.9305 | Completed | PO + Contract issuance done | 2018-10-26 | Substantial completion / handover done | 2018-11-02 | 2018-11-09 | 2019-03-06 | Completed | DLP effective till 6 Sep 2019 | 2019-04-25 | Completed | School | 1 | 141 | Japan | 98720 | 32.9033 | 13.2385 | 0.71058 | 0.57865
292 | Works | West | Tripoli, Souq Al-Gomma | Education | Rehabilitation of School | Phase 1 | 14780 | 9422.2217 | 19421.32 | 12381.0544 | Completed | PO + Contract issuance done | 2018-10-26 | Substantial completion / handover done | 2018-11-02 | 2018-11-09 | 2019-03-06 | Completed | DLP effective till 6 Sep 2019 | 2019-04-25 | Completed | School | 1 | 141 | Japan | 98720 | 32.8893 | 13.2371 | 0.60948 | 0.6375
293 | Works | West | Tripoli, Souq Al-Gomma | Education | Rehabilitation of School | Phase 1 | 15315 | 9558.5693 | 15861.21 | 9899.476 | Completed | PO + Contract issuance done | 2018-10-26 | Substantial completion / handover done | 2018-11-02 | 2018-11-09 | 2019-03-06 | Completed | DLP effective till 6 Sep 2019 | 2019-04-25 | Completed | School | 1 | 141 | Japan | 98720 | 32.8905 | 13.2442 | 0.50668 | 0.62413
294 | Goods | West | Tripoli, Souq Al-Gomma | Health | Suppy of Medical Equipment | Phase 1 | 26010.0531 | 18397.3976 | 21603.6606 | 15280.6737 | Completed | PO + Contract issuance done | 2019-01-29 | Substantial completion / handover done |  |  | 2020-11-05 | Completed | Handover documents signed on 5 Nov 2020. Transfer of title lists equipment under Lot A & D delivered. Sensitive reagents (Lot B & C) not included. | 2020-11-11 | Completed | Medical Equipment | 1 | 187 12113 117 10480 | Norway Canada (DFATD) Germany (MOFA) USAID | 98720 112158 |  |  | 0.52967 | 0.70732
295 | Goods | West | Tripoli, Souq Al-Gomma | Health | Suppy of Medical Equipment | Phase 1 | 26010.0531 | 15182.2779 | 21603.6606 | 12610.2311 | Completed | PO + Contract issuance done | 2019-01-29 | Substantial completion / handover done |  |  | 2020-11-05 | Completed | Handover documents signed on 5 Nov 2020. Transfer of title lists equipment under Lot A & D delivered. Sensitive reagents (Lot B & C) not included. | 2020-11-11 | Completed | Medical Equipment | 1 | 187 12113 117 10480 | Norway Canada (DFATD) Germany (MOFA) USAID | 98720 112158 |  |  | 0.71207 | 0.58371
296 | Goods | West | Tripoli, Souq Al-Gomma | Health | Suppy of Medical Equipment | Phase 1 | 26010.0531 | 16349.0705 | 21603.6606 | 13579.356 | Completed | PO + Contract issuance done | 2019-01-29 | Substantial completion / handover done |  |  | 2020-11-05 | Completed | Handover documents signed on 5 Nov 2020. Transfer of title lists equipment under Lot A & D delivered. Sensitive reagents (Lot B & C) not included. | 2020-11-11 | Completed | Medical Equipment | 1 | 187 12113 117 10480 | Norway Canada (DFATD) Germany (MOFA) USAID | 98720 112158 |  |  | 0.67033 | 0.62857
297 | Goods | West | Tripoli, Souq Al-Gomma | Health | Suppy of Medical Equipment | Phase 1 | 26010.0531 | 18021.1994 | 21603.6606 | 14968.2077 | Completed | PO + Contract issuance done | 2019-01-29 | Substantial completion / handover done |  |  | 2020-11-05 | Completed | Handover documents signed on 5 Nov 2020. Transfer of title lists equipment under Lot A & D delivered. Sensitive reagents (Lot B & C) not included. | 2020-11-11 | Completed | Medical Equipment | 1 | 187 12113 117 10480 | Norway Canada (DFATD) Germany (MOFA) USAID | 98720 112158 |  |  | 0.74453 | 0.69286
298 | Goods | West | Tripoli, Souq Al-Gomma | Health | Suppy of Medical Equipment | Phase 1 | 26010.0531 | 16967.759 | 21603.6606 | 14093.2318 | Completed | PO + Contract issuance done | 2019-01-29 | Substantial completion / handover done |  |  | 2020-11-05 | Completed | Handover documents signed on 5 Nov 2020. Transfer of title lists equipment under Lot A & D delivered. Sensitive reagents (Lot B & C) not included. | 2020-11-11 | Completed | Medical Equipment | 1 | 187 12113 117 10480 | Norway Canada (DFATD) Germany (MOFA) USAID | 98720 112158 |  |  | 0.51147 | 0.65235
299 | Goods | West | Tripoli, Souq Al-Gomma | Health | Supply of Generators | Phase 1 | 51370.537 | 29789.1274 | 55870.5726 | 32398.6414 | Completed | PO + Contract issuance done | 2018-10-03 | Substantial completion / handover done |  |  | 2019-06-30 | Completed | Delivered on 30 June 2019 | 2019-07-03 | Completed | Generator | 1 | 10283 | Germay(KfW) | 98720 |  |  | 0.68332 | 0.57989
300 | Works | West | Tripoli, Tajoura | Education | Rehabilitation of School | Phase 1 | 28750 | 16541.2735 | 87635.92 | 50421.2077 | Completed | PO + Contract issuance done | 2018-07-19 | Substantial completion / handover done | 2018-08-18 | 2018-08-25 | 2018-12-05 | Completed | DLP effective till 5 June 2019 | 2019-04-25 | Completed | School | 1 | 717 | C/S ROK | 98720 | 32.7706 | 13.4718 | 0.59221 | 0.57535
301 | Works | West | Tripoli, Tajoura | Education | Rehabilitation of School | Phase 1 | 29005 | 15342.0877 |  | 0 | Completed | PO + Contract issuance done | 2018-07-19 | Substantial completion / handover done | 2018-08-18 | 2018-08-25 | 2018-12-05 | Completed | DLP effective till 5 June 2019 | 2019-04-25 | Completed | School | 1 | 717 | C/S ROK | 98720 | 32.7574 | 13.3102 | 0.67536 | 0.52895
302 | Works | West | Tripoli, Tajoura | Education | Rehabilitation of School | Phase 1 | 29940 | 18574.321 |  | 0 | Completed | PO + Contract issuance done | 2018-07-19 | Substantial completion / handover done | 2018-08-18 | 2018-08-25 | 2018-12-05 | Completed | DLP effective till 5 June 2019 | 2019-04-25 | Completed | School | 1 | 717 | C/S ROK | 98720 | 32.8803 | 13.3077 | 0.53966 | 0.62038
303 | Works | West | Tripoli, Tajoura | Education | Rehabilitation of School | Phase 1 | 22890 | 15692.3531 | 89757.09 | 61533.4183 | Completed | PO + Contract issuance done | 2018-07-19 | Substantial completion / handover done | 2018-08-18 | 2018-08-25 | 2018-12-05 | Completed | DLP effective till 15 June 2019 | 2019-04-25 | Completed | School | 1 | 717 | C/S ROK | 98720 | 32.8685 | 13.3605 | 0.60623 | 0.68555
304 | Works | West | Tripoli, Tajoura | Education | Rehabilitation of School | Phase 1 | 35475 | 22142.3559 |  | 0 | Completed | PO + Contract issuance done | 2018-07-19 | Substantial completion / handover done | 2018-08-18 | 2018-08-25 | 2018-12-05 | Completed | DLP effective till 15 June 2019 | 2019-04-25 | Completed | School | 1 | 717 | C/S ROK | 98720 | 32.8906 | 13.3343 | 0.53173 | 0.62417
305 | Works | West | Tripoli, Tajoura | Education | Rehabilitation of School | Phase 1 | 31450 | 19728.0663 |  | 0 | Completed | PO + Contract issuance done | 2018-07-19 | Substantial completion / handover done | 2018-08-18 | 2018-08-25 | 2018-12-05 | Completed | DLP effective till 15 June 2019 | 2019-04-25 | Completed | School | 1 | 717 | C/S ROK | 98720 | 32.7937 | 13.4407 | 0.51761 | 0.62728
306 | Goods | West | Tripoli, Tajoura | Health | Suppy of Medical Equipment | Phase 1 | 26010.0531 | 17457.6614 | 21603.6606 | 14500.1393 | Completed | PO + Contract issuance done | 2019-01-29 | Substantial completion / handover done |  |  | 2020-11-05 | Completed | Handover documents signed on 5 Nov 2020. Transfer of title lists equipment under Lot A & D delivered. Sensitive reagents (Lot B & C) not included. | 2020-11-11 | Completed | Medical Equipment | 1 | 187 12113 117 10480 | Norway Canada (DFATD) Germany (MOFA) USAID | 98720 112158 |  |  | 0.60728 | 0.67119
307 | Goods | West | Tripoli, Tajoura | Health | Suppy of Medical Equipment | Phase 1 | 26010.0531 | 15787.8673 | 21603.6606 | 13113.2268 | Completed | PO + Contract issuance done | 2019-01-29 | Substantial completion / handover done |  |  | 2020-11-05 | Completed | Handover documents signed on 5 Nov 2020. Transfer of title lists equipment under Lot A & D delivered. Sensitive reagents (Lot B & C) not included. | 2020-11-11 | Completed | Medical Equipment | 1 | 187 12113 117 10480 | Norway Canada (DFATD) Germany (MOFA) USAID | 98720 112158 |  |  | 0.67116 | 0.60699
308 | Goods | West | Tripoli, Tajoura | Health | Suppy of Medical Equipment | Phase 1 | 26010.0531 | 18753.1627 | 21603.6606 | 15576.1682 | Completed | PO + Contract issuance done | 2019-01-29 | Substantial completion / handover done |  |  | 2020-11-05 | Completed | Handover documents signed on 5 Nov 2020. Transfer of title lists equipment under Lot A & D delivered. Sensitive reagents (Lot B & C) not included. | 2020-11-11 | Completed | Medical Equipment | 1 | 187 12113 117 10480 | Norway Canada (DFATD) Germany (MOFA) USAID | 98720 112158 |  |  | 0.6849 | 0.721
309 | Goods | West | Tripoli, Tajoura | Health | Suppy of Medical Equipment | Phase 1 | 26010.0531 | 15739.4144 | 21603.6606 | 13072.9825 | Completed | PO + Contract issuance done | 2019-01-29 | Substantial completion / handover done |  |  | 2020-11-05 | Completed | Handover documents signed on 5 Nov 2020. Transfer of title lists equipment under Lot A & D delivered. Sensitive reagents (Lot B & C) not included. | 2020-11-11 | Completed | Medical Equipment | 1 | 187 12113 117 10480 | Norway Canada (DFATD) Germany (MOFA) USAID | 98720 112158 |  |  | 0.60124 | 0.60513
310 | Goods | West | Tripoli, Tajoura | Health | Suppy of Medical Equipment | Phase 1 | 26010.0531 | 13084.8945 | 21603.6606 | 10868.1677 | Completed | PO + Contract issuance done | 2019-01-29 | Substantial completion / handover done |  |  | 2020-11-05 | Completed | Handover documents signed on 5 Nov 2020. Transfer of title lists equipment under Lot A & D delivered. Sensitive reagents (Lot B & C) not included. | 2020-11-11 | Completed | Medical Equipment | 1 | 187 12113 117 10480 | Norway Canada (DFATD) Germany (MOFA) USAID | 98720 112158 |  |  | 0.54687 | 0.50307
311 |  |  | Ajdabiya | Unidentified |  | Broadening |  | 0 |  | 0 | To be initiated | [17 empty] | 0.51391 | 0.67362
| Goods | East | Ajdabiya | Public Infrastructure and Services | Supply of Fire Fighting Trucks | Broadening | 448812.97 | 317229.6216 | 360189.18 | 254588.6258 | Completed | PO + Contract issuance done | 2020-06-25 | Substantial completion / handover done |  |  | 2021-05-07 | Completed | Delivered to end users on 7 May 2021. PO issued on 25 June. | 2021-05-19 | Completed | Firetruck | 2 | 10283 717 | Germany (KfW) C/S ROK | 112158 |  |  | 0.5934 | 0.70682
| Goods | East | Ajdabiya | Solid Waste Management | Supply of Garbage Trucks | Broadening | 100834.125 | 73765.7355 | 76018.375 | 55611.6428 | Completed | PO + Contract issuance done | 2020-06-02 | Substantial completion / handover done |  |  | 2021-06-11 | Completed | Delivered as of 11 June 2021. ETA Misurata 8 May 2021. | 2021-07-28 | Completed | Garbage truck | 1 | 717 | C/S ROK | 112158 |  |  | 0.50935 | 0.73156
312 |  |  | Bani Walid |  |  | Deepening |  | 0 |  | 0 | [18 empty] | 0.74813 | 0.52901
313 | Works | West | Bani Walid | Education | Rehabilitation of University | Deepening | 212142 | 114678.1224 |  | 0 | Completed | [6 empty] | In Development | To be readvertised, revised BOQ approval in process | 2021-07-07 | Further Funding | University | 1 | [5 empty] | 0.50042 | 0.54057
| Works | West | Bani Walid | Education | Rehabilitation of University | Deepening | 208845 | 153942.0278 |  | 0 | Completed | [6 empty] | In Development | To be readvertised, revised BOQ approval in process | 2021-07-07 | Further Funding | University | 1 | [5 empty] | 0.54418 | 0.73711
| Works | West | Bani Walid | Education | Rehabilitation of University | Deepening | 367691 | 209612.5858 |  | 0 | Completed | [6 empty] | In Development | To be readvertised, revised BOQ approval in process | 2021-07-07 | Further Funding | University | 1 |  |  |  | 31.7441 | 14.0092 | 0.66721 | 0.57008
| Works | West | Bani Walid | Education | Rehabilitation of University | Deepening | 107074.5 | 69950.8798 | 107074.5 | 69950.8798 | Completed | PO + Contract issuance done | 2021-03-25 | Substantial completion / handover done | 2021-06-10 | 2021-06-20 | 2021-10-04 | Completed | Completed and handed over on 4 October 2021. Contract signed on 25 March 2021. | 2021-12-10 | Completed | University | 1 | 10159 | SUSC | 122619 | 31.7573 | 14.0259 | 0.57947 | 0.65329
| Goods | West | Bani Walid | Energy | Provision of Power Cables | Deepening | 118438.195 | 78551.5515 | 118438.195 | 78551.5515 | Completed | PO + Contract issuance done | 2019-10-16 | Substantial completion / handover done |  |  | 2019-10-26 | Completed | PO issued on 16 Oct 2019. DAMCO ordered for shipment on same day. Delivered on 26/10. | 2019-11-15 | Completed | Cable | 2 | 10480 10159 | USAID EU | 112158 |  |  | 0.63383 | 0.66323
| Goods | West | Bani Walid | WASH | Supply of Sewage Pumps | Deepening | 24900 | 16823.4366 | 24900 | 16823.4366 | Completed | PO + Contract issuance done | 2021-04-25 | Substantial completion / handover done |  |  | 2021-05-27 | Completed | On May 28 2021, Vendor sent a payment request confirming that the equipment have already been delivered. PO issued on 25 April 2021. | 2021-07-02 | Completed | Water Pump | 5 | 11410 | UK (FCO) | 112158 |  |  | 0.5609 | 0.67564
314 |  |  | Benghazi | Unidentified |  | Deepening |  | 0 |  | 0 | To be initiated | [17 empty] | 0.65554 | 0.6827
315 | Goods | East | Benghazi | WASH | Supply of Sewage Pumps | Deepening | 351319.6 | 223663.7513 | 302269.23 | 192436.3738 | Completed | PO + Contract issuance done | 2019-09-15 | Substantial completion / handover done |  |  | 2020-06-22 | Completed | Handed over on 22 June 2020. Shipment was stopped by the Benghazi customs who did not accept Diplomatic Exemption from MOFA and requested to pay the custom fees @6.35% of total invoice value. | 2020-06-29 | Completed | Sewage Pump | 36 | 10159 141 | EU Japan | 112158 |  |  | 0.55076 | 0.63664
316 | Works | East | Benghazi | Health | Rehabilitation of Hospital | Deepening | 335065 | 178772.9634 | 335013.294 | 178745.3758 | Completed | PO + Contract issuance done | 2020-05-06 | Substantial completion / handover done | 2020-06-14 | 2020-07-30 | 2021-04-08 | Completed | Completed and handed over on 8 April 2021. 1st part-ICU and newborn ward completed and handed over on 19 Nov 2020. 2nd part-patient's room is ongoing and will complete on 20 Feb 2021. Site handed over to contractor on 14 June 2020. | 2021-04-09 | Completed | Hospital | 1 | 187 10283 | Norway Germay(KfW) | 112158 | 32.0769 | 20.0929 | 0.51803 | 0.53355
318 | Works | East | Benghazi | Public Infrastructure and Services | Rehabilitation of Public Building | Deepening | 138962 | 71681.3125 | 138962 | 71681.3125 | Completed | PO + Contract issuance done | 2020-07-09 | Substantial completion / handover done | 2020-07-20 |  | 2020-12-18 | Completed | Works completed. Handover done on 18 Dec 2020. Contract amended on 30 Nov to extend implementation until 30 Dec 2020. Site handed over to contractor on 20 July 2020. Contract issued on 9 July 2020. | 2021-02-16 | Completed | Public Infrastructure | 1 | 10283 | Germay(KfW) | 112158 | 32.1192 | 20.0597 | 0.62492 | 0.51583
319 | Works | East | Benghazi | Education | Rehabilitation of School | Deepening | 187486 | 96613.8627 | 187456.28 | 96598.5476 | Completed | PO + Contract issuance done | 2019-12-18 | Substantial completion / handover done | 2019-12-23 |  | 2020-07-20 | Completed | Substantially handed over on 20 July 2020. | 2020-08-18 | Completed | School | 1 | 10283 | Germay(KfW) | 112158 | 32.1154 | 20.0647 | 0.695 | 0.51531
320 | Works | East | Benghazi | Education | Rehabilitation of School | Deepening | 149110 | 103199.2487 | 148383.23 | 102696.2501 | Completed | PO + Contract issuance done | 2020-06-18 | Substantial completion / handover done | 2020-07-27 |  | 2020-10-14 | Completed | Completed and handed over on 14 Oct 2020. Site handed over to contractor on 27 July 2020. Contract issued on 18 June 2020. | 2020-10-19 | Completed | School | 1 | 141 | Japan | 112158 | 32.1439 | 20.0867 | 0.71387 | 0.6921
321 | Works | East | Benghazi | Energy | Supply and Installation of Solar Street Lights | Deepening | 1251746.97 | 818666.9299 | 1251746.97 | 818666.9299 | Completed | PO + Contract issuance done | 2020-01-09 | Substantial completion / handover done | 2020-06-29 | 2020-08-16 | 2021-06-10 | Completed | Completed on 10 June 2021. Signed handover document shared on 21 Dec 2021. | 2021-12-22 | Completed | Solar Street Light | 24 | 10283 151 | Germay(KfW) Gov't of Libya | 112158 |  |  | 0.56504 | 0.65402
322 | Works | East | Benghazi | Public Infrastructure and Services | Rehabilitation of Public Building | Deepening | 370134 | 264169.7825 | 370088.401 | 264137.2378 | Completed | PO + Contract issuance done | 2020-08-22 | Substantial completion / handover done |  | 2020-11-18 | 2021-04-10 | Completed | Completed and handed over on 10 April 2021. Contract issued on 22 August 2020. | 2021-04-14 | Completed | Public Infrastructure | 1 | 187 10283 | Norway Germany(KfW) | 112158 | 32.1182 | 20.0578 | 0.74341 | 0.71371
323 | Goods | East | Benghazi | WASH | Supply of Sewage Treatment Plant | Deepening | 1000000 | 569133.8935 |  | 0 | BOQ development stage | [6 empty] | Cancelled | On 5 Feb 2021, Shembesh confirmed verbally that this has been cancelled. Shembesh provided signed updated projects list for Benghazi on 23 Feb 2021. | 2021-02-25 | Cancelled | Treatment plant | 1 |  |  |  | 32.1057 | 20.0742 | 0.51197 | 0.56913
| Works | East | Benghazi | Health | Rehabilitation of Clinic | Deepening | 58101 | 30429.8257 | 58101 | 30429.8257 | Completed | PO + Contract issuance done | 2020-12-05 | Substantial completion / handover done | 2020-12-10 |  | 2021-02-11 | Completed | Completed and handed over on 11 Feb 2021. Site handed over on 10 Dec 2020. Contract issued on 5 Dec 2020. | 2021-02-26 | Completed | Clinic | 1 | 112 | France | 98720 |  |  | 0.63887 | 0.52374
| Works | East | Benghazi | Energy | Rehabilitation of Substation | Deepening | 93784 | 64118.0364 | 93784 | 64118.0364 | Completed | PO + Contract issuance done | 2021-06-26 | Substantial completion / handover done |  | 2021-07-28 | 2021-11-28 | Completed | Completed and handed over on 28 Nov 2021. Contract issued on 26 June 2021. | 2021-12-22 | Completed | Substation | 1 | 151 | Gov't of Libya | 112158 | 32.0362 | 20.044 | 0.74125 | 0.68368
324 |  |  | Derna | Unidentified |  | Broadening |  | 0 |  | 0 | To be initiated | [17 empty] | 0.65406 | 0.63368
| Goods | East | Derna | Health | Supply of Ambulances | Broadening | 158657.16 | 106921.7889 | 140485.52 | 94675.6082 | Completed | PO + Contract issuance done | 2020-01-21 | Substantial completion / handover done |  |  | 2020-10-06 | Completed | 3 ICU ambulances handed over on 6 Oct 2020. One regular ambulance delivered on 26 March 2020. | 2020-10-12 | Completed | Ambulance | 4 | 10283 | Germay(KfW) | 112158 |  |  | 0.70776 | 0.67392
| Goods | East | Derna | Solid Waste Management | Supply of Garbage Trucks | Broadening | 302502.375 | 196928.7857 | 228055.125 | 148463.6901 | Completed | PO + Contract issuance done | 2020-06-02 | Substantial completion / handover done |  |  | 2021-06-11 | Completed | Delivered as of 11 June 2021. ETA Misurata 8 May 2021. PO issued on 2 June 2020. | 2021-07-12 | Completed | Garbage truck | 3 | 717 | C/S ROK | 112158 |  |  | 0.72978 | 0.651
| Goods | East | Derna | Public Infrastructure and Services | Supply of Fire Fighting Trucks | Broadening | 448812.97 | 293705.452 | 360189.18 | 235709.6006 | Completed | PO + Contract issuance done | 2020-06-25 | Substantial completion / handover done |  |  | 2021-05-07 | Completed | Delivered to end users on 7 May 2021. PO issued on 25 June. | 2021-05-19 | Completed | Firetruck | 2 | 10283 717 | Germany (KfW) C/S ROK | 112158 |  |  | 0.54775 | 0.65441
| Goods | East | Derna | WASH | Supply of Pesticide Sprayer Trucks | Broadening | 111979.25 | 71783.9434 | 93378.9 | 59860.248 | Completed | PO + Contract issuance done | 2020-06-25 | Substantial completion / handover done |  |  | 2020-12-16 | Completed | Handed over on 16 Dec 2020. PO issued on 25 June 2020. | 2020-12-24 | Completed | Pesticide Sprayer | 3 | 112 717 | France C/S ROK | 98720 112158 |  |  | 0.57685 | 0.64105
| Goods | East | Derna | Health | Supply of Generators | Broadening | 162570.45 | 102649.1587 | 60274.71 | 38058.2589 | Completed | PO + Contract issuance done | 2020-06-25 | Substantial completion / handover done |  |  | 2021-01-28 | Completed | Handed over on 28 Jan 2021. Document pending. Arrived to Benghazi port on 3 Dec 2020. PO issued on 25 June 2020. | 2021-02-12 | Completed | Incinerator | 1 | 141 10283 | Japan Germany(KfW) | 121748 112158 |  |  | 0.56001 | 0.63141
| Goods | East | Derna | WASH | Supply of Water Pumps | Broadening | 84970.31 | 46922.9368 | 74847.36 | 41332.766 | Completed | PO + Contract issuance done | 2021-04-13 | Substantial completion / handover done |  |  | 2021-11-08 | Completed | Handed over to Derna municipality on 8 Nov 2021. PO issued on 13 April 2021. | 2021-12-08 | Completed | Water Pump | 10 | 11410 187 | UK (FCO) Norway | 112158 | 32.752 | 22.6407 | 0.69326 | 0.55223
| Works | East | Derna | Public Infrastructure and Services | Rehabilitation of Public Market | Broadening | 205030 | 134233.813 |  | 0 | Completed | PO + Contract issuance done | 2022-06-22 |  |  |  |  | Contract Issued | As of 3 August 2022, Ehab working on to plan site handover. Contract issued on 22 June 2022. Request submitted through PROMPT on 22 December 2021. | 2022-08-03 | Contract Issued | Public Infrastructure | 1 | 141 | Japan | 127766 |  |  | 0.63871 | 0.6547
| Works | East | Derna | Education | Rehabilitation of School | Broadening | 122795 | 87330.1285 | 110501.19 | 78586.9386 | Completed | PO + Contract issuance done | 2020-12-27 | Substantial completion / handover done | 2021-01-25 | 2021-02-20 | 2021-07-14 | Completed | Handed over on 14 July 2021. Site handed over on 25 Jan 2021. Contract issued on 27 Dec 2020. | 2021-09-01 | Completed | School | 1 | 151 10159 | Gov't of Libya SUSC | 112158 122619 |  |  | 0.62687 | 0.71119
325 |  | South | Ghat |  |  | Broadening |  | 0 |  | 0 | [18 empty] | 0.73061 | 0.59751
326 | Goods | South | Ghat | WASH | Supply of Sewage Suction Trucks | Broadening | 704513.15 | 363592.6138 | 631567.5 | 325946.0496 | Completed | PO + Contract issuance done | 2019-07-23 | Substantial completion / handover done |  |  | 2020-11-12 | Completed | Handed over on 12 Nov 2020. | 2020-11-20 | Completed | Sewage suction truck | 4 | 141 | Japan | 112158 | 24.9583 | 10.1756 | 0.63583 | 0.51609
327 | Goods | South | Ghat | WASH | Supply of Sewage Suction Trucks | Broadening | 519789.1 | 374792.9015 | 498924.1 | 359748.2346 | Completed | PO + Contract issuance done | 2019-07-18 | Substantial completion / handover done |  |  | 2020-07-14 | Completed | Handed over on 14 July 2020. | 2020-07-23 | Completed | Water Tanker | 4 | 10283 117 10159 | Germay(KfW) Germany(MOFA) EU | 112158 98720 | 24.9583 | 10.1756 | 0.7073 | 0.72105
328 | Goods | South | Ghat | WASH | Supply of Vehicles | Broadening | 297482.58 | 201029.2099 | 291837.57 | 197214.4927 | Completed | PO + Contract issuance done | 2019-07-25 | Substantial completion / handover done |  |  | 2019-12-18 | Completed | Delivered to Ghat as reported by Jamal on 14 Dec 2019. Handed over on 18 Dec 2019 | 2019-12-21 | Completed | Vehicle | 4 | 10480 | USAID | 112158 | 24.9583 | 10.1756 | 0.68422 | 0.67577
330 | Goods | South | Ghat | WASH | Supply of Pesticide Sprayer Trucks | Broadening | 139476 | 97158.6195 | 125627.33 | 87511.6719 | Completed | PO + Contract issuance done | 2019-07-23 | Substantial completion / handover done |  |  | 2020-03-18 | Completed | Handed over on 18 March 2020 | 2020-03-24 | Completed | Pesticide Sprayer | 4 | 10159 | EU | 112158 | 24.9752 | 10.1849 | 0.73889 | 0.6966
332 | Goods | South | Ghat | WASH | Supply of Generators | Broadening | 291580.53 | 172731.4441 | 291922.91 | 172934.269 | Completed | PO + Contract issuance done | 2019-07-10 | Substantial completion / handover done |  |  | 2020-03-16 | Completed | Handed over on 16 March 2020. 17 distributed to 17 water wells and 4 installed at Sewage Lifting Station in Ghat. | 2020-03-24 | Completed | Generator | 21 | 10283 | Germay(KfW) | 112158 | 24.97393889 24.96379722 24.95229444 24.97313056 24.96244444 24.93944444 24.94606389 24.88128333 24.89 24.91415278 25.0925 25.78479722 25.78435833 25.76058611 25.79748333 25.82989444 24.91415278 24.96423889 24.95082778 24.949925 24.97151944 | 10.07 10.18631389 10.040025 10.01979167 10.18905556 10.16656111 10.0769 10.186225 10.54 10.53444444 10.35299444 10.56254722 10.56076944 10.56488889 10.53606667 10.51439444 10.93833333 10.18750833 10.18582222 10.15880278 10.17559722 | 0.55097 | 0.5924
333 | Goods | South | Ghat | WASH | Supply of Sewage Pumps | Broadening | 86690.32 | 55961.6106 | 62438.58 | 40306.2706 | Completed | PO + Contract issuance done | 2019-10-17 | Substantial completion / handover done |  |  | 2020-06-14 | Completed | Handed over to Ghat Water Company on 14 June 2020. | 2020-06-29 | Completed | Sewage Pump | 8 | 10159 | EU | 112158 | 24.96423889 24.95082778 24.949925 24.97151944 | 10.18750833 10.18582222 10.15880278 10.17559722 | 0.72165 | 0.64553
334 | Goods | South | Ghat | WASH | Supply of Water Pumps | Broadening | 47505.1 | 27783.914 | 27054.4 | 15823.0826 | Completed | PO + Contract issuance done | 2019-10-16 | Substantial completion / handover done |  |  | 2020-06-14 | Completed | Handed over to Ghat Water & Wastewater Company on 14 June 2020. | 2020-06-30 | Completed | Water Pump | 4 | 10283 | Germay(KfW) | 112158 | 24.9731 | 10.1847 | 0.63782 | 0.58486
336 | Goods | South | Ghat | WASH | Supply of Sewage Pumps | Broadening | 188701.48 | 128763.8334 | 179296.38 | 122346.095 | Completed | PO + Contract issuance done | 2020-02-25 | Substantial completion / handover done |  |  | 2020-10-07 | Completed | Handed over on 7 Oct 2020. PO issued on 25 Feb. | 2020-10-16 | Completed | Water Pump | 17 | 141 151 10159 | Japan Gov't of Libya SUSC | 112158 | 24.97393889 24.96379722 24.95229444 24.97313056 24.96244444 24.93944444 24.94606389 24.88128333 24.89 24.91415278 25.0925 25.78479722 25.78435833 25.76058611 25.79748333 25.82989444 24.91415278 | 10.07 10.18631389 10.040025 10.01979167 10.18905556 10.16656111 10.0769 10.186225 10.54 10.53444444 10.35299444 10.56254722 10.56076944 10.56488889 10.53606667 10.51439444 10.93833333 | 0.65357 | 0.68237
337 | Goods | South | Ghat | Public Infrastructure and Services | Supply of Personal Protection Equipment | Broadening | 72742.61 | 41298.7263 | 71534.18 | 40612.655 | Completed | PO + Contract issuance done | 2020-06-02 | Substantial completion / handover done |  |  | 2021-04-11 | Completed | Handed over on 11 April 2021. PO issued on 2 June 2020. | 2021-04-14 | Completed | PPE | 1 | 112 10283 | France Germay(KfW) | 98720 112158 | 24.9731 | 10.1847 | 0.59412 | 0.56774
338 | Goods | South | Ghat | WASH | Supply of Generators | Broadening | 185040.5 | 97709.6259 | 49425.39 | 26098.8074 | Completed | PO + Contract issuance done | 2019-10-18 | Substantial completion / handover done |  |  | 2020-03-18 | Completed | Handed over on 18 March 2020 | 2020-03-24 | Completed | Generator | 4 | 10159 | EU | 112158 | 24.9731 | 10.1847 | 0.61911 | 0.52804
340 | Goods | South | Ghat | Energy | Provision of Power Cables | Broadening | 233438.75 | 117510.2966 | 233438.75 | 117510.2966 | Completed | PO + Contract issuance done | 2019-07-30 | Substantial completion / handover done |  |  | 2019-09-23 | Completed | Cables arrived to Ghat on 3 Sep 2019. Handed over on 23 Sep | 2019-09-30 | Completed | Cable | 4 | 10480 | USAID | 112158 | 24.9641 | 10.1858 | 0.68293 | 0.50339
341 | Goods | South | Ghat | WASH | Supply of Equipment | Broadening | 4182.33 | 2979.3837 | 4182.33 | 2979.3837 | Completed | PO + Contract issuance done | 2020-08-14 | Substantial completion / handover done |  |  | 2021-05-11 | Completed | Delivered to end users on 11 may 2021. Arrived to Ghat on same day. | 2021-05-11 | Completed | Mechanical equipment | 4 | 10283 11410 | Germay(KfW) UK (FCO) | 112158 98720 | 24.9731 | 10.1847 | 0.68326 | 0.71237
| Goods | South | Ghat | WASH | Supply of Sewage Pumps | Broadening | 60000 | 35203.4835 |  | 0 | BOQ development stage | [6 empty] | In Development |  |  | Further Funding | Water Pump | 1 | [5 empty] | 0.66316 | 0.58672
| Goods | South | Ghat | WASH | Supply of Pipes and Fittings | Broadening | 10000 | 6654.4725 |  | 0 | BOQ development stage | [6 empty] | In Development |  |  | Further Funding | WASH equipment | 1 | [5 empty] | 0.66478 | 0.66545
| Goods | South | Ghat | WASH | Supply of Pipes and Fittings | Broadening | 10000 | 5362.0593 |  | 0 | BOQ development stage | [6 empty] | In Development |  |  | Further Funding | WASH equipment | 1 | [5 empty] | 0.6655 | 0.53621
343 |  |  | Kufra | Unidentified |  | Broadening |  | 0 |  | 0 | [18 empty] | 0.62131 | 0.57894
| Works | South | Kufra | WASH | Borehole Drilling | Broadening | 190220 | 136946.6975 |  | 0 | Completed | PO + Contract issuance done |  |  | 2021-03-31 |  |  | With Procurement | Readvertised on 6 July 2022 with deadline on 18 July 2022. Readvertisement request with ISRF was submitted on 22 June 2022. This case was readvertised as per discussion with Engineering and Procurement Unit on 20 June 2022. As informed by Ali on 1 June 2022, Meeting was held with Site engineer and Compnay - planning to start the work on 15 June 2022. On 18 May 2022, Shembesh agreed to work on to provide update within one week with clear picture on when this can be started. Same contractor working for resilience and progress there is also very slow. Work not started yet as workers and some equipment are stuck in Tunis due to land route closure. Drillers are in site. Site handover done on 31 March 2021. Start of work expected within 5 days of handover. Contract issued on 6 Dec 2020. CAP approved on 27 Nov 2020. Contract sent for RR's signature on 30 Nov 2020. | 2022-07-07 | With Procurement | Borehole drilling | 2 | 10159 | SUSC | 112158 | 24.3261916666667 24.2199388888889 | 23.1863083333333 23.2964083333333 | 0.54943 | 0.71994
| Works | South | Kufra | Energy | Supply of transformers | Broadening | 120800 | 78366.3954 |  | 0 | Completed |  | 2021-01-29 |  | 2021-03-02 |  |  | In Development | Termination letter signed and shared on 24 Sep 2021. Qualified bidder signed the initial contract; however, they have requested to increase the contract's value up to an additional 75%. Site handover to contractor done on 2 March 2021. Contract issued on 29 Jan 2021. | 2021-09-27 | Further Funding | Transformers | 4 |  |  | 122619 |  |  | 0.60701 | 0.64873
| Works | South | Kufra | Public Infrastructure and Services | Rehabilitation of Public Infrastructure | Broadening | 629638 | 389741.5229 |  | 0 | Completed | [6 empty] | In Development | Will be evaluated with end users whether to go ahead or push this back to free some funds for Kufra. Technical documents submitted on 10 Sep 2019. E-req submitted, approval pending. | 2020-06-10 | Further Funding | Public Infrastructure | 1 | 10283 | Germay(KfW) |  |  |  | 0.69454 | 0.61899
| Works | South | Kufra | Energy | Supply and Installation of Solar Street Lights | Broadening | 777635 | 491795.6396 | 777635 | 491795.6396 | Completed | PO + Contract issuance done | 2020-07-13 | Substantial completion / handover done | 2020-10-12 |  | 2021-04-08 | Completed | Completed on 8 April 2021 with spare parts also handed over and signed. Official handover event remaining. Site is handed over to contactor on 13 Oct 2020 to start the work. | 2021-07-01 | Completed | Solar Street Light | 9.8 | 187 10159 | Norway SUSC | 112158 |  |  | 0.62087 | 0.63242
| Works | South | Kufra | Public Infrastructure and Services | Rehabilitation of Public Infrastructure | Broadening | 100000 | 53506.2274 |  | 0 | BOQ development stage | [6 empty] | In Development | As discussed with the municipality and community reps , these two play areas are based in both Tebu and Zwey Areas. SFL can proceed with this project | 2020-04-16 | Further Funding | Public Infrastructure | 1 | [5 empty] | 0.74091 | 0.53506
| Goods | South | Kufra | Public Infrastructure and Services | Supply of Fire Fighting Trucks | Broadening | 200000 | 105813.5355 |  | 0 | BOQ development stage | [6 empty] | In Development |  |  | Further Funding | Firetruck | 4 | [5 empty] | 0.63142 | 0.52907
| Goods | South | Kufra | Public Infrastructure and Services | Supply of Vehicles | Broadening | 156722.64 | 109731.3277 | 119628.77 | 83759.588 | Completed | PO + Contract issuance done | 2020-05-20 | Substantial completion / handover done |  |  | 2021-05-25 | Completed | End users don't know how to operate. PU exploring possiblities to resolve this. Delivered to end users on 25 May 2021. PO issued on 20 May. | 2021-07-07 | Completed | Mechanical equipment | 1 | 10283 10159 137 | Germany(KfW) SUSC Italy | 112158 122619 |  |  | 0.73497 | 0.70016
| Works | South | Kufra | Education | Rehabilitation of School | Broadening | 100000 | 59891.7111 |  | 0 | To be initiated | [6 empty] | In Development |  |  | Further Funding | School | 1 | [5 empty] | 0.62156 | 0.59892
| Works | South | Kufra | Education | Rehabilitation of School | Broadening | 120000 | 80002.6808 |  | 0 | To be initiated | [6 empty] | In Development |  |  | Further Funding | School | 1 | [5 empty] | 0.71503 | 0.66669
|  |  | Misurata |  |  | Broadening |  | 0 |  | 0 | [18 empty] | 0.71338 | 0.53082
| Goods | West | Misurata | WASH | Supply of Sewage Suction Trucks | Broadening | 182905.1 | 115528.7859 | 176065.2633 | 111208.5235 | Completed | PO + Contract issuance done | 2020-12-29 | Substantial completion / handover done |  |  | 2022-03-22 | Completed | Handed over on 22 March 2022. Arrived in Misurata port on 27 Feb 2022. Produced as informed on 24 November 2021. PO issued on 29 Dec 2020. | 2022-03-24 | Completed | Sewage suction truck | 1 | 151 | Gov't of Libya | 112158 |  |  | 0.53119 | 0.63163
| Goods | West | Misurata | WASH | Supply of Water Tankers | Broadening | 211255.1 | 135664.3858 | 171965.2633 | 110433.1296 | Completed | PO + Contract issuance done | 2020-12-29 | Substantial completion / handover done |  |  | 2022-03-22 | Completed | Handed over on 22 March 2022. Arrived in Misurata port on 27 Feb 2022. Produced as informed on 24 November 2021. PO issued on 29 Dec 2020. | 2022-03-24 | Completed | Water Tanker | 2 | 151 | Gov't of Libya | 112158 |  |  | 0.65265 | 0.64218
| Goods | West | Misurata | WASH | Supply of Sewage Pumps | Broadening | 195851.44 | 144267.9744 | 125735.2333 | 92619.0148 | Completed | PO + Contract issuance done | 2020-12-29 | Substantial completion / handover done |  |  | 2021-08-29 | Completed | Handed over on 29 August 2021. PO issued on 29 Dec 2020. Technical documents submitted on 25 Nov 2020 | 2021-04-14 | Completed | Sewage suction truck | 1 | 151 182 | Gov't of Libya Netherlands | 112158 |  |  | 0.55559 | 0.73662
344 |  | South | Sebha |  |  | Deepening |  | 0 |  | 0 | [18 empty] | 0.5432 | 0.71019
345 | Works | South | Sebha | Education | Rehabilitation of School | Deepening | 279802.72 | 170476.0702 | 278828.582 | 169882.5548 | Completed | PO + Contract issuance done | 2019-12-12 | Substantial completion / handover done | 2020-01-08 |  | 2020-08-27 | Completed | Handed over on 27 August 2020. Al-Akaber school is a center for the education of older women who did not have the opportunity to learn when they were young | 2020-09-14 | Completed | School | 2 | 10283 10159 | Germay(KfW) EU | 112158 | 27.0283972222222 27.0254333333333 | 14.4411833333333 14.4364833333333 | 0.53751 | 0.60927
346 | Works | South | Sebha | Education | Rehabilitation of School | Deepening | 240653.87 | 171275.0155 | 240564.977 | 171211.7498 | Completed | PO + Contract issuance done | 2019-10-17 | Substantial completion / handover done | 2019-10-31 |  | 2020-05-11 | Completed | Substantial handover document signed backdated and shared on 11 Feb 2021 with handover date as 11 May 2020. Unofficial handover (taking over) done for student's use on 5 May. | 2021-02-12 | Completed | School | 2 | 10159 | EU | 112158 | 27.0249 27.0266333333333 | 14.4323222222222 14.4330194444444 | 0.62435 | 0.71171
347 | Works | South | Sebha | Public Infrastructure and Services | Rehabilitation of Public Building | Deepening | 189221.88 | 120593.649 | 187721.412 | 119637.3806 | Completed | PO + Contract issuance done | 2019-11-14 | Substantial completion / handover done |  | 2019-11-12 | 2021-07-05 | Completed | Handed over on 5 July 2021. As of 15 July 2021, minor defects rectification in progress and will be ready for use after Eid 24-25 July 2021. Contract Issued on 14 Nov 2019. | 2021-07-16 | Completed | Public Infrastructure | 1 | 141 | Japan | 112158 | 27.0461 | 14.4204 | 0.61308 | 0.63731
348 | Works | South | Sebha | Education | Rehabilitation of School | Deepening | 118905.54 | 88464.4522 |  | 0 | Completed | PO + Contract issuance done | 2022-08-10 | Work progress 0 - 25% | 2022-08-21 |  |  | Contract Issued | 12.5% completed. Site handed over on 21 August 2022. Contract issued on 10 August 2022. Pre-bid site visit conducted on 26 Jan 2022. Request submitted through PROMPT on 28 December 2021. | 2022-09-11 | Contract Issued | School | 2 | 182 | Netherlands | 112158 | 27.0360833333333 27.0372916666667 | 14.411175 14.4127972222222 | 0.59742 | 0.74399
349 | Works | South | Sebha | Education | Rehabilitation of School | Deepening | 183306.43 | 93331.9589 | 183081.46 | 93217.4136 | Completed | PO + Contract issuance done | 2020-02-14 | Substantial completion / handover done | 2020-09-01 | 2020-09-08 | 2021-01-21 | Completed | Completed and handed over. Al-Wahda school handed over on 21 Jan 2021. Al-Khansa school handed over on 31 Dec 2020. | 2021-01-22 | Completed | School | 2 | 141 717 | Japan C/S ROK | 112158 | 27.04135 27.04985 | 14.430925 14.4158777777778 | 0.51309 | 0.50916
350 | Works | South | Sebha | Education | Rehabilitation of School | Deepening | 81731.14 | 42699.4298 | 81702.04 | 42684.2269 | Completed | PO + Contract issuance done | 2020-03-27 | Substantial completion / handover done | 2020-09-29 |  | 2021-05-05 | Completed | Completed and handed over on 5 May 2021. Site handed over on 29 Sep 2020. | 2021-05-11 | Completed | School | 1 | 10283 | Germay(KfW) | 112158 | 26.4386 | 14.2736 | 0.62643 | 0.52244
351 | Works | South | Sebha | Health | Rehabilitation of Clinic | Deepening | 141339.06 | 79220.1052 |  | 0 | Completed | PO + Contract issuance done | 2022-01-20 | Work progress over 75% | 2022-02-01 |  |  | Contract Issued | 85% completed. As of 21 July 2022, awaiting revised time schedule from contractor. Site handed over on 1 Feb 2022. Contract issued on 20 Jan 2022. Cost (additional US$ 14,719) amendment and time extension (30 days) request submitted to PU on 29 April 2022. | 2022-09-11 | Contract Issued | Clinic | 1 | 10159 137 | SUSC Italy | 122619 | 27.0659 | 14.4197 | 0.51598 | 0.5605
352 | Works | South | Sebha | Health | Rehabilitation of Clinic | Deepening | 233714.37 | 172061.0102 | 233713.782 | 172060.5773 | Completed | PO + Contract issuance done | 2020-01-12 | Substantial completion / handover done | 2020-01-20 |  | 2020-08-24 | Completed | Handed over on 24 August 2020. Located in Al-Tayyari neighbourhood which is one of the most marginalized neighborhoods in the city where many old huts and slums still surround the clinic. | 2020-09-14 | Completed | Clinic | 1 | 182 10159 | Netherlands EU | 112158 | 27.0135 | 14.4408 | 0.57677 | 0.7362
353 | Works | South | Sebha | Health | Rehabilitation of Clinic | Deepening | 42769.55 | 30876.7484 | 42738.01 | 30853.9786 | Completed | PO + Contract issuance done | 2019-12-05 | Substantial completion / handover done | 2020-01-02 |  | 2020-05-03 | Completed | Works completed. Handed over on 3 May 2020. Handover doc signed on 22 Dec 2020. | 2020-12-29 | Completed | Clinic | 1 | 10159 | EU | 112158 | 27.0361 | 14.416 | 0.59793 | 0.72193
354 | Works | South | Sebha | Health | Rehabilitation of Clinic | Deepening | 99876.22 | 52846.9318 | 99841.91 | 52828.7775 | Completed | PO + Contract issuance done | 2019-12-06 | Substantial completion / handover done | 2020-01-19 | 2020-01-26 | 2021-01-10 | Completed | Completed and handed over on 10 Jan 2021. Site handed over on 19 January 2020. | 2021-01-25 | Completed | Clinic | 1 | 141 | Japan | 112158 | 27.0421 | 14.4037 | 0.68494 | 0.52912
355 | Works | South | Sebha | Health | Rehabilitation of Clinic | Deepening | 80539.67 | 48509.4381 | 82210.96 | 49516.0643 | Completed | PO + Contract issuance done | 2020-06-26 | Substantial completion / handover done | 2020-09-06 | 2020-09-10 | 2021-01-05 | Completed | The contract was closed. in conversation with PU, it was decided to open a small contract for the additional work. Total completed (Block B) and handed over on 5 Jan 2021. Block A Completed and handed over on 29 Oct 2020. Site handed over to contractor on 6 September 2020. Contract issued on 26 June 2020. | 2021-02-01 | Completed | Clinic | 1 | 10283 | Germay(KfW) | 112158 | 27.0479444444444 27.0408166666667 | 14.4284694444444 14.4339111111111 | 0.6454 | 0.6023
356 | Goods | South | Sebha | Health | Supply of Ambulances | Deepening | 66211.83 | 44323.0031 | 46402.01 | 31062.069 | Completed | PO + Contract issuance done | 2019-09-23 | Substantial completion / handover done |  |  | 2020-03-12 | Completed | Handed over on 12 March 2020. | 2020-03-15 | Completed | Ambulance | 1 | 717 10159 | C/S ROK SUSC | 112158 | 26.4395 | 14.2745 | 0.53993 | 0.66941
357 | Works | South | Sebha | Health | Rehabilitation of Clinic | Deepening | 51673.97 | 37043.1854 | 49931.22 | 35793.8714 | Completed | PO + Contract issuance done | 2019-12-12 | Substantial completion / handover done | 2019-12-25 | 2020-01-02 | 2021-05-02 | Completed | Completed and Handed over on 2 May 2021. Additional works also completed as of 8 Apr 2021. Site handover for additional works done on 18 Jan 2021. Issued on 12 Dec 2019. Site handed over on 25 Dec 2019. | 2021-05-11 | Completed | Clinic | 1 | 10283 112 | Germay(KfW) France | 98720 112158 | 26.8786 | 14.4271 | 0.57861 | 0.71686
358 | Goods | South | Sebha | WASH | Supply of Sewage Suction Trucks | Deepening | 632106.45 | 322136.184 | 516393.7 | 263166.2688 | Completed | PO + Contract issuance done | 2019-07-04 | Substantial completion / handover done |  |  | 2020-07-22 | Completed | Trucks delivered to Sebha and physically handed over on 22 Oct 2020. Documents were already signed back in 22 July along with 3 pumps. | 2020-11-16 | Completed | Sewage suction truck | 3 | 10283 10159 | Germay(KfW) SUSC | 112158 | 27.0382 | 14.4317 | 0.65222 | 0.50962
359 | Goods | South | Sebha | WASH | Supply of Sewage Pumps | Deepening | 240964.85 | 152954.5484 | 165781.67 | 105231.3666 | Completed | PO + Contract issuance done | 2019-10-01 | Substantial completion / handover done |  |  | 2020-07-22 | Completed | Handed over to General Water and Sanitation company on 22 July 2020. | 2020-07-31 | Completed | Sewage Pump | 3 | 10159 10283 | EU Germany (KfW) | 112158 | 27.0382 | 14.4317 | 0.61413 | 0.63476
361 | Works | South | Sebha | WASH | Supply of Generators | Deepening | 61995.1 | 34072.903 | 61974.29 | 34061.4657 | Completed | PO + Contract issuance done | 2020-06-21 | Substantial completion / handover done | 2020-09-03 | 2020-09-18 | 2020-12-20 | Completed | Completed and handed over on 20 Dec 2020. Contract amended to include additional works on 3 Nov 2020. The extra work was added to the BoQ to accommodate Tebu access to the water system to avoid any conflict in the village. Site handed over on 3 Sep 2020. (the wells are located in Godwah village 70 km south from Sebha). Contract issued on 21 June 2020. | 2020-12-24 | Completed | Public Infrastructure | 1 | 10283 | Germay(KfW) | 112158 | refer to list | refer to list | 0.54351 | 0.54961
362 | Works | South | Sebha | Energy | Supply and Installation of Solar Street Lights | Deepening | 3349006.33 | 1985669.6754 | 3349006.33 | 1985669.6754 | Completed | PO + Contract issuance done | 2020-03-03 | Substantial completion / handover done | 2020-12-03 | 2020-12-10 | 2021-12-23 | Completed | Sector 13,14,15 handed over on 23 Dec 2021. Sectors 4 & 5 handed over by 3 May 2021. Sector 1,2 & 3 (284 out of 1070 poles) handed over on 30 March 2021 Site handed over on 3 Dec 2020. Access to site from 10 Dec 2020. PO issued with GPU CREE Copenhagen on 3 March 2020. | 2021-12-30 | Completed | Solar Street Light | 14 | 10283 | Germay(KfW) | 112158 | refer to list | refer to list | 0.63587 | 0.59291
364 | Works | South | Sebha | Public Infrastructure and Services | Rehabilitation of Public Infrastructure | Deepening | 769682.5 | 536641.9109 |  | 0 | Completed |  | 2020-04-11 |  |  |  |  | In Development | As informed by PU on 8 Oct 2020, Contractor informed its inability to implement due to change of market for materials and high cost for tranportation to import from abroad in light of covid-19 as well as curfews and lock downs. Now prices will be re-assessed and new estimates prepared. Evaluation criteria will be adjusted accordingly. ITB invitation may be extended to qualified companies only. Contract issued on 11 April 2020. | 2021-01-29 | Further Funding | Public Infrastructure | 1 | 10283 | Germay(KfW) |  | 27.0266 | 14.4575 | 0.60196 | 0.69723
365 | Works | South | Sebha | Public Infrastructure and Services | Rehabilitation of Public Building | Deepening | 118726.62 | 78290.2734 | 34569.83 | 22795.9108 | Completed | PO + Contract issuance done | 2021-05-12 | Work progress over 75% | 2021-09-15 | 2021-10-25 |  | Contract Issued | 82% completed. Site handed over on 15 Sep 2021. Site handover was delayed as municipality was working to ensure that site is registered with the Real Estate Registration Authority so that there's no dispute over it. Contract issued on 12 May 2021.- | 2022-09-11 | Contract Issued | Public Infrastructure | 1 | 10159 | SUSC | 122619 | 27.0086 | 14.4385 | 0.69782 | 0.65942
366 | Goods | South | Sebha | Energy | Provision of Power Cables | Deepening | 118919.375 | 72812.1548 | 118919.375 | 72812.1548 | Completed | PO + Contract issuance done | 2019-07-30 | Substantial completion / handover done |  |  | 2019-09-08 | Completed | Cables arrived to Sebha Airport on 2 Sep 2019. Handed over on 8 sep 2019 | 2019-09-19 | Completed | Cable | 2 | 10480 | USAID | 112158 | 27.0025 | 14.4613 | 0.5861 | 0.61228
367 |  |  | Sirt | Unidentified |  | Deepening |  | 0 |  | 0 | To be initiated | [17 empty] | 0.72927 | 0.6179
| Works | West | Sirt | Education | Rehabilitation of School | Deepening | 304592.6 | 201438.7187 | 267422.9 | 176856.9766 | Completed | PO + Contract issuance done | 2020-04-15 | Substantial completion / handover done | 2020-04-26 |  | 2020-10-28 | Completed | Competed and handed over on 28 Oct 2020. Site handover to contractor on 26 April 2020. Contract issued on 15 April 2020. This project was visited by Gerardo who promised it will receive the full attention and support of UNDP. | 2020-11-02 | Completed | School | 1 | 10283 | Germay(KfW) | 112158 | 31.1999 | 16.6083 | 0.61253 | 0.66134
| Works | West | Sirt | Education | Rehabilitation of School | Deepening | 149299 | 97852.29 |  | 0 | Completed |  | 2020-10-23 |  |  |  |  | Cancelled | Site handover was blocked by another contractor, who is reported to have been contracted initially back in 2013 to Rehabilitate this school. Khalifa, in coordination with authorities, identified Al-Manara school as a replacement. A letter stating the same was shared by Khalifa on 29 Dec 2020. Contract for Omar Ibn Al-Alas was issued on 23 Oct 2020. | 2020-12-29 | Cancelled | School | 1 | 717 | C/S ROK |  | 31.2072 | 16.6819 | 0.65621 | 0.65541
| Works | West | Sirt | Education | Rehabilitation of School | Deepening | 150653 | 97582.5147 | 135587.7 | 87824.2632 | Completed | PO + Contract issuance done | 2021-08-18 | Substantial completion / handover done |  |  | 2022-02-25 | Completed | Completed and handed over on 25 Feb 2022. Contract issued on 18 August 2021. Identified as a replacement for Omar Ibn Al-Alas School, as per letter shared by Khalifa on 29 Dec 2020. | 2022-04-19 | Completed | School | 1 | 10159 | SUSC | 122619 | 31.2094 | 16.5861 | 0.50343 | 0.64773
| Works | West | Sirt | Education | Rehabilitation of School | Deepening | 173376 | 120496.6297 | 173376 | 120496.6297 | Completed | PO + Contract issuance done | 2020-11-06 | Substantial completion / handover done | 2020-11-16 |  | 2021-04-15 | Completed | Completed and handed over on 15 April 2021. Contract issued on 4 Nov 2020. | 2021-06-21 | Completed | School | 1 | 10159 | SUSC | 122619 | 31.2081 | 16.566 | 0.62946 | 0.695
| Works | West | Sirt | Education | Rehabilitation of School | Non-SFL | 145824 | 91927.6044 | 145824 | 91927.6044 | Completed | PO + Contract issuance done | 2020-10-23 | Substantial completion / handover done | 2020-11-16 |  | 2020-12-31 | Completed | Completed and handed over on 31 Dec 2020. Site handed over on 16 Nov 2020. Contract issued on 23 Oct 2020. | 2020-12-31 | Non SFL | School | 1 |  | PBF | 124052 | 31.1504 | 16.9483 | 0.57092 | 0.6304
| Works | West | Sirt | Education | Rehabilitation of School | Deepening | 900000 | 588620.0048 |  | 0 | To be initiated | [6 empty] | In Development | With Project |  | Further Funding | School | 1 | [5 empty] | 0.50196 | 0.65402
| Goods | West | Sirt | Health | Supply of Generators | Deepening | 108379.16 | 81271.1602 |  | 0 | Completed |  | 2022-04-06 |  |  |  |  | Contract Issued | PO issued on 6 April 2022. Request submitted through PROMPT on 29 December 2021. | 2022-04-08 | Contract Issued | Generator | 2 | 10159 | SUSC | 122619 112158 |  |  | 0.55179 | 0.74988
| Goods | West | Sirt | WASH | Supply of Generators | Deepening | 109250 | 66857.5586 |  | 0 | Completed | [6 empty] | In Development | Email sent to PU to drop this request on 22 March 2022. PFI quote of US$ 430,500 was much higher than initial estimate of US$ 95,000, therefore removed. Quote request in process. Request submitted through PROMPT on 29 December 2021. | 2022-03-28 | Further Funding | Mechanical equipment | 1 | [5 empty] | 0.69536 | 0.61197
| Goods | West | Sirt | WASH | Supply of Generators | Deepening | 162568.74 | 102899.6752 |  | 0 | Completed |  | 2022-04-06 |  |  |  |  | Contract Issued | PO issued on 6 April 2022. Request submitted through PROMPT on 29 December 2021. | 2022-04-08 | Contract Issued | Generator | 3 | 10159 | SUSC | 122619 112158 |  |  | 0.68992 | 0.63296
| Goods | West | Sirt | WASH | Supply of Water Pumps | Deepening | 66470 | 38263.7573 |  | 0 | Completed | PO + Contract issuance done | 2022-07-21 |  |  |  |  | Contract Issued | PO issued on 21 July 2022. CAP approved on 23 June 2022. Sumbitted to CAP on 15 June 2022. Evaluation done by Anis Karoui. Under technical evaluation. Anis requested clarification from end users on 3 topics on 24 Feb 2022. Official response from end users related to enquiries were shared by Khalifa on 1 March 2022. Request submitted through PROMPT on 29 December 2021. | 2022-07-26 | With Procurement | Water Pump | 4 | 717 | C/S ROK | 112158 |  |  | 0.55515 | 0.57565
| Goods | West | Sirt | Public Infrastructure and Services | Supply of Generators | Deepening | 174676.17 | 88872.901 |  | 0 | Completed |  | 2022-04-06 |  |  |  |  | Contract Issued | On 21 June 2022, WFP (Christina) informed that the equipment is out of stock and new delivery lead time will be 8-12 months. Algaddafi (coordinator) agreed with the provided delivery timeline, which was communicated to PU on 23 June 2022. PO issued on 6 April 2022. Request submitted through PROMPT on 23 December 2021. | 2022-06-23 | Contract Issued | Vehicle | 1 | 232 | Switzerland | 112158 |  |  | 0.63838 | 0.50879
| Goods | West | Sirt | Public Infrastructure and Services | Supply of Generators | Deepening | 123386.5 | 82658.7333 |  | 0 | Completed |  | 2022-04-06 |  |  |  |  | Contract Issued | PO issued on 6 April 2022. Request submitted through PROMPT on 23 December 2021. | 2022-04-08 | Contract Issued | Pesticide Sprayer | 2 | 187 | Norway | 98720 112158 |  |  | 0.53726 | 0.66992
| Goods | West | Sirt | Public Infrastructure and Services | Supply of Generators | Deepening | 150000 | 104407.6817 |  | 0 | BOQ development stage | [6 empty] | In Development | BOQ completed. To be uploaded to PROMPT soon | 2020-06-01 | Further Funding | Vehicle | 1 | [5 empty] | 0.5571 | 0.69605
| Works | West | Sirt | Public Infrastructure and Services | Rehabilitation of Public Building | Deepening | 62836 | 45237.432 | 62791 | 45205.0352 | Completed | PO + Contract issuance done | 2021-04-17 | Substantial completion / handover done | 2021-04-22 | 2021-04-29 | 2021-09-14 | Completed | Completed and Handed over on 14 September 2021. Site handed over on 22 April 2021. Contract issued on 17 April 2021. | 2021-09-16 | Completed | Public Infrastructure | 1 | 10159 | SUSC | 122619 | 31.2106 | 16.5867 | 0.59995 | 0.71993
| Goods | West | Sirt | Health | Supply of Generators | Deepening | 162047.06 | 119327.8928 |  | 0 | Completed | [6 empty] | In Development | This project is in response to WHO's request to support Sirt Health Emergency condition. Put under priority 2. | 2021-02-15 | Further Funding | Generator | 1 | [5 empty] | 0.59983 | 0.73638
| Works | West | Sirt | Education | Rehabilitation of School | Deepening | 250000 | 137591.9731 |  | 0 | Completed | PO + Contract issuance done | 2022-09-03 | Site Handover done | 2022-09-04 |  |  | Contract Issued | Site handed over on 4 September 2022. Contract signed on 3 September 2022. Readvertised on 13 July 2022 with deadline on 3 August 2022. On 12 July 2022, BOQ was confirmed by Ali and readvertisement request officially submitted to PU with all required documents. Under evaluation. Request submitted through PROMPT on 23 December 2021. | 2022-09-07 | Contract Issued | School | 1 | 141 | Japan | 127766 | 31.1952 | 16.5767 | 0.6211 | 0.55037
| Goods | West | Sirt | Health | Supply of Ambulances | Deepening | 120369.04 | 71745.3018 |  | 0 | Completed |  | 2022-04-06 |  |  |  |  | Contract Issued | As informed by Shohrukh on 4 August 2022, Ambulance shall be ready soon. PO issued on 6 April 2022. Request submitted through PROMPT on 23 December 2021. | 2022-08-04 | Contract Issued | Ambulance | 2 | 141 | Japan | 127766 112158 |  |  | 0.63543 | 0.59604
368 |  |  | Tawergha | Unidentified |  | Broadening |  | 0 |  | 0 | To be initiated | [17 empty] | 0.68081 | 0.73204
| Works | West | Tawergha | Education | Rehabilitation of School | Broadening |  | 0 |  | 0 | Completed | [6 empty] | Cancelled | Technical documents submitted on 13 September 2019 | 2019-09-13 | Cancelled |  |  | 117 | Germany(MOFA) |  |  |  | 0.63778 | 0.59983
| Goods | West | Tawergha | Health | Supply of Ambulances | Broadening | 60000 | 39020.1104 |  | 0 | Completed | PO + Contract issuance done | 2018-12-01 | Substantial completion / handover done |  |  | 2019-08-28 | Completed | Handed over on 28 August 2019 | 2020-02-17 | Completed | Ambulance | 1 |  |  | 112158 |  |  | 0.68809 | 0.65034
| Works | West | Tawergha | Energy | Supply and Installation of Solar Street Lights | Broadening | 107715.71 | 70864.4594 | 107715.71 | 70864.4594 | Completed | PO + Contract issuance done | 2019-09-03 | Substantial completion / handover done |  |  | 2020-01-23 | Completed | Substantial handover on 23 Jan 2020. | 2020-02-26 | Completed | Solar Street Light | 1.5 | 10159 10283 | EU Germay(KfW) | 112158 |  |  | 0.59149 | 0.65788
| Works | West | Tawergha | Education | Rehabilitation of School | Broadening | 107085 | 71058.6164 | 107085 | 71058.6164 | Completed | PO + Contract issuance done | 2020-01-10 | Substantial completion / handover done | 2020-05-12 |  | 2020-07-07 | Completed | Handed over on 7 July 2020. Before suspended internally. Contract issued on 10 Jan 2020. | 2020-07-09 | Completed | School | 1 | 10283 | Germay(KfW) | 112158 |  |  | 0.72376 | 0.66357
| Works | West | Tawergha | Education | Rehabilitation of School | Broadening | 98098.1 | 49876.2243 | 98082.37 | 49868.2267 | Completed | PO + Contract issuance done | 2020-01-30 | Substantial completion / handover done | 2020-05-12 |  | 2020-07-27 | Completed | Substantial handover done on 27 July 2020. Site handed over to contractor on 12 May 2020. Before this suspended internally. Issed on 30 Jan 2020 | 2020-07-28 | Completed | School | 1 | 10283 | Germay(KfW) | 112158 |  |  | 0.55178 | 0.50843
| Works | West | Tawergha | Education | Rehabilitation of School | Broadening | 92414 | 51601.3461 | 92380 | 51582.3615 | Completed | PO + Contract issuance done | 2020-01-21 | Substantial completion / handover done | 2020-05-12 | 2020-05-16 | 2020-09-02 | Completed | Handed over on 2 September 2020. Site handed over to contractor on 12 May 2020. Before this suspended internally. Issed on 21 Jan 2020 | 2020-09-03 | Completed | School | 1 | 10283 | Germay(KfW) | 112158 |  |  | 0.67289 | 0.55837
| Goods | West | Tawergha | Public Infrastructure and Services | Supply of Computer Equipment | Broadening | 40530.85 | 23771.7569 | 40530.85 | 23771.7569 | Completed | PO + Contract issuance done | 2020-04-29 | Substantial completion / handover done |  |  | 2020-10-31 | Completed | On 23 May 2022, Letter received from Tawergha Municipality that they've received all equipment as agreed. Electricity is there so end users were asking for generators in place of Solar panels. Solar panels needs readvertisement as of 26 March 2021. Solar Panels on advertisement with deadline of 9 Nov 2020. VSAT completed by 31 Oct 2020. Furnitures delivered on 21 September 2020 and to be installed in Lab shortly. Computers handed over on 21 May 2020. Solar Panels - the mayor has requested to supply generator instead of the solar panels, request is under review by the project. | 2022-05-24 | Completed | IT equipment | 1 | 187 10283 | Norway Germany(KfW) Netherlands | 112158 |  |  | 0.63082 | 0.58651
| Works | West | Tawergha | Public Infrastructure and Services | Rehabilitation of Public Building | Broadening | 8499.9 | 5900.5734 | 8395.5 | 5828.0996 | Completed | PO + Contract issuance done | 2020-08-26 | Substantial completion / handover done | 2020-09-02 | 2020-09-02 | 2020-09-13 | Completed | Handed over on 13 Sep 2020. Site handed over to contractor on 2 September 2020. Contract issued on 26 August 2020. Tawergha computer lab project divided into equipment delivery and rehabiliation separately | 2020-09-29 | Completed | Public Infrastructure | 1 | 10283 | Germay(KfW) | 112158 |  |  | 0.67501 | 0.69419
| Works | West | Tawergha | Energy | Supply and Installation of Solar Street Lights | Broadening | 466125 | 286228.1363 | 466125 | 286228.1363 | Completed | PO + Contract issuance done | 2020-11-16 | Substantial completion / handover done | 2020-12-17 |  | 2021-08-23 | Completed | Handed over on 23 August 2021. Fabrication of foundation will start by 1 March. Site handed over on 17 Dec 2020. PO issued on 16 Nov 2020. | 2021-09-01 | Completed | Solar Street Light | 3.5 | 10159 | SUSC | 122619 |  |  | 0.5146 | 0.61406
| Goods | West | Tawergha | WASH | Supply of Sewage Suction Trucks | Broadening | 169894.9 | 112989.8825 | 165582 | 110121.5559 | Completed | PO + Contract issuance done | 2020-12-31 | Substantial completion / handover done |  |  | 2022-03-22 | Completed | Handed over on 22 March 2022. Under customs clearance process as of 15 March 2022. Diplomatic exemption received on 10 March 2022. Arrived in Misurata port on 27 Feb 2022. Produced as informed on 24 November 2021. PO issued on 31 Dec 2020. Technical document submitted on 25 Nov 2020. Revised e-req shared on 6 Dec 2020. | 2022-03-24 | Completed | Sewage suction truck | 1 | 151 | Gov't of Libya | 112158 |  |  | 0.69552 | 0.66506
369 | Goods | West | Tawergha | WASH | Supply of Water Tankers | Broadening | 112144.9 | 65857.6413 | 92382 | 54251.7816 | Completed | PO + Contract issuance done | 2020-12-31 | Substantial completion / handover done |  |  | 2022-03-22 | Completed | Handed over on 22 March 2022. Under customs clearance process as of 15 March 2022. Diplomatic exemption received on 10 March 2022. Arrived in Misurata port on 27 Feb 2022. Produced as informed on 24 November 2021. PO issued on 31 Dec 2020. Technical document submitted on 25 Nov 2020. Revised e-req shared on 6 Dec 2020. | 2022-03-24 | Completed | Water Tanker | 1 | 151 | Gov't of Libya | 112158 |  |  | 0.73595 | 0.58725
| Goods | West | Tawergha | WASH | Supply of Pesticide Sprayer Trucks | Broadening | 112353.64 | 64524.1107 | 94566.52 | 54309.0603 | Completed | PO + Contract issuance done | 2020-12-31 | Substantial completion / handover done |  |  | 2021-09-08 | Completed | Handed over on 8 September 2021. Handover Status unconfirmed. As communicated by Shohrukh on 18 July, ETA Misurata 20 August 2021. Shipment started from Belgium on 15 July 2021. Technical document submitted on 25 Nov 2020. Revised e-req shared on 6 Dec 2020. | 2021-09-13 | Completed | Pesticide Sprayer | 2 | 151 | Gov't of Libya | 112158 |  |  | 0.65672 | 0.57429
| Works | West | Tawergha | Health | Rehabilitation of Clinic | Broadening | 249400 | 138433.2597 |  | 0 | Completed | PO + Contract issuance done | 2022-01-22 | Work progress 50% - 75% | 2022-02-03 |  |  | Contract Issued | 65% compelted. Site handover done on 3 Feb 2022. Contract issued on 22 Jan 2022. | 2022-06-01 | Contract Issued | Clinic | 1 | 10159 12 | SUSC RFF | 122619 125873 |  |  | 0.69038 | 0.55507
| Works | West | Tawergha | Public Infrastructure and Services | Cleaning Works and Removal of War Remnants | Broadening | 135200 | 98419.046 | 135200 | 98419.046 | Completed | PO + Contract issuance done | 2021-05-03 | Substantial completion / handover done | 2021-06-09 |  | 2021-08-25 | Completed | Handover for both done on 25 August 2021. Allam neighbourhood completed on 4 July 2021. Site handed over to contractor on 9 June 2021. LIBMAC issued clearance letter on 3 June 2021. Contract issued on 3 May 2021. As of 6 May 2021, site handover postponed until receipt of Mine Clearance Certificate from LIBMAC | 2021-09-01 | Completed | ERW removal | 1 | 11410 | UK (FCO) | 112158 |  |  | 0.74116 | 0.72795
| Works | West | Tawergha | WASH | Supply of Water Pumps | Broadening | 414299.64 | 218721.2029 |  | 0 | Completed | PO + Contract issuance done | 2022-06-14 | Site Handover done | 2022-06-22 |  |  | Contract Issued | Site handed over to contractor on 22 June 2022. Contract issued on 14 June 2022. Submitted to RACP for review on 2 June 2022. Request submitted through PROMPT on 27 December 2021. | 2022-06-23 | Contract Issued | WASH equipment | 1 | 151 137 | Gov't of Libya Italy | 112158 |  |  | 0.72354 | 0.52793
370 |  |  | Tripoli | Unidentified |  | Deepening |  | 0 |  | 0 | [18 empty] | 0.71149 | 0.72185
| Goods | West | Tripoli | Solid Waste Management | Supply of Refuse Trailers | Deepening | 2866691.48 | 1715388.5235 | 2579201.51 | 1543358.5026 | Completed | PO + Contract issuance done | 2019-07-25 | Substantial completion / handover done |  |  | 2020-04-06 | Completed | Defect reported in 2 trailers on Aug 2 2020. PU checking with LTA holder regarding warranty and truck malfunction as of 6 Oct 2020. Handed over on 6 April 2020. Refuse collectors arrived to Tripoli on 27 March 2020. Tractor heads also delivered to Tripoli in Abu Salim, Ein Zara, Souq Al-Gomma, Tajoura and Tripoli Centre municipalities. | 2020-10-12 | Completed | Gargabe trailer | 25 | 10283 141 10480 10159 | Germay(KfW) Japan USAID EU | 112158 |  |  | 0.74657 | 0.59839
| Goods | West | Tripoli | Solid Waste Management | Supply of Refuse Trailers | Deepening | 961619.65 | 566802.2641 | 883081.21 | 520509.7766 | Completed | PO + Contract issuance done | 2019-11-21 | Substantial completion / handover done |  |  | 2020-07-01 | Completed | Handed over on 1st week of July 2020. 8 refuse collectors delivered on 17 May. 2 tractor heads delivered to Tripoli Crisis Committee as reported by Ala on 8 June. Hay Al-Andalus and Ben Gashir municipalities. | 2020-07-15 | Completed | Gargabe trailer | 10 | 10159 10283 | EU Germay(KfW) | 112158 |  |  | 0.57396 | 0.58942
| Works | West | Tripoli | Public Infrastructure and Services | Supply & Installation of Eco-LED Street light | Deepening | 347200 | 227413.8948 |  | 0 | Completed | PO + Contract issuance done | 2021-11-12 |  |  |  |  | Contract Issued | On 3 June 2022, Yuka informed Shohrukh about cancelling this contract and sought his advise for next steps. On 20 June 2022, Shohrukh advised to get formal communication from end user to cancel the contract. Yuka asked Saeid for the letter on the same day. As communicated by Saeid Zekry on 27 May 2022, the contractor was informally informed by him on 24 May 2022 that the contract will be cancelled. Based on agreement in internal meeting of 18 May 2022, Yuka asked Saeid Zekry and Ala Dhiem on 20 May 2022 to communicate to the contractor to explain the situation to cancel the contract. Once this is done, Yuka will ask procurement officially. Internal issues related to GECOL and Ministry has delayed start of work. Saeid working to resolve this with respective counterparts. Final meetings planned to be concluded in March and work likely to start from mid April 2022. Contract issued on 12 November 2021. | 2022-06-23 | Contract Issued | LED Light | 29.4 | 141 | Japan | 127766 |  |  | 0.62232 | 0.65499
166 | Works | West | Tripoli | Public Infrastructure and Services | Rehabilitation of Public Infrastructure | Deepening | 873141 | 651825.1801 | 484751.68 | 361881.2438 | Completed | PO + Contract issuance done | 2021-06-20 | Work progress over 75% | 2021-09-29 |  |  | Contract Issued | Signed Contract Amendment shared on 12 July by PU. Request for contract amendment with additional works with value of US$ 115,441 and timeline extension of 2 months submitted to PU on 22 June 2022. 90% completed. As of 1 June 2022, MOP request for Cost amendment appx: 113,000 USD , Waiting for approval and documentation. Site handover done on 29 September 2021. Contract issued on 20 June 2021. Based on the received offers, only one company may be qualified, subject to obtaining clarifications from the company. Once received, the PU will finalize the case and submit it to RACP for review. The PU has sent the request to provide the additional documents on 29 March 2021. Pre bid site visit conducted on 3 March 2021. Advertised on 23 Feb with deadline on 16 March 2021. Technical documents submitted on 23 Dec 2020. E-req shared on 20 Jan 2021. | 2022-07-12 | Contract Issued | Public Infrastructure | 1 | 151 187 137 | Gov't of Libya Norway Italy | 112158 |  |  | 0.7249 | 0.74653
| Works | West | Tripoli | Health | Rehabilitation of Hospital | Deepening |  | 0 |  | 0 | [7 empty] | Cancelled | Based on information received from site , the rehabilitation project is already started by Hospital administration | 2020-01-17 | Cancelled | [7 empty] | 0.53829 | 0.61027
| Works | West | Tripoli | Public Infrastructure and Services | Cleaning Works and Removal of War Remnants | Deepening | 81900 | 46816.1396 | 81900 | 46816.1396 | Completed | PO + Contract issuance done | 2020-12-30 | Substantial completion / handover done |  |  | 2021-03-31 | Completed | Ben Gashir completed and handed over on 31 March 2021. During the cleaning rubble removal in Qaser Bin Ghashir municipality some Unexploded Explosive Ordnance (UXO) are found on site , and the cleaning works are suspended at the moment until further cleared by LIBMAC. Al-Ssabiaa completed and handed over on 4 March 2021. Document pending. Handover of 18 locations for Al-Ssabia municipality done on 24 Jan 2021. PO issued on 30 Dec 2020. Ali shared clearance letter received from LibMac, clearing 18 locations in Al-Ssabea and 20 locations in Ben Gashir. | 2021-03-31 | Completed | ERW removal | 1 | 151 | Gov't of Libya | 112158 |  |  | 0.65483 | 0.57163
371 | Works | West | Tripoli | Public Infrastructure and Services | Cleaning Works and Removal of War Remnants | Deepening | 155064 | 107037.3674 | 82212 | 56749.1877 | Completed | PO + Contract issuance done | 2021-04-08 | Substantial completion / handover done |  |  | 2022-08-09 | Completed | Handed over on 9 August 2022. Works completed on 29 July 2022 as reported by Ahmed Albukhari. Work started on 3 July 2022. As of 27 June 2022, contractor was transporting required machinary to site. Work to start from 1st week of July 2022. Mining clearance approval was received on 20 June 2022. On 19 May 2022, the site was handed over to contractor for 2nd phase of works. Clearnce from Ministry of defencse was expected to be received within a week. This one week period will also serve as mobilizatiion period for contractor to start the works. As of end of March 2022, still in negotiation to decide new locations. Now when the location will be finalized, LIBMAC will need to conduct survey for clearance. Implementation period is less than a month. Works in Abu Salim completed. Handover scheduled on 4 August 2021. Libmac location clearance letter for Ein Zara received on 31 May 2021. Abu Salim site handed over on 17 May 2021. PO created on 8 April 2021 and successfully dispatched/shared on 21 April after valid CoA. Revised e-req shared on 8 April 2021. E-req shared on 17 Feb 2021 | 2022-08-12 | Completed | ERW removal | 1 | 11410 | UK (FCO) | 112158 |  |  | 0.64028 | 0.69028
372 |  | South | Ubari |  |  | Deepening |  | 0 |  | 0 | [18 empty] | 0.54136 | 0.73297
373 | Works | South | Ubari | Education | Rehabilitation of University | Deepening | 325689 | 173128.6563 |  | 0 | Completed | [6 empty] | In Development | To be readvertised. BOQ will be changed. | 2020-06-01 | Further Funding | University | 1 | 10283 | Germay(KfW) |  | 26.5897 | 12.7684 | 0.66645 | 0.53158
374 | Works | South | Ubari | Education | Rehabilitation of University | Deepening | 225688 | 155825.3897 | 225623.968 | 155781.179 | Completed | PO + Contract issuance done | 2019-12-10 | Substantial completion / handover done |  | 2019-12-24 | 2020-10-04 | Completed | Handed over on 4 October 2020. | 2020-10-09 | Completed | University | 1 | 182 | Netherlands | 112158 | 26.5903 | 12.7685 | 0.61015 | 0.69045
375 | Works | South | Ubari | Public Infrastructure and Services | Rehabilitation of Public Building | Deepening | 621418 | 345994.7089 | 620375.295 | 345414.1489 | Completed | PO + Contract issuance done | 2019-11-01 | Substantial completion / handover done | 2019-11-10 |  | 2020-10-04 | Completed | Handed over on 4 October 2020. | 2020-10-09 | Completed | Public Infrastructure | 1 | 10159 | EU | 112158 | 26.5959 | 12.7798 | 0.56781 | 0.55678
376 | Works | South | Ubari | Energy | Supply and Installation of Solar Street Lights | Deepening | 1514492.45 | 1000517.4706 | 1514492.45 | 1000517.4706 | Completed | PO + Contract issuance done | 2020-01-09 | Substantial completion / handover done |  | 2020-04-15 | 2020-11-26 | Completed | Works completed and final sector handed over on 26 Nov 2020. PO issued on 2nd week of Dec 2019. | 2021-08-03 | Completed | Solar Street Light | 11 | 10283 | Germay(KfW) | 112158 | 26.5896 | 12.7749 | 0.68966 | 0.66063
| Works | South | Ubari | Public Infrastructure and Services | Rehabilitation of Public Infrastructure | Deepening | 375025 | 224228.6433 | 337513.08 | 201800.1467 | Completed | PO + Contract issuance done | 2020-12-24 | Substantial completion / handover done |  | 2021-04-06 | 2022-03-27 | Completed | Completed and handed over on 27 March 2022. Started on 6 April 2021. On 10 March 2021, end user issued letter to abide by technical specification in original SoW and BoQ and approved revised BOQ. Contractor also agreed to implement in line with original contract terms, as per revised BoQ, and within originally agreed amount . Contract issued on 24 Dec 2020. Roundabout and airport project divided into 2 projects. | 2022-03-28 | Completed | Public Infrastructure | 1 | 151 10159 | Gov't of Libya SUSC | 112158 122619 | 26.5877 | 12.7771 | 0.59029 | 0.5979
377 | Works | South | Ubari | Public Infrastructure and Services | Rehabilitation of Public Infrastructure | Deepening | 40190 | 20417.9506 | 40176 | 20410.8381 | Completed | PO + Contract issuance done | 2021-02-06 | Substantial completion / handover done |  | 2021-02-21 | 2021-08-29 | Completed | Completed and handed over on 29 August 2021. The project was suspended on 1 May 2021 due to intervention from unknown armed group entering the site and forcing the contractor team to stop the work and leave the site immediately. Contract issued on 6 Feb 2021. Roundabout and airport project divided into 2 projects | 2021-09-02 | Completed | Public Infrastructure | 1 | 717 | C/S ROK | 112158 |  |  | 0.60418 | 0.50804
| Goods | South | Ubari | Health | Suppy of Medical Equipment | Deepening |  | 0 |  | 0 | Completed | [6 empty] | Cancelled | MoH requested hospital to submit evidence of having qualified personnel to operate the equipment . Letter received and sent to MoH . MoH was expected to send people on the ground to make verifications. This Project can be cancelled completely by the SFL as Mehdi was informed by the MoH that (1) Obari does not have capacity to operate MRI CT scanner , (2) MoH has a number of Scanners in Tripoli which it can supply to hospitals that have qualified personnel to operate the equipment. | 2020-04-16 | Cancelled |  |  | 10283 | Germay(KfW) |  | 26.5928 | 12.7629 | 0.52032 | 0.66987
| Works | South | Ubari | Education | Rehabilitation of University | Deepening | 752000.01 | 470870.2418 | 376942.62 | 236025.3461 | Completed | PO + Contract issuance done | 2020-09-24 | Works completed | 2020-10-26 | 2021-02-01 |  | Contract Issued | Works completed. Will be ready for handover by 1st week of June 2022. Work just started as of 18 feb after access was given to site. Site handed over on 26 Oct 2020. Mayor was in Tripoli as of 13 Oct and he wanted to be present in this handover. Planning to come by end of this week (18 Oct) to Ubari. Contract issued on 24 Sep 2020. | 2022-06-01 | Contract Issued | University | 1 | 11410 717 141 | UK (FCO) C/S ROK Japan | 112158 119794 |  |  | 0.54739 | 0.62616
[8 empty] | 0 |  | 0 | [18 empty] | 0.73051 | 0.61148
|  | GMMRA | GMMRA | WASH | Supply of Sewage Pumps | Broadening | 1000000 | 580091.9987 |  | 0 | To be initiated | [6 empty] | In Development |  |  | Further Funding | [7 empty] | 0.62969 | 0.58009
[8 empty] | 0 |  | 0 | [18 empty] | 0.54736 | 0.6036
| Works |  | Brak Al-Shati | Energy | Supply and Installation of Solar Street Lights | Non-SFL | 850000 | 521161.609 |  | 0 | Completed | Advertisement period ongoing | [5 empty] | In Development | On 25 April 2022, as per discussion with RR, this case was suspended due to unexpected funding issue under SUSC. Procurement unit acknowledged suspension request on same day. Advertised on 7 April 2022 with deadline on 28 April 2022. TNRL activity to be implemented by SFL. Needs to be contracted. | 2022-04-25 | With Procurement |  |  | 10159 | SUSC | 122619 |  |  | 0.64404 | 0.61313
[8 empty] | 0 |  | 0 | [18 empty] | 0.54394 | 0.62343
| Goods | West | Tripoli | Covid-19 | Covid-19 Medical Equipment | Deepening | 24636.0582 | 13470.5847 | 24636.0582 | 13470.5847 | Completed | PO + Contract issuance done | 2019-12-05 | Substantial completion / handover done |  |  | 2020-08-31 | Completed | 1st batch, which consists of 430 cartridges (10 tests per cartridge), has been succesfully delivered to Misrata CNDC Warehouse on 14 July 2020. All the remaining cartridges (1070) were delivered to Misrata CNDC Warehouse on late August 2020. To be distributed by MoH to Sebha, Tripoli, Kufra and Ghat. | 2020-09-15 | Completed |  |  | 10283 | Germay(KfW) | 112158 |  |  | 0.74597 | 0.54678
| Goods | West | Tripoli | Covid-19 | Covid-19 Medical Equipment | Deepening | 120000 | 86742.2231 |  | 0 | Completed | PO + Contract issuance done | 2019-07-15 | Substantial completion / handover done |  |  | 2020-04-10 | Completed | UNDP Libya has concluded this activity together with WHO as the implementing partner. Delivered on 10 April 2020 - done by WHO - The WHO was requested to submit the debit advice along with other documents to process the payment. Representative of WHO informed that WHO is currently having issues with payment. The issue should be solved soon, and WHO should come back to us by the end of this week (17 July 2020). Byashim will follow up on the payment to WHO. | 2020-08-14 | Completed | [7 empty] | 0.51401 | 0.72285
| Goods | West | Tripoli | Covid-19 | Covid-19 Medical Equipment | Deepening |  | 0 |  | 0 | Completed | PO + Contract issuance done | 2020-01-19 | Substantial completion / handover done |  |  | 2020-10-15 | Completed | Arrived at Misrata Airport on 15 October, Will be distributed in coordination with MoH. | 2020-11-06 | Completed | [7 empty] | 0.67946 | 0.67238
| Works | South | Bent Baya | Covid-19 | Covid-19 Isolatin Centre | Broadening | 395000 | 274245.6886 | 395000 | 274245.6886 | Completed | PO + Contract issuance done | 2020-11-23 | Substantial completion / handover done |  |  | 2021-03-18 | Completed | Completed and handed over on 18 March 2021. Contract issued on 23 Nov 2020. | 2021-03-24 | Completed |  |  | 10283 | Germay(KfW) | 112158 |  |  | 0.61687 | 0.69429
| Goods | West | Tripoli | Covid-19 | Covid-19 Medical Equipment | Deepening | 80000 | 59106.7783 |  | 0 | Completed | Advertisement period completed | [5 empty] | With Procurement | Under evaluation. Case forwarded to Ehab to evaluate on 2 March 2022. JSB agreed to fund this project. No response to initial RFQ was received. Case was readvertised 5 July 2021. The case will be advertised on 30 March 2021, with closing date on 7 April 2021. Expected contract issuance 30 April 2021 (non-CAP Case) | 2022-03-03 | With Procurement |  |  | 141 | START |  |  |  | 0.5312 | 0.73883
| Works | West | Bani Walid | Covid-19 | Covid-19 Isolatin Centre | Deepening |  | 0 |  | 0 | Completed | [6 empty] | Cancelled | 60% completed. Implemented under contract "ITB/LBY/SFL/2019/062" - Rehabilitation of Bani Walid General Hospital. Technical documents submitted to SC. Byashim, together with Ali was working on the review of BOQ. It is expected to complete the exercise by 13 July 2020. On 2 July 2020, NTF was sent to the SC to amend the current contract in which the location should be switched from Bani Walid Hospital to Diabetes healthcare facility. | 2020-08-14 | Cancelled | [7 empty] | 0.56485 | 0.54494
| Works | South | Kufra | Covid-19 | Covid-19 Isolatin Centre | Broadening | 41890 | 21792.5791 | 40509 | 21074.1367 | Completed | PO + Contract issuance done | 2021-02-04 | Substantial completion / handover done | 2021-02-15 | 2021-02-28 | 2021-08-04 | Completed | Completed and handed over on 4 August 2021. Contract issued on 4 Feb 2021 and site handed over on 15 Feb 2021. | 2021-09-02 | Completed | Hospital | 1 | 10159 | SUSC | 122619 |  |  | 0.74424 | 0.52023
| Goods | South | Ghat | Covid-19 | Covid-19 Medical Equipment | Broadening | 100000 | 63416.0389 |  | 0 | Completed | PO + Contract issuance done | 2020-04-06 | Substantial completion / handover done |  |  | 2021-01-01 | Completed | consist of 3 components: 1- One GeneXpert Machines (COVID 19 testing machine): delivered in Jan 2021 2- 3 ICU Ventilators: Delivered in Jan 2021 3- Medical equipment to be purchased through GPU. As of 5 July 2021, project adjusting quantities of items | 2021-07-07 | Completed | Medical Equipment |  | 10283 | Germay(KfW) |  |  |  | 0.54142 | 0.63416
| Works | East | Derna | Covid-19 | Covid-19 Isolatin Centre | Broadening | 271509 | 163477.9162 |  | 0 | Completed | PO + Contract issuance done | 2021-12-03 | Work progress 50% - 75% | 2021-12-18 |  |  | Contract Issued | 55% completed. Site handover done on 18 Dec 2021. Contract issued on 3 Dec 2021. | 2022-06-01 | Contract Issued | Hospital | 1 | 141 | Japan | 127766 |  |  | 0.68973 | 0.60211
| Goods | South | Sebha | Covid-19 | Covid-19 Medical Equipment | Deepening | 164533.72 | 87511.2884 | 140300.83 | 74622.4324 | Completed | PO + Contract issuance done | 2020-06-03 | Substantial completion / handover done |  |  | 2021-02-28 | Completed | Initially consisted of 3 components. International medical equipment purchase was cancelled as per reprioritization exercise submitted to PU on 23 August 2021. 1- Two ICU Ambulances delivered Feb 2021 2- local PPE items were delivered. 3- Medical Items from the Global market is under development with GPU. As of 5 July 2021, project adjusting quantities of items. | 2021-09-02 | Completed |  |  | 187 151 10283 | Norway Gov't of Libya | 98720 112158 |  |  | 0.61055 | 0.53187
| Goods | East | Ajdabiya | Covid-19 | Covid-19 Medical Equipment | Broadening | 172022.41 | 127602.9623 | 135673.62 | 100640.1191 | Completed | PO + Contract issuance done | 2020-05-21 | Substantial completion / handover done |  |  | 2021-02-15 | Completed | Handed over on 15 Feb 2021. The Purchase order for the ICU ambulances was placed on 21 July 2020, expected delivery is late November/early December 2020 | 2021-06-03 | Completed |  |  | 187 151 10283 | Norway Gov't of Libya Germay(KfW) | 98720 112158 |  |  | 0.58737 | 0.74178
| Works | East | Benghazi | Covid-19 | Covid-19 Isolatin Centre | Non-SFL | 176644.5 | 125914.2019 | 158980.5 | 113323.1025 | Completed | PO + Contract issuance done | 2021-02-21 | Substantial completion / handover done | 2021-03-07 |  | 2021-07-25 | Completed | Works completed and handover document signed dated 25 July 2021. Handover event may be organized mid october 2021. Site handed over to contractor on 7 March 2021. Contract issued on 21 Feb 2021. | 2021-09-29 | Non SFL | Hospital | 1 | 141 | JSB Covid-19 | 121748 |  |  | 0.66701 | 0.71281
| Goods | West | Tripoli | Covid-19 | Covid-19 Medical Equipment | Deepening |  | 0 |  | 0 | Completed | PO + Contract issuance done | 2020-05-01 | Substantial completion / handover done |  |  | 2021-01-26 | Completed | Second lot of 10 ventilators handed over to WHO on 26 Jan 2021. Previously, 12 ventilators handed over to MoH covid 19 warehouse on 26 Oct 2020. | 2021-02-01 | Completed | [7 empty] | 0.51849 | 0.61469
| Goods | West | Tripoli | Covid-19 | Covid-19 Medical Equipment | Deepening | 292200 | 147392.8445 | 291260 | 146918.6854 | Completed | PO + Contract issuance done | 2020-11-13 | Substantial completion / handover done |  |  | 2021-08-10 | Completed | Handover ceremony organized on 10 August 2021. Will be stored in Palm City at SFL villa# 245. This was delayed because manufacturer had issues with the component of compressor. | 2021-08-17 | Completed |  |  | 10283 | Germay(KfW) | 112158 |  |  | 0.63131 | 0.50442
| Works | West | Tripoli | Covid-19 | Covid-19 Isolatin Centre | Non-SFL | 36400 | 19500.4893 | 32760 | 17550.4404 | Completed | PO + Contract issuance done | 2021-05-07 | Substantial completion / handover done | 2021-06-01 |  | 2021-11-21 | Completed | Completed and handed over on 21 Nov 2021. Site handed over on 1 June 2021. Contract issued on 7 May 2021. | 2021-11-25 | Non SFL | Solar Panels | 1 | 141 | JSB Covid-19 | 121748 |  |  | 0.50153 | 0.53573
| Works | East | Benghazi | Covid-19 | Covid-19 Isolatin Centre | Non-SFL | 430000 | 216536.5001 | 387000 | 194882.8501 | Completed | PO + Contract issuance done | 2021-07-01 | Substantial completion / handover done | 2021-09-26 |  | 2022-02-21 | Completed | Completed and handed over on 21 Feb 2022. Site handover done on 26 Sep 2021. Contract issued on 1 July 2021. | 2022-04-07 | Non SFL | Medical Equipment | 1 | 141 | JSB Covid-19 | 121748 |  |  | 0.7248 | 0.50357
| Works | West | Tripoli | Covid-19 | Covid-19 Isolatin Centre | Deepening | 385000 | 206275.3189 | 385000 | 206275.3189 | Completed | PO + Contract issuance done | 2021-07-25 | Substantial completion / handover done |  |  | 2021-11-18 | Completed | Completed and handed over on 18 Nov 2021. Site handed over on 3 Aug 2021. Revised e-req shared with PU on 29 July 2021. Contract issued on 25 July 2021. | 2021-11-25 | Completed | Medical Equipment | 1 | 141 | Japan | 127766 |  |  | 0.6941 | 0.53578
| Works | West | Tripoli | Covid-19 | Covid-19 Isolatin Centre | Deepening | 400000 | 238260.0327 |  | 0 | To be initiated | [6 empty] | In Development | MoH signed request letter was shared by Lamine on 8 March 2021. Craig informed Lamine on the same days that this will be subject to further funding. | 2021-03-18 | Further Funding | Medical Equipment | 1 | [5 empty] | 0.55188 | 0.59565
| Goods | East | Tokara | Covid-19 | Covid-19 Medical Equipment | Non-SFL | 250000 | 154137.5675 |  | 0 | Completed | PO + Contract issuance done | 2019-06-01 | In shipment to Libya |  |  |  | Contract Issued | As informed on 8 November 2021, shipment to Libya underway. ETA Misurata port 2 December 2021. The Purchase order for the ICU ambulances was placed on 21 July 2020, expected delivery is late November/early December 2020. As for the Sewage Truck - waiting for the budget to be determined. | 2021-11-18 | Non SFL |  |  | 141 | RFF | 134229 |  |  | 0.6045 | 0.61655
| Goods | South | Sebha | Covid-19 | Covid-19 Medical Equipment | Non-SFL | 293800 | 202312.1294 |  | 0 | Scope of work development stage | [6 empty] | In Development | Draft requirement shared with field engineers for review and inputs on 19 Oct 2020 | 2020-10-30 | Non SFL | [7 empty] | 0.62792 | 0.6886
| Works | West | Gharyan | Covid-19 | Covid-19 Isolatin Centre | Broadening | 96100 | 49998.9422 | 86460.48 | 44983.6893 | Completed | PO + Contract issuance done | 2021-09-25 | Substantial completion / handover done | 2021-10-31 |  | 2022-07-27 | Completed | Handedover on 27 July 2022. As of 7 July, works reported complete by field team. Site handover to contractor done on 31 Oct 2021. Contract issued on 25 Sep 2021. | 2022-07-29 | Contract Issued | Solar Panels |  | 141 | Japan | 127766 |  |  | 0.71936 | 0.52028
| Works | South | Bent Baya | Covid-19 | Covid-19 Isolatin Centre | Non-SFL | 106725 | 68691.9523 |  | 0 | Completed | PO + Contract issuance done | 2021-10-04 | Work progress 50% - 75% |  |  |  | Contract Issued | 70% completed as of 13 June 2022. On same day, Moulay informed that main solar equipment has been delivered to the site. Expected to be completed within additional month (Mid July 2022). As of 1 June 2022, Ali informed that the construction works are going slowly on the project site, and we have not been updated about the status of the imported solar equipment and the schedule for installation works. 10% completed. Contract issued on 4 Oct 2021 | 2022-06-14 | Non SFL | Solar Panels |  | 141 | JSB Covid-19 | 121748 |  |  | 0.61496 | 0.64364
| Works | South | Bent Baya | Covid-19 | Covid-19 Isolatin Centre | Non-SFL |  | 0 |  | 0 | Completed | PO + Contract issuance done | 2021-10-04 | Work progress 50% - 75% |  |  |  | Contract Issued | 70% completed as of 13 June 2022. On same day, Moulay informed that main solar equipment has been delivered to the site. Expected to be completed within additional month (Mid July 2022). As of 1 June 2022, Ali informed that the construction works are going slowly on the project site, and we have not been updated about the status of the imported solar equipment and the schedule for installation works. 10% completed. Contract issued on 4 Oct 2021 | 2022-06-14 | Non SFL | Solar Panels |  | 141 | JSB Covid-19 | 121748 |  |  | 0.7003 | 0.67722
Formulas:
Start Date = Table1[[#This Row],[Site handover date]]+7
Start Date = [Site handover date]+7
Contract Signing = Table1[[#This Row],[Actual completion date]]-270
Note on J3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: cost for 8 out of 9 garbage trucks
Note on R3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 1 - 10 dec 2017 4 - 24 July 2018 3 - 28 Aug 2018
Note on Z3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Korea - PO 4772 @ US$ 35,532.17
Note on F4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Not specific enough Cost Calculation: apart from Fire trucks every other truck's average cost was USD 150,000 per truck or higher but this estimate may be farfetched from realistic costs in absence of further info
Note on F5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 15 m3 USD 116,000 per truck for sirt in June 2018
Note on F6: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Not specific enough Cost Calculation: apart from Fire trucks every other truck's average cost was USD 150,000 per truck or higher but this estimate may be farfetched from realistic costs in absence of further info
Note on Z7: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Korea - PO 4752 @ US$ 18,714.12
Note on F8: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: USD 500 per bin for sirt back in June 2018
Note on F13: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Renamed from Supply of Refrigeration for vaccines, cold chain for Health Directorate.
Note on F14: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: USD 58,000 for regular ambulance for Ghodowah in Sep 2019 Approximately USD 45,000 for both ICU and regular back in Jan 2017
Note on H14: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 3 already delivered as test case.
Note on J14: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Based on SFL Procurement Monitoring cost breakdown Cost Reconciliation tab Rows 4&5
Note on Z22: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Japan - PO 4936 @ US$ 14,080
Note on Z23: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Korea - PO 4831 @ US$ 10,844
Note on Z25: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: KfW - PO 5430 @US$ 11,416
Note on AA25: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: KfW @ US$ 11,416 under 112158
Note on Z26: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: As per info on GJLE reversal from Korea, provided by Basma on 24 Feb 2022
Note on F30: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: estimated at $100,000
Note on F31: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: estimated at $100,000
Note on F32: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: estimated at $100,000
Note on Z35: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: KfW - US$ 119,427.89 transferred from Netherlands through GLJE (in process)
Note on J37: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Based on SFL Procurement Monitoring cost breakdown Cost Reconciliation tab Rows 4&5
Note on J51: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: PO 4626 for transportation of 3 ambulances to Bani walid
Note on Z51: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Denmark - PO 4626 @ US$ 6,575
Note on Z52: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: KfW - @ US$ 335,223.44 transferred from Italy through GLJE 7164218
Note on Z58: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Italy - PO 4005 @ US$ 43,885.27 for shipment of 14 generators Denmark - PO 4704 @ US$ 3,846.15
Note on Z62: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Netherlands - PO 6746 @ US$ 57,248.81 for retention amount
Note on J63: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Based on SFL Procurement Monitoring cost breakdown Cost Reconciliation tab Rows 4&5
Note on Z63: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Denmark - PO 4626 @ US$ 6,575
Note on J64: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: $ 237.63 insurance for shipment (non PO voucher-0027332) 516 euros damco demurrage cost-processed to finance on 23 dec 2019 6,501.65 shipment
Note on Z64: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: KfW - PO 5242 @ US$ 6,501.65
Note on AA64: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: KfW - PO 5242 @ US$ 6,501.65 under 112158
Note on R66: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 1 - 8 Feb 2018
Note on Z67: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Italy - PO 4005 @ US$ 43,885.27 for shipment of 14 generators Denmark - PO 4704 @ US$ 3,846.15
Note on F69: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: estimated $55000
Note on F70: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: estimated $30000
Note on J71: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: US$ 299.25 insurance for delivery of goods.
Note on Z71: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: UK - PO 5102 @ US$ 7,146.04
Note on J72: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: payment of shipping services for 6 pcs
Note on Z72: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: USAID - PO 5089 @ US$ 7,554.95
Note on AA72: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: USAID - PO 5089 @ US$ 7,554.95 under 112158
Note on H74: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Includes transportation to palm city
Note on J74: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Includes transportation to palm city
Note on Z74: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Korea - PO 4832 @ US$ 5,835.23 Japan - PO 4704 @ US$ 3,226.18
Note on Z75: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Japan - PO 4997 @ US$ 11,178.45
Note on F76: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: estimated $25000
Note on Z77: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: KfW - @ US$ 335,223.44 transferred from Italy through GLJE 7164218
Note on H82: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: initial amount reflected as per PO 3975
Note on N85: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: amendmend signed on 28 August 17
Note on Z85: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: KfW - PO 4440 @ US$ 19,133
Note on Z87: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: GoL - 6498 for retention @ US$ 26,232.50
Note on F89: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 200 bins for $95,667
Note on Z99: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: US$ 29,750 transferred to KfW from Norway through GLJE 7164218
Note on Z100: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: US$ 29,750 transferred to KfW from Norway through GLJE 7164218
Note on Z101: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: US$ 29,750 transferred to KfW from Norway through GLJE 7164218
Note on Z102: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: US$ 29,750 transferred to KfW from Norway through GLJE 7164218
Note on H105: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 100000 allocation shifted to tawergha case (PO 5364)
Note on J105: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 100000 allocation shifted to tawergha case (PO 5364)
Note on Z105: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: KfW - GP600439-1 @ US$ 2,700 transferred from Italy Through GLJE 7164218 Korea- GP600439-2 @ US$ 59,900 KfW- GP600439-2 & GP600439-8 @ US$ 60,935.05 Japan- GP600439-3 @ US$ 71,689.49 Norway- GP600439-4 @ US$ 13,468.01
Note on Z106: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: KfW - PO 4409 @ US$ 119,099.78 Denmark - PO 4699 @ US$ 5,565.07 EU - PO 4592 @ US$ 9,250 USAID - PO 4338 @ US$ 245,880.4 transferred from France through GLJE 7686419
Note on F107: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Need to check if there is transport cost under a different PO.
Note on Z107: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 255,036.4 transferred to USAID from Norway through GLJE 7686419
Note on H111: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: includes shipment by air and sea
Note on Z125: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Korea - PO GP-2 @ US$ 4,914.29 Korea - PO 4792 @ US$ 1,934.01 for transport
Note on Z128: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Transferred from Italy through GLJE 7164218
Note on Z131: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: France - PO 4754 @ US$ 394,093.35 Canada - PO 4754 @ US$ 82,957.77 USAID - PO 4754 @ US$ 33,393.57 Japan - PO 5080 @ US$ 17,502.76
Note on AA131: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Japan - PO 5080 @ US$ 17,502.76 under 112158
Note on H132: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Includes transportation to Palm city $39.28 for insurance of shipment (non PO voucher 00028950)
Note on Z132: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Korea - PO 4832 @ US$ 15,202.31 KfW - PO 5259 @ US$ 9.349.5
Note on AA132: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: KfW - PO 5259 @ US$ 9.349.5 under 112158 EU - PO 5318 @ US$ 9,318.68 under 112158 EU - PO 5344 @ US$ 16,307.69 under 112158
Note on Z133: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Japan - PO 5528 @ US$ 5,714.5
Note on J134: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: $ 118.81 insurance for shipment (non PO voucher-0027332)
Note on Z134: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Germany (KfW)-PO 5241 @ US$ 6,668.77 USAID-PO 5222 @ US$ 13,076.92
Note on AA134: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: USAID-PO 5222 @ US$ 13,076.92 under 98720
Note on Z135: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Italy - PO 5071 @ US$ 8,615.97 Japan - PO 5632 @ US$ 8,825.09 Japan - PO 5633 @ US$ 34,596.94 UK - PO 6115 @ US$ 900
Note on AA135: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Japan - PO 5632 @ US$ 8,825.09 under 112158 Japan - PO 5633 @ US$ 34,596.94 under 112158
Note on F136: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Initially advertised in 2 April 2020. Readvertised in September 2020 for 2 wks. Readvertised in 6 January 2022 for 3rd time Readvertised on 18 July 2022
Note on H136: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: updated engineering estimate
Note on F137: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: estiamted at $20,000
Note on F138: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: estimated at $130,000
Note on J142: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: formerly =712320+56000
Note on Z144: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: US$ 198,410.47 transferred to KfW from USDoS through GLJE 7299501
Note on Z147: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Demark - GP405127-1 (one line) @ US$ 10,416.48
Note on H150: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Add cost for transportation once PO is raised
Note on J157: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Includes delivery cost
Note on Z158: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Italy - US$ 173,303.93 transferred from UK through GLJE 8676295
Note on Z161: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Netherlands - PO 6745 @ US$ 22,695.11 for retention
Note on J163: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 1040.86 insurance for shipment of 4 from Belgium to Tripoli
Note on Z163: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Norway - PO 5188 @ US$ 81,619.26
Note on AA163: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Japan - PO 5091 @ US$ 20,562.29 under 112158
Note on F166: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: initial estimate $ 1,500,000
Note on J167: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: cost of 1 out of 9 garbage trucks
Note on Z167: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Korea - PO 4772 @ US$ 8,883.04
Note on Y174: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Canada - GP405110-1 @ US$ 614,020.9 MOFA - GP405110-1 @ US$ 151,553.73 USAID - GP405110-3 @ US$ 12,950
Note on Z174: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: USAID - GP405110-3 @ US$ 12,950 under 112158
Note on AA174: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: USAID - GP405110-3 @ US$ 12,950 under 112158
Note on Z201: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Italy - PO 5895 @ US$ 10,245.5 for retention
Note on Z202: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Italy - PO 5895 @ US$ 10,245.5 for retention
Note on Z203: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Italy - PO 5895 @ US$ 10,245.5 for retention
Note on R278: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: completed in march but substantial handover document availed near end of 2019
Note on R279: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: completed in march but substantial handover document availed near end of 2019
Note on R280: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: completed in march but substantial handover document availed near end of 2019
Note on Z281: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: KfW - US$ 4,845.20 transferred from USAID through GLJE 8630159. This is for PO 4982 for 3 schools Omar Ebn Al-Khatab, Al-Nidhal, and Ebn Al-Hasan Schools
Note on Z282: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: KfW - US$ 4,845.20 transferred from USAID through GLJE 8630159. This is for PO 4982 for 3 schools Omar Ebn Al-Khatab, Al-Nidhal, and Ebn Al-Hasan Schools
Note on Z283: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: KfW - US$ 4,845.20 transferred from USAID through GLJE 8630159. This is for PO 4982 for 3 schools Omar Ebn Al-Khatab, Al-Nidhal, and Ebn Al-Hasan Schools
Note on Z300: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: KfW - @ US$ 335,223.44 transferred from Italy through GLJE 7164218
Note on Z313: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Total expenditure of Trucks procurement US$ 678,696.51 shifted to KfW from GoL through GLJE 0009128005 Korea - PO 6071 @ US$ 52,753.94 divided equally between 2
Note on H316: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: engineering estimate
Note on H317: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: engineering estimate
Note on H318: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: engineering estimate
Note on J319: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 10,707.45 request submitted on 22 August 2022
Note on H320: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 76.59 for insurance of shipment (non po voucher 00028950)
Note on Z320: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: USAID - US$ 452,877.5 total cost of 8000m cable transferred to Repsol through GLJE 8282350 EU - PO 5403 for shipment
Note on Z323: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: EU - PO 5365 @ US$ 285,344.73 Japan - PO 5334 @ US$ 54,651.42
Note on Z324: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: KfW - @ US$ 95,753.84 payment reversed from Norway through GLJE 9141924
Note on H328: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: VID 29492 @ $750 for custom clearance of Benghazi Solar Shipment
Note on Z328: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Libya - PO GP600788-4 @ US$ 55,202.70
Note on J329: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 37.008.84 payment request submitted on 17 August 2022
Note on Z329: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: $228,842.70 shifted from Norway to KfW through GLJE 0009128005 Therefore Norway contribution becomes $141,291.3
Note on H334: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: $16633.42 shipment cost of 3 ICUs to Derna EUR 3250 shipment of 1 regular to Derna VID 29450 @ $250 for custom clearance of 2 ICU ambulances VID 29451 @ $200 for custom clearance of 1 ICU ambulance
Note on Z336: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Total expenditure of Trucks procurement US$ 678,696.51 shifted to KfW from GoL through GLJE 0009128005 Korea - PO 6071 @ US$ 52,753.94 divided equally between 2
Note on H337: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: shipment cost 11538.35
Note on Z337: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Korea - PO 5823 @ US$ 11,538.35
Note on AA337: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Korea - PO 5823 @ US$ 11,538.35 under 112158
Note on H338: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: $6,853.35 for shipment
Note on Z338: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: KfW - PO 5832 @ US$ 6,853.35
Note on AA338: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: KfW - PO 5832 @ US$ 6,853.35 under 112158
Note on Z339: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Norway - PO 6248 @ US$ 11,459.7
Note on N340: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: typo in contract as March 22 2022, Anees has email correspondence
Note on Z341: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 90% payment of US$ 110,501.19 shifted to SUSC from GoL through GLJE 0009136820
Note on H344: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: $400 for custom clearance cost
Note on J344: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: $400 custom clearance under non PO VID 00029356 (processed on 28 July 20 for payment)
Note on Z344: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: MOFA - PO 5615 @ US$ 81224.1 EU - US$ 401,781.64 transferred from KfW through GLJE 8631034 for trucks
Note on Z345: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: USAID- PO 5408 payment @ US$ 43,696.37 transferred from Japan through GLJE 8353473
Note on H346: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: $411 demurrage cost on shipping under non PO voucher 00028902 Rohan: $500 customs clearance cost under non PO voucher 00029019
Note on H348: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: $380.72 for customs with non PO voucher 29194
Note on H349: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: $542.8 for customs with non PO voucher 00029200
Note on H350: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: US$ 150 under non PO VID 30344 for customs clearance
Note on Z350: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: GoL- PO 6065 @ US$ 18,048.23 SUSC - VID 30344 @ US$ 150
Note on Z351: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: KfW- GP405177-2 @ US$ 11,848.34
Note on Z353: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: USAID - US$ 452,877.5 total cost of 8000m cable transferred to Repsol through GLJE 8282350 USAID - PO 5331 for shipment @ US$ 7,000 transferred from Japan through GLJE 8353473
Note on H354: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: US$ 1,200 for transportation 2,982.33 is USD amount for Hydraulic Cranes. LYD amount is LYD 4,220 paid via VID 28806.
Note on Z354: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: UK- PO 6115 @ US$ 1,200
Note on H359: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Previous contract value US$ 248,854
Note on N359: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: previous contract signing date 6 Dec 2020 which was cancelled.
Note on N360: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: this contract was terminated on 24 Sep 2021
Note on Z362: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: SUSC - VID 30419 @ US$ 1,335 for custom clearance
Note on Z365: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: SUSC - PO 6064 @ US$ 18,363.61 Reply: Italy - PO 6250 @ US$ 1,292.03
Note on H369: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 34,251 MCR for WFP-UNHRD (sewage truck, water tankers, sewer cleaner) Reply: 55.276.2 shipment cost for 1 sewage truck and 2 water tankers
Note on J369: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 27,144.79 actual cost of MCR for WFP-UNHRD (sewage truck, water tankers, sewer cleaner)
Note on H370: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 34,251 MCR for WFP-UNHRD (sewage truck, water tankers, sewer cleaner) Reply: 55.276.2 shipment cost for 1 sewage truck and 2 water tankers
Note on J370: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 27,144.79 actual cost of MCR for WFP-UNHRD (sewage truck, water tankers, sewer cleaner)
Note on H371: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 34,251 MCR for WFP-UNHRD (sewage truck, water tankers, sewer cleaner)
Note on J371: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 27,144.79 actual cost of MCR for WFP-UNHRD (sewage truck, water tankers, sewer cleaner)
Note on Z371: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Netherlands - PO 6162 @ US$ 11,184.44
Note on Z373: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: EU - US$ 104,213.85 transferred from KfW through GLJE 8631034
Note on J375: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 18,772.14 processed for payment on 17 Aug 2022
Note on H377: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 23775.43 additiional as amendment
Note on Z377: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Korea - PO 6094 @ US$ 23,775.43
Note on Z379: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Italy - PO 6610 @ US$ 14,719.06 for amendment for extra works
Note on Z380: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: EU - US$ 106,232.22 transerred from Netherlands through GLJE 8818340
Note on R381: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: taking over inspection date
Note on Z384: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: SUSC - VID 30344 @ US$ 824.13
Note on Z385: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: France - PO 5987 @ US$ 17,185.5
Note on AA385: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: France - PO 5987 @ US$ 17,185.5 under 98720
Note on Z386: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: SUSC - VID 30341 @ US$ 750
Note on H387: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: VID 29455 @ $500 for custom clearance of 3 pumps $19,818.54 for shipment $157.29 additional storage cost
Note on Z387: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Germany (KfW)-PO 5635 @ US$ 19,818.54
Note on H388: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: $7,563.10 increment through amendment on 3 Nov 2020
Note on N390: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: contract was terminated as informed by PU on 8 Oct 2021
Note on Z392: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: USAID - US$ 452,877.5 total cost of 8000m cable transferred to Repsol through GLJE 8282350 USAID - PO 5331 for shipment @ US$ 5,700 transferred from Japan through GLJE 8353473
Note on L396: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: e-req pending
Note on Z398: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: US$ 145,824 shifted to PBF project from Italy through GLJE 9140566
Note on H400: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 10,000 Management support cost 16,179.16 shipment
Note on H402: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 10,000 Management support cost 24,268.74 shipment
Note on H403: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: shipement estimated @15% of equipment cost
Note on H404: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 10,000 Management support cost 26, 076.17 shipment
Note on H405: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 8,367 Management support cost 18, 419.5 shipment
Note on L407: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Technical docs submitted on 19 Oct 2020. e-req shared on 4 Nov 2020
Note on L408: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: endorsed specs submitted on 28 Jan 2021. E-req issuance pending, put under priority 2
Note on H410: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 10,000 Management support cost 17,969.04 shipment
Note on F412: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Estimated amount $406,585. Cancelled as this was prefab.
Note on H413: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: estimated cost for 1 ambulance and shipping. This was delivered from stock present at Palm City at the time.
Note on Z414: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: KfW - GP600439-8 @ US$ 47,015.05
Note on Z418: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: KfW - PO 5789 @ US$ 8,055.95 Netherlands - VID 30587 @ US$ 3083.90
Note on H421: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 22858.5 MCR for WFP-UNHRD (suction truck, water tanker and pesticide sprayers) Reply: 36,850.8/2 shipment cost for 1 sewage truck and 1 water tanker
Note on J421: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 20,412 actual cost of MCR for WFP-UNHRD (sewage truck, water tanker, pesticide sprayers)
Note on H422: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 22858.5 MCR for WFP-UNHRD (suction truck, water tanker and pesticide sprayers) Reply: 36,850.8/2 shipment cost for 1 sewage truck and 1 water tanker
Note on J422: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 20,412 actual cost of MCR for WFP-UNHRD (sewage truck, water tanker, pesticide sprayers)
Note on H423: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 22858.5 MCR for WFP-UNHRD (suction truck, water tanker and pesticide sprayers)
Note on J423: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 20,412 actual cost of MCR for WFP-UNHRD (sewage truck, water tanker, pesticide sprayers)
Note on Z424: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: US$ 130,000 contributioin from RFF
Note on Z426: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: GoL - @ US$ 200,000 Italy - @ US$ 160,299.64 Italy - PO 6762 @ US$ 54,000 for amendment
Note on Z428: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Japan - PO 5549 @ US$ 249,754.05 USAID - US$ 489,151.94 trasferred from KfW through GLJE 8353473 EU - US$ 36,347.75 transferred from KfW through GLJE 8631034
Note on Z429: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: EU - PO 5467 expenditure US$ 752,178.26 reversed through GLJE 0008631034
Note on J431: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 237,200.4 request submitted on 17 August 2022
Note on L431: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: technical docs submitted on 23 Dec 2020. E-Req shared on 20 Jan 2021.
Note on Z431: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Italy - PO 6673 for amendment @ US$ 115,441 PO 6163 distributed evenly between Libya and Norway
Note on F432: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: estimated amount $356,357
Note on H436: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: engineering estimate
Note on F440: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: First case advertisement was closed in 1 Aug 2019 and was scheduled for readvertisement
Note on Z440: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Payment of US$ 146,497.49 transferred from GoL to SUSC through GLJE 9136820
Note on F441: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: First case advertisement was closed in 1 Aug 2019 and was scheduled for readvertisement. Case then divided into two separate cases.
Note on J441: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 4,017.6 request submitted on 22 August 2022
Note on F442: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: estimated at $1,000,000
Note on H442: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: engineering estimate
Note on Z443: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Divided among 3 donors UK - @ US$ 332,000 Korea - @ US$ 220,000 Japan - @ US$ 200,000 under START
Note on H445: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Initial agreed allocation
Note on H447: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: engineering estimate
Note on J455: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 4,050.9 request submitted on 17 Aug 2022
Note on Z458: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Norway - PO 5755 for 2 ambulances GoL - PO 6069 @ US$ 49,850 for medical items GoL - PO 5930 @ US$ 9,074.72 for 2 ambulances KfW - US$ 488.43 shifted from GoL through GLJE 9128005
Note on Z459: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: PO 5930 @ US$ 13,608.91 against which payment of US$ 11,196.24 was done. GoL - PO 5930 @ US$ 732.46 in payment KfW - PO 5930 @ US$ 10,463.78 in payment reversed from GoL through GLJE 0009128005
Note on D461: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Tobruk, Derna, Al Baida,Al Marj, Benghazi, Ajdabiya, Al Wahat, Al Kufra, Sebha, Ubari Murzuk, Ashashatti
Note on D462: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Kufra, Derna, Benghazi, Ghat, Sebha, Tripoli, Tawergha, Ubari, Ajdabiya, Bani walid
Note on L463: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: submitted on 20 Jan 2021. E-req shared on 28 Dec 2020.
Note on J465: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 38,500 payment request submitted on 2 August 2022
Note on F468: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: -CNCD Lab -Sebha Isolation Centre, -Sebha Medical Centre; A-Dialysis Department B-Baby Incubators C-Laboratory
Note on H468: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: engineering estimate
Note on H471: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Lumped together with medical lab bent baya above

## Board Approved Budget
Location | Approved Budget
Ajdabiya | 2000000
Bani Walid | 3000000
Benghazi | 10660000
Bent Baya
Derna | 2000000
Gharyan
Ghat | 2500000
Kikla | 2000000
Kufra | 2000000
Misurata
Sebha | 7250000
Sirt | 10640000
Tawergha | 3000000
Tripoli | 18000000
Ubari | 7650000
70700000

## Data inputs
WORKS / GOODS / SERVICES | LOCATION | SECTOR |  | Initial Phase | Status Contracting Phase |  | Status Implementation Phase |  | Fund | Donor
|  |  |  | To be initiated | ITB/RFQ Prep done | 10 | Site Handover done | 0 - 25% | 30000 | 00095 - Denmark |  | 95 | Denmark
Goods | Ajdabiya | Education |  | Scope of work development stage | ITB/RFQ review, approval, sign & upload done | 10 | Work progress 0 - 25% | 0 - 25% | 30000 | 00112 - France |  | 112 | France
Works | Bani Walid | Solid Waste Management |  | BOQ development stage | Technical documents approved | 25 | Work progress 25% - 50% | 25% - 50% | 30000 | 00117 - Germany (MOFA) |  | 117 | Germany(MOFA)
Goods/Works | Benghazi | Health |  | Site survey done | Quotation received from vendor | 50 | Work progress 50% - 75% | 50% - 75% | 30000 | 00137 - Italy |  | 137 | Italy
| Bent Baya | Energy |  | Initial BOQ prep done | Quotation approved by end user | 75 | Work progress over 75% | Over 75% | 32045 | 00141 - Japan |  | 141 | Japan
| Derna | Public Infrastructure and Services |  | Finalization of BOQ/Project spec prep done | Advertisement period ongoing | 20 | Punch List (@95% completion) | Punch List (@95% completion) | 30071 | 00151 - Gov't of Libya |  | 151 | Gov't of Libya
| Ghat | WASH |  | Technical documents for procurement done | Advertisement period completed | 40 | Rectification period (15 days) | 100% | 30000 | 00182 - Netherlands |  | 182 | Netherlands
| Kikla | ERW Removal |  | Completed | Admin, financial and tech eval done | 80 | Works completed |  | 30000 | 00187 - Norway |  | 187 | Norway
| Kufra | Covid-19 |  |  | Review and endorsement done | 85 | Order placed |  | 30000 | 00232 - Switzerland |  | 232 | Switzerland
| Misurata | Unidentified |  |  | Submitted to CAP | 85 | In production |  | 30000 | 00717 - C/S ROK |  | 717 | C/S ROK
| Sebha |  |  |  | CAP-RACP done | 90 | Goods produced |  | 30000 | 10283 - Germany (KfW) |  | 10283 | Germay(KfW)
| Sirt |  |  |  | PO + Contract issuance done | 100 | In shipment to Libya |  | 30000 | 10480 - USAID |  | 10480 | USAID
| Tawergha |  |  |  | Completed | 100 | Goods at Libya |  | 30079 | 10159 - European Union Comm |  | 10159 | EU
| Tripoli | [5 empty] | In shipment to Final destination |  | 30000 | 11207 - US DOS G/TI |  | 11207 | US DOS G/TI
| Tripoli, Abu Salim |  |  | - |  |  | Reached final destination | Handed Over | 30000 | 11410 - UK (FCO) |  | 11410 | UK (FCO)
| Tripoli, Al-Swani | [5 empty] | Delivered | Handed Over | 30000 | 12113 - Canada (DFATD) |  | 12113 | Canada (DFATD)
| Tripoli, Al-Ssabiaa | [5 empty] | Substantial completion / handover done | Handed Over |  |  |  | 10283 141 | Germay(KfW) + Japan
| Tripoli, Ein Zara | [5 empty] | Completed prior to required service agreement |  |  |  |  | 10159 717 10283 | EU + C/S ROK + Germay(KfW)
| Tripoli, Central Tripoli | [5 empty] | Completed with service level & management agreements in place |  |  |  |  | 232 112 | Switzerland + France
| Tripoli, Al-Garabouli | [10 empty] | 12113 187 | Canada (DFATD) + Norway
Tripoli, Hay Al-Andoules
Tripoli, Janzour
| Tripoli, Ben Gashir |  |  |  | -
Tripoli, Sidi Al-Sayah
| Tripoli, Souq Al-Gomma |  |  | Overall Status |  |  | Remarks
| Tripoli, Souq Al-Khamees |  | Planned | In Development | rest |  | 100% complete (technically completed but pending final handover to end user)
| Tripoli, Tajoura |  | With Procurement | With Procurement | rest |  | 100% complete (pending documentation of final handover to end user)
| Ubari |  | Contract Issued | Contract Issued | rest |  | 100% complete |  |  | Support Type | Ben. Sector
| GMMRA |  | Completed | Completed | rest |  |  |  |  | Ambulance | Education
|  |  | Cancelled | Cancelled | rest |  |  |  |  | Borehole drilling | Energy
| Region |  |  | - | completed |  |  |  |  | Power Cable | Health
| East | [8 empty] | Medical Infrastructure | Public
| West | [8 empty] | Educational equipment | Solid waste
| South |  |  |  | Financial Helper |  |  |  |  | ERW removal | WatSan
[5 empty] | Contracted |  |  |  |  | Firetruck
[5 empty] | Estimated/Projected |  |  |  |  | Garbage Bin
Garbage truck
| Procurement Plan Ref | [8 empty] | Generator
| Completed | [8 empty] | IT equipment
| Contract Issued | [8 empty] | Medical Equipment
| With Procurement | [8 empty] | Public Service Equipment
| Priority 2 | [8 empty] | Public Infrastructure
| Further Funding | [8 empty] | Sewage Pump
| Cancelled | [8 empty] | Sewage suction truck
| To be cancelled | [8 empty] | Solar interventions
| Non SFL | [8 empty] | Substation
Transformers
Treatment plant
Truck
WASH equipment
Water Pump
Water Tanker